## Summary
Nexi Purchasing — full audit, v21.49
Prepared for Eyal Ben Ari · ABA Pardes · 04 October 2026 · four purchasing paths audited: Accounting ▸ 🛒 Purchasing Workspace (13-stage), Accounting ▸ 🧰 Purchasing Quick Tools, Inventory ▸ 🛒 Purchase Engine, Inventory ▸ 📝 Requests (+ their SOS / QuickBooks hooks). Static code review of every function plus a live click-through in Chromium.
Findings by severity
Severity | Count | Open | Share
critical | 5 | 5 | 7.042%
high | 16 | 16 | 22.54%
medium | 29 | 29 | 40.85%
low | 21 | 21 | 29.58%
Total | 71 | 71
Counts are as of this audit (static); filter the Findings sheet for live counts.
Findings by path
Path | Findings | Critical | High
Accounting ▸ 🛒 Purchasing Workspace | 28 | 3 | 8
Accounting ▸ 🧰 Purchasing Quick Tools | 28 | 0 | 3
Inventory ▸ 🛒 Purchase Engine | 3 | 0 | 2
Inventory ▸ 📝 Requests | 7 | 1 | 2
Inventory ▸ 📝 Requests → SOS | 3 | 1 | 1
Inventory ▸ 📝 Requests / Purchase Engine | 2 | 0 | 0
Live click-through (Accounting screens) | 0 | 0 | 0
What actually works today, end to end
• Nothing reaches SOS Inventory or QuickBooks from any purchasing screen: no PO is created in SOS, no bill in QuickBooks. The only working SOS calls are READS (open POs, items) and a receipt post that will 404 (wrong SOS entity).
• Accounting ▸ 🛒 Purchasing Workspace: a local tracker. A PR can be typed, "AI-checked" by a substring match, approved by anyone with Payroll edit, quoted as one typed total, awarded into a PO with invented line prices, received, invoiced and force-approved — all by the same person, numbered per device, and never synced with a timestamp.
• Accounting ▸ 🧰 Quick Tools: a comparison notebook plus an SOS PO-line import that counts cancelled POs and is silently trimmed to 250 rows; "Nexi RFQ outreach" opens mailto: links and logs them as sent; "supplier search" searches nothing.
• Inventory ▸ 🛒 Purchase Engine: draft POs that go nowhere and duplicate themselves; Inventory ▸ 📝 Requests: a purchase request for a manual item DEDUCTS stock (−18 on hand in the live test) and the worker forwards an unmapped body to SOS.
• Three unrelated PO notions (hydroPro_purch_pos, hydroPro_inv_draft_pos_v1, hydroPro_acct_purch_history), two supplier masters joined by name, three numbering schemes that collide across devices.
Recommendation
Stop patching four screens. Build ONE Purchasing module (rail entry, not under Accounting or Inventory) on one request → PO → receipt → invoice → payment record, with SOS APAC as the inventory ledger (PO and item receipt created there through the hnx-sync worker) and QuickBooks as the books (vendor + bill created through the nexi-qb worker). The Word design document Nexi_Purchasing_Module_Design_v21.49.docx describes it; the Fix plan sheet sequences it. P0 hotfixes (the critical rows) ship first because they lose money or stock today.

## Findings
ID | Path / screen | Area | Severity | index.html line(s) | What is wrong | How it fails for a user | Fix | Status | Phase
PW-01 | Accounting ▸ 🛒 Purchasing Workspace | permissions | critical | 21674; 96885–97205 | View is perm:null and only Approve / Award / Issue PO check canApprovePurch(). Save, submit, AI override, every stage advance, RFQ, quotes, amend PO, GRN, 'Complete anyway', add invoice and Force-approve invoice have no role check. | Any operator opens Accounting → Purchasing, logs a fake invoice against an issued PO and clicks Force approve: it shows Approved with their name. The same user can type quotes, record a GRN that raises SOS stock, or close a PR. | Give the view a real permission (viewAccounting) and a second gate (purchasing edit) on every mutating action; keep invoice approval behind the approver gate. | Open | P0 hotfix
PW-02 | Accounting ▸ 🛒 Purchasing Workspace | approval gate | high | 96347–96354; 96926–96931 | canApprovePurch() = admin, admin_secondary or anyone with Payroll EDIT (managePayroll). deptApprove never compares the requester with the approver. | A payroll clerk is a purchasing approver. One admin creates a ₱500,000 PR, submits, approves, awards and issues the PO alone; nothing stops it. | Dedicated approvePurchasing permission on the Accounting/Purchasing module; refuse approval/award by the requester. | Open | P1 consolidation
PW-03 | Accounting ▸ 🛒 Purchasing Workspace | approval gate | high | 96914–96918; 96539–96545 | AI 'not required' verdict lets any user close the PR as Completed, skipping Department Approval. No amount threshold, no multi-level chain; the override of the AI verdict is ungated. | The AI substring match (PW-16) says stock covers the need; a user clicks 'close as not required' and a legitimate ₱200k request vanishes without a manager seeing it. | Route 'not required' through the approval gate and add an amount-based chain stored on the PR. | Open | P1 consolidation
PW-04 | Accounting ▸ 🛒 Purchasing Workspace | numbering | critical | 96356–96362 | Document numbers come from a per-device counter in localStorage; the counter object merges as max(), while records merge per random id, so two records with the same number both survive. A lost counter restarts at 000001. | Eyal creates PR-2026-000007 in the office while Accounting creates one on a laptop → both are PR-2026-000007, both stay, the next is 000008. | Next number = max existing in the synced array + 1, re-checked after each cloud pull; one-time renumber of collisions. | Open | P0 hotfix
PW-05 | Accounting ▸ 🛒 Purchasing Workspace | sync | high | 96375–96388; 97141; 97189 | PR/RFQ/PO/GRN/invoice writes never set updatedAt, so the cloud merge ties on createdAt and keeps each device's own copy; stage and status are scalars that never converge. | Device A approves PR-7; device B still holds the old stage; after sync both machines disagree permanently and the cockpit counters differ per device. | Stamp updatedAt=Date.now() on every write. | Open | P1 consolidation
PW-06 | Accounting ▸ 🛒 Purchasing Workspace | invoice 3-way match | critical | 96776–96788; 97181–97191 | An invoice is matched against the WHOLE PO total ±1% and the GRN value ±2%; previously logged invoices are not summed. Duplicate check is invoice number only. | INV-1 for ₱100,000 (PO total) → Matched. INV-2, different number, same ₱100,000 → also Matched and approvable: double payment. Two honest partial invoices (₱40k + ₱60k) both show Exception. | Cumulative match: invoiced-to-date + this ≤ PO total; this ≤ received value not yet invoiced; per-line when lines exist. | Open | P0 hotfix
PW-07 | Accounting ▸ 🛒 Purchasing Workspace | PO | high | 97095–97099 | PO line prices are invented: PR estimates scaled by quote total ÷ estimate. With no estimates every PO line is ₱0 while the total is the quote. | PR lines entered without Est ₱ → PO issued with ₱0 unit prices; the supplier e-mail shows '@ 0'; GRN value stays 0; every invoice is 'Waiting GRN' forever. | Capture per-line unit prices on the quote and build the PO from them; refuse award when no prices exist. | Open | P1 consolidation
PW-08 | Accounting ▸ 🛒 Purchasing Workspace | award | high | 96717; 97082–97086 | The award button passes the supplier name inline; esc() turns ' into &#39; which the browser decodes back inside the onclick, so the JS string breaks. | Recommended supplier 'D'Agro Supply' → 'Approve award → generate PO' throws and nothing happens; the PR is stuck. | Pass only the PR id and recompute the recommended supplier inside award(). | Open | P1 consolidation
PW-09 | Accounting ▸ 🛒 Purchasing Workspace | quotes | medium | 96660–96687; 97074–97081 | A quote is one typed total plus lead days/terms/warranty: no per-line prices, no VAT-inclusive flag, currency, validity or attachment. Ranking is by total only; late quotes are accepted silently. | Supplier A ₱98,000 ex-VAT vs B ₱105,000 VAT-inclusive: A is 'cheapest' though B is cheaper. | Quote lines, vatIncluded, currency, validUntil; normalise before ranking; block quotes after closing date without a reason. | Open | P1 consolidation
PW-10 | Accounting ▸ 🛒 Purchasing Workspace | PR | high | 96475–96530; 97113 | No edit of an existing PR; rejection sends it to Draft with only a Submit button; no cancel/void for PR, RFQ or PO; 'Amendment' appends a sentence and changes nothing. | Manager rejects 'qty too high' → requester can only resubmit the same PR. Supplier delivers 80 of 100 → the PO stays 100 and can never be closed. | Editable Draft with revision, Cancel request, Cancel/close PO with reason, real PO revisions. | Open | P1 consolidation
PW-11 | Accounting ▸ 🛒 Purchasing Workspace | receiving | high | 97120–97172 | No over-receipt check; PO flips to Partially Delivered even when only rejected qty was entered; date cannot be back-dated; catalogue match uses a field PO lines never carry, so matching falls back to exact name equality. | Receiver types 1000 instead of 100 → posted to history and SOS. 'PVC pipe 2in' vs catalogue 'PVC Pipe 2" Sched 40' → 'not in catalogue — stock not raised': receiving almost never updates inventory. | Clamp to remaining, carry the SKU from a catalogue picker on the PR line, match on SKU first. | Open | P1 consolidation
PW-12 | Accounting ▸ 🛒 Purchasing Workspace | payment | high | 97193–97204 | The flow ends at invoice Approved: no payment record, due date, AP ageing, partial payment or Paid state; payTerms captured on the quote is never used. | Accounting approves 30 invoices; nobody can see which are paid or due this week. | Payment stage: due date from terms, Record payment, Paid state, AP-due alert. | Open | P1 consolidation
PW-13 | Accounting ▸ 🛒 Purchasing Workspace | QuickBooks | medium | whole block | Nothing in the Workspace references QuickBooks; no code anywhere creates a QB Bill or PO (the QB worker is read-only: query/entity/reports). | A user assumes approving an invoice posts a bill to QuickBooks; the books must be updated by hand and nothing flags it. | Add /qb/create-bill (and vendor) to the QB worker and a 'Post bill to QuickBooks' action storing qbBillId; until then say 'QB posting is manual' on screen. | Open | P2 integration
PW-14 | Accounting ▸ 🛒 Purchasing Workspace | SOS Inventory | medium | 96549–96579; 97151–97168; 165601 | SOS is only read for on-hand hints and written for catalogue-matched receipts. The PO itself is never pushed to SOS although /sos/create-po exists. | After issuing PO-2026-000003 the user looks for it in SOS APAC — it is not there; the receipt later arrives without a PO. | On Issue PO build the SOS purchase-order payload and call /sos/create-po; store sosId and show push state. | Open | P2 integration
PW-15 | Accounting ▸ 🛒 Purchasing Workspace | sourcing | medium | 95803–95805; 97067–97070 | Suppliers are free-text names everywhere (RFQ, PO, scorecard, history). The gather function unions two supplier stores by name and creates new vendor rows for every new spelling. | 'ACME Trading' and 'Acme Trading Corp' appear twice; the scorecard shows two suppliers with half the orders each. | supplierId on every record pointing at one canonical vendors store; de-duplicate by normalised name. | Open | P1 consolidation
PW-16 | Accounting ▸ 🛒 Purchasing Workspace | AI gate | medium | 96573–96580; 94890–94893 | The catalogue hint matches the FIRST item whose name merely contains the PR text; if its on-hand ≥ qty the verdict is 'No purchase — stock covers need' at 95% confidence. | PR 'Filter' matches 'Filter housing 10in' with 500 on hand → 'Purchase not required', and PW-03 lets the PR be closed on that. | Match SKU/code first, exact name second; substring hits are 'possible matches' only; a human picks the item. | Open | P1 consolidation
PW-17 | Accounting ▸ 🛒 Purchasing Workspace | PR | medium | 96547–96551 | 'Purchasing Review' and 'Inventory Verification' are one-click pass-throughs; no buyer assigned, no verification result stored. | Any user clicks through both stages in two seconds; nobody can later see who verified stock or what was on hand. | Persist buyer and a stock-check snapshot before advancing. | Open | P1 consolidation
PW-18 | Accounting ▸ 🛒 Purchasing Workspace | PR | medium | 96896–96907; 97173–97180 | 'Complete anyway' closes a PR with nothing received; the PO stays Issued and Mission Control keeps alerting 'PO past delivery date' forever. | After 20 completed-anyway PRs the Alerts box is permanently full of stale POs and real ones are cut off. | Require a reason, set PO 'Closed – short', exclude closed POs from alerts. | Open | P1 consolidation
PW-19 | Accounting ▸ 🛒 Purchasing Workspace | RFQ | medium | 96944–96975 | 'SENT' is stamped as soon as a mailto:/sms: link opens; nothing confirms a send. Reply rate divides by these. | No mail client on the PC → nothing sent, RFQ shows SENT, supplier later scored 0% reply. | Distinguish confirmed sends from opened drafts; count only confirmed. | Open | P1 consolidation
PW-20 | Accounting ▸ 🛒 Purchasing Workspace | scorecard | medium | 96817–96822 | On-time uses the PR need-by date, not the supplier's promised lead time; each GRN counts as a sample. | Supplier promised 5 days, delivered in 25, PR need-by was 30 days out → scored on-time. | Promised date = issued + lead days; compare with the first/completing GRN. | Open | P1 consolidation
PW-21 | Accounting ▸ 🛒 Purchasing Workspace | UI | medium | 96417–96436; 97216–97268 | innerHTML rewritten on every action; a 600 ms injector and a 4 s interval run forever; in-progress GRN/quote inputs live only in the DOM. | User fills six GRN boxes, a re-render fires, all inputs are blank again. | Keep in-progress values in state; drop the intervals (the view div is static). | Open | P1 consolidation
PW-22 | Accounting ▸ 🛒 Purchasing Workspace | UI | low | 96657 | Every RFQ e-mail/SMS is signed 'AteretPaz'. | Suppliers receive RFQs from ABA Pardes signed by another company. | Use the active company name. | Open | P1 consolidation
PW-23 | Accounting ▸ 🛒 Purchasing Workspace | analytics | low | 96856–96860; 96444 | 'Negotiation savings' = highest quote − awarded; 'Open value' uses PR estimates after a PO exists. | One absurd quote inflates savings to millions; open value disagrees with the PO list. | Savings vs estimate and vs second-lowest; PO total once a PO exists. | Open | P1 consolidation
PW-24 | Accounting ▸ 🛒 Purchasing Workspace | invoice 3-way match | low | 97192–97204 | Rematch can flip an Approved invoice to Exception with no audit; approve does not refuse an already-approved invoice or a Draft/Closed PO; a ₱0 PO always gives Exception. | Approved + Exception shown side by side; cockpit counts it as failed. | Skip rematch for Approved (or audit it); guard approve. | Open | P1 consolidation
PW-25 | Accounting ▸ 🛒 Purchasing Workspace | help | medium | guides block | No in-app guide describes the 13-stage Workspace (CLAUDE.md requires one). | Help on the Workspace finds nothing on stages, who approves, match rules. | Add the guide entry; regenerate nexidoc. | Open | P1 consolidation
PW-26 | Accounting ▸ 🛒 Purchasing Workspace | audit trail | low | 96363–96367; 96343 | Audit rows have no id so the sync treats the list as 'last writer wins'; who() falls back to 'user'. | Two devices append; the last pusher's list replaces the other's approval trail. | Give audit rows an id; refuse actions without a signed-in user. | Open | P1 consolidation
PW-27 | Accounting ▸ 🛒 Purchasing Workspace | sync | low | 96336–96337 | Writes never call hnxScheduleSync; rely on the 20 s dirty scan. | An approval seconds before closing the laptop never leaves the device. | Call hnxScheduleSync(k) in Sv(). | Open | P1 consolidation
PW-28 | Accounting ▸ 🛒 Purchasing Workspace | tests | low | tests/ | No regression test covers any purchasing store or screen. | Any fix can silently regress. | tests/purchasing suite driving a PR through all stages. | Open | P1 consolidation
QT-01 | Accounting ▸ 🧰 Purchasing Quick Tools | RFQ outreach | high | 95929; 96147–96167 | 'Send RFQ' says Nexi dispatches e-mail; it uses the user's own browser EmailJS keys if pasted, else just opens mailto: and logs 'sent'. No Nexi worker, no nexi@ mailbox, no server log. | Buyer ticks 4 suppliers → toast 'RFQ dispatched · 4 email'; the popup blocker allowed one mailto; 3 suppliers get nothing but the log shows 4 sent. | Real sender route (Gmail bridge under nexi@abapardes.com.ph with buyer in CC, supplier allow-list); until then log 'draft opened', not 'sent'. | Open | P1 consolidation
QT-02 | Accounting ▸ 🧰 Purchasing Quick Tools | RFQ outreach | high | 96168–96175 | SMS 'send' opens an sms: link with the + of +63 URL-encoded; desktop PCs have no SMS handler; errors are swallowed; logged as sent. | Office PC: nothing opens, no error, RFQ Log says SMS sent. | Disable SMS on desktop or use a gateway route with a message id. | Open | P1 consolidation
QT-03 | Accounting ▸ 🧰 Purchasing Quick Tools | history | high | 233559; 233678 vs 94808–94856 | hydroPro_acct_purch_history is on the auto-slim list (keep newest 250 rows once >120 KB, every 45 s) while the SOS importer writes one row per PO line; the importer then re-adds what was trimmed. | After a year of POs, 'total logged spend' and 'times bought' silently exclude older purchases and change between refreshes. | Remove the key from the slim rules or import incrementally into per-product×supplier aggregates. | Open | P1 consolidation
QT-04 | Accounting ▸ 🧰 Purchasing Quick Tools | history | medium | 94814–94856 | Every SOS PO line is imported as a purchase: cancelled/voided POs included, ordered qty used instead of received. | A cancelled ₱180,000 PO shows as a real purchase and drives 'cheapest historically'. | Skip cancelled/void; use received qty (or /sos/item-receipts). | Open | P1 consolidation
QT-05 | Accounting ▸ 🧰 Purchasing Quick Tools | integration | medium | 94808; worker 1617/1786 | The screen never shows which SOS account the single token is on (APAC per CLAUDE.md); rows carry no company tag. | Supply POs raised in APTI → import returns the other company's POs or nothing and the buyer cannot tell. | Show accountInfo.companyName in the banner; stamp company on rows; block import when unknown. | Open | P2 integration
QT-06 | Accounting ▸ 🧰 Purchasing Quick Tools | integration | medium | 95268–95269; 94898–94903 | Banner says 'QuickBooks ● cached' as a history source; nothing reads QuickBooks. | User expects QB bills in history; they never appear. | Remove the chip or implement a QB bills import. | Open | P2 integration
QT-07 | Accounting ▸ 🧰 Purchasing Quick Tools | supplier search | medium | 95974; 95929; 96038–96068 | 'Add a supplier Nexi found on the web' — there is no web search, no API, no geocoding; the typed name is saved with source 'nexi-web'. | Manager asks for rockwool suppliers near Tarlac; only already-typed vendors appear; the buyer assumes a search ran. | Rename to 'Add a supplier manually' or implement a real search. | Open | P1 consolidation
QT-08 | Accounting ▸ 🧰 Purchasing Quick Tools | supplier search | medium | 94925–94928; 95284–95285 | Default base location is Manila (14.600, 120.984) labelled 'AteretPaz farm'. | Every distance and radius tier is measured from Manila; a Pampanga supplier 20 km away shows ~70 km. | Seed from Geographic Setup or show 'base not set' and disable radius filtering. | Open | P1 consolidation
QT-09 | Accounting ▸ 🧰 Purchasing Quick Tools | supplier search | low | 95145–95151 | Coordinates captured with three prompt() dialogs keyed by lowercased name. | Rename a vendor → coordinates orphaned; comma decimals give NaN silently. | Small form keyed by vendor id. | Open | P1 consolidation
QT-10 | Accounting ▸ 🧰 Purchasing Quick Tools | supplier search | low | 94966–94982 | Address fallback reads fields neither supplier master has: dead code. | None visible. | Add address to the vendor master or delete the branch. | Open | P1 consolidation
QT-11 | Accounting ▸ 🧰 Purchasing Quick Tools | supplier master | medium | 95207–95226 vs 95807 | Two supplier masters reconciled by name only; some helpers read one, some both. | A supplier maintained in Inventory ▸ Master Data shows NEW on a comparison but EXISTING in outreach. | One merged helper; one canonical master with ids. | Open | P1 consolidation
QT-12 | Accounting ▸ 🧰 Purchasing Quick Tools | supplier master | medium | 96053–96056; 97067–97075; 94732–94735 | Three writers append vendors with no duplicate check; the Vendors list has no edit. | 'Acme Hydro' added twice with a typo; only remedy is delete and re-add. | Upsert by normalised name; inline edit. | Open | P1 consolidation
QT-13 | Accounting ▸ 🧰 Purchasing Quick Tools | UI | medium | 95581; 95997; 21674–21675 | Links to switchView('acct_vendors') target a view registered in no module, so the header flips to PRODUCTION. | Click 'Add vendors in Vendors' → module header says Production. | Register acct_vendors under Accounting. | Open | P1 consolidation
QT-14 | Accounting ▸ 🧰 Purchasing Quick Tools | permissions | medium | 21675; 95286 | perm:null: every role can open the screen, delete comparisons/history, clear SOS history, rewrite the RFQ template and send RFQs in the company's name. | A greenhouse user finds the screen via search and clears all SOS history. | perm viewAccounting; destructive buttons behind a manage permission. | Open | P1 consolidation
QT-15 | Accounting ▸ 🧰 Purchasing Quick Tools | RFQ outreach | medium | 95645–95647; 95836–95844 | Banner promises ranking by reply rate; the sort never uses it. | A supplier that never answered stays above one that always quoted. | Add responseRate to the sort or drop the claim. | Open | P1 consolidation
QT-16 | Accounting ▸ 🧰 Purchasing Quick Tools | RFQ outreach | medium | 96183–96203 | A quote mirrors into history only when 'quoted' is selected AFTER the price is typed; the UI order is the reverse; re-selecting duplicates. | Buyer marks 3 replies quoted then types prices → no quote rows; later re-selecting inserts duplicates. | Mirror on either change; upsert by id. | Open | P1 consolidation
QT-17 | Accounting ▸ 🧰 Purchasing Quick Tools | comparison | medium | 96193–96201 vs 95197–95205 | Quote rows (qty 0) sit in the same history store and are counted as purchases. | A supplier who merely quoted shows EXISTING '1× before · 0 units'. | Exclude source rfq-quote from purchase counts. | Open | P1 consolidation
QT-18 | Accounting ▸ 🧰 Purchasing Quick Tools | help | medium | 286935–286938 | The Help guide has the two Purchasing screens' descriptions swapped and covers no SOS import, outreach or tiers. | Staff open the wrong screen. | Swap and extend the guide; regenerate nexidoc. | Open | P1 consolidation
QT-19 | Accounting ▸ 🧰 Purchasing Quick Tools | RFQ outreach | low | 96095–96104; 96208–96211 | Preview uses alert(). | 15-line RFQ in a native alert; disappears under 'prevent dialogs'. | In-app modal with copy. | Open | P1 consolidation
QT-20 | Accounting ▸ 🧰 Purchasing Quick Tools | comparison | low | 95683; 95699; 95749; 95764 | Validation via alert(). | Inconsistent with toasts on the same screen. | showToast + focus. | Open | P1 consolidation
QT-21 | Accounting ▸ 🧰 Purchasing Quick Tools | history | low | 94800–94802; 95276 | Sync meta 'running' is written before the fetch and synced cloud-wide. | Second PC shows 'syncing…' for days after the first PC closed mid-import. | Keep running state in memory with a stale timeout; device-local key. | Open | P1 consolidation
QT-22 | Accounting ▸ 🧰 Purchasing Quick Tools | integration | low | 94808 | Import pulls every PO in the account on every click (up to 45×200), no cursor. | Tens of seconds per click; SOS throttling. | Pass from=<last sync> and store a high-water mark. | Open | P2 integration
QT-23 | Accounting ▸ 🧰 Purchasing Quick Tools | RFQ outreach | low | 28963–28970; 96120 | EmailJS keys sync to every device; reply_to defaults to the supplier's own address. | Supplier hits Reply and mails themselves; the buyer never sees the quote. | Default reply-to to the requester / nexi@; keep keys device-local. | Open | P1 consolidation
QT-24 | Accounting ▸ 🧰 Purchasing Quick Tools | UI | low | 95616 | toISOString() on a missing sentAt throws and blanks the RFQ Log tab. | One bad row blanks the whole tab. | Guard the date. | Open | P1 consolidation
QT-25 | Accounting ▸ 🧰 Purchasing Quick Tools | comparison | low | 96213–96217; 95846–95852 | 'Ask Nexi for more quotes' passes no estimated value, so the radius tier defaults to the smallest. | A ₱500k comparison starts at 25 km. | Pass the estimated value. | Open | P1 consolidation
QT-26 | Accounting ▸ 🧰 Purchasing Quick Tools | UI | low | 95956; 96060; 96215 | Company signature hard-coded 'AteretPaz' in three places. | APAC RFQs go out signed AteretPaz. | Active company legal name. | Open | P1 consolidation
QT-27 | Accounting ▸ 🧰 Purchasing Quick Tools | UI | low | 95511 | Filter box rebuilds the whole view per keystroke and relies on the global caret-keeper. | Focus loss returns if that list is edited. | Filter the table body in place. | Open | P1 consolidation
QT-28 | Accounting ▸ 🧰 Purchasing Quick Tools | UI | low | 94780; 95262; 96422 | Three different names for one screen; the Workspace is also titled 'Purchasing'. | Users cannot tell which purchasing screen they are on. | Use the nav label as the title. | Open | P1 consolidation
IV-01 | Inventory ▸ 📝 Requests → SOS | worker /sos/create-po | critical | workers/hnx-sync-worker.js 1803–1823; index.html 165677–165683 | The worker forwards the app's generic request body verbatim to SOS /purchaseorder with a literal 'TODO(verify): transform body': no vendor id, no item id, no lines[]. Same for adjustment/transfer/shipment. | Procurement approves a Purchase Request, warehouse presses 'Confirm issued → post to SOS'; SOS rejects it; the clerk is told to create the PO by hand and paste a reference. | Implement the SOS v2 mapping in the worker (vendor by name, item by SKU, lines[], date, comment=ref), idempotency on idemKey, clear errors back to the app. | Open | P0 hotfix
IV-02 | Inventory ▸ 📝 Requests | confirmIssue for purchase | critical | 165516–165518; 165616–165634; 165600 | A 'purchase' request for an app-only item is booked as a stock OUT and marked completed; no PO is ever raised. | Live test: Purchase Request for 20 Test Gloves (2 on hand) → Confirm issued → on hand 2 → −18, movement 'out', status completed. | Purchases never move stock: status 'ordered' / 'awaiting-sos'; stock rises only on receipt. | Open | P0 hotfix
IV-03 | Inventory ▸ 🛒 Purchase Engine | Purchase Engine → SOS | high | 166211; 166216–166231 | Draft POs are never sent anywhere: no /sos/create-po call, no hand-off to Accounting or Requests; 'Mark ordered' is a flag. | User generates a draft PO and marks it ordered; nothing is ordered in SOS; the cockpit counts it as a PO. | Convert 'Generate draft PO' into creating the one PO lifecycle (Purchasing module) that posts to SOS. | Open | P2 integration
IV-04 | Inventory ▸ 🛒 Purchase Engine | reorder list | high | 166111–166118; 166079 | Ordered/draft local POs do not offset the reorder list; the same item is suggested again and duplicates are generated. | Live: Acme Supply generated twice → PO261004-001 and -003 with the same line; after Mark ordered the item is still listed. | Count local draft/ordered POs as on-order; warn on duplicate SKU. | Open | P1 consolidation
IV-05 | Inventory ▸ 📝 Requests | approval chain | high | 164845; 165433–165442; 164851 | Every chain level (Dept Manager, Division Head, VP/COO, Procurement, Accounting, HR) is approved by whoever has manageInventory; requester may approve own request. | Live: one admin approved all four levels in 4 clicks then confirmed the issue himself. | Approval matrix mapping levels to people/roles; no self-approval; exec override admin only. | Open | P1 consolidation
IV-06 | Inventory ▸ 📝 Requests | Warehouse reorder | high | 211176–211179; 164866 | Warehouse 'reorder' prefills a request without a type, so it defaults to Stock Issue and posts a NEGATIVE adjustment instead of a PO. | Warehouse clicks reorder on a low item, submits, approves, confirms: stock is deducted further. | Prefill type 'purchase' and supplier. | Open | P1 consolidation
IV-07 | Inventory ▸ 📝 Requests → SOS | worker receipt mapping | high | workers/hnx-sync-worker.js 1799 vs 1622 | /sos/create-receipt maps to '/receivinginventory' (marked VERIFY) while the read route uses the real entity 'itemreceipt'. | Every Accounting GRN receipt will 404 in SOS once the worker is reachable. | Map to /itemreceipt with vendor, lines and PO reference; test in sandbox. | Open | P2 integration
IV-08 | Inventory ▸ 📝 Requests | retry / duplicates | medium | 165669–165674; 165696–165701 | Retry on a completed request regresses it to awaiting-sos on failure and creates a second SOS document on success. | Live: completed with PO-MANUAL-1 → Retry → status back to awaiting-sos. | Restore status on failure; worker dedupe on idemKey. | Open | P1 consolidation
IV-09 | Inventory ▸ 📝 Requests | offline message | medium | 165703–165705 vs 165379 | The real error text is wiped by the immediate re-render; no 'cloud unreachable' detection. | Any worker outage looks like 'not configured'. | Store sosError on the record and render it. | Open | P1 consolidation
IV-10 | Inventory ▸ 📝 Requests / Purchase Engine | numbering | medium | 164846; 166222 | Request numbers = today's local count+1; PO refs = array length+1. | Two devices raise IR1004-26-001; deleting a draft then generating reuses an existing ref. | max existing +1 or cloud counter. | Open | P1 consolidation
IV-11 | Inventory ▸ 📝 Requests | completion semantics | medium | 165541–165549; 165618–165632 | Pasting any text as SOS reference marks a purchase 'completed'; nothing links it to a receipt; the request leaves the open queue before goods arrive. | Procurement pastes a PO number; the warehouse has no signal the goods are expected. | 'ordered' state; close only on receipt. | Open | P1 consolidation
IV-12 | Inventory ▸ 🛒 Purchase Engine | open-PO offset | low | 166034–166037; 166055 | After one failed SOS fetch the offset is never retried for the session. | Worker briefly down at first render → whole session without on-order offset. | Retry after N minutes / Refresh. | Open | P1 consolidation
IV-13 | Inventory ▸ 📝 Requests | data typing | low | 164960–164961; 165423 | qty and unitCost stored as strings. | Any arithmetic without num() concatenates. | Coerce in submit(). | Open | P1 consolidation
IV-14 | Inventory ▸ 📝 Requests → SOS | account | medium | workers/hnx-sync-worker.js 1596; 1701–1731 | One SOS token for all writes; a PO would land in whichever account the worker is on (APAC) with no selector. | An APTI purchase posts into APAC. | Company field on the request; refuse writes that do not match the token's account. | Open | P2 integration
IV-15 | Inventory ▸ 📝 Requests / Purchase Engine | help | low | 285815; 286892 | Guide says a Purchase Request moves nothing until received and the Engine produces POs ready for sign-off; neither matches the code. | Users trust the guide. | Update after IV-02/03. | Open | P1 consolidation

## Stores
localStorage key | Owner path | What it holds | Cloud sync / external
hydroPro_purch_prs | Accounting ▸ Workspace | PR records: number, title, dept, need-by, lines, stage, workflow log, AI analysis | cloud (generic rule); no updatedAt
hydroPro_purch_rfqs | Accounting ▸ Workspace | RFQ: suppliers, sent channel, typed quote totals, award | cloud; no updatedAt
hydroPro_purch_pos | Accounting ▸ Workspace | PO: supplier name (free text), scaled line prices, status, revisions | cloud; never pushed to SOS
hydroPro_purch_grns | Accounting ▸ Workspace | GRN lines accepted/rejected | cloud
hydroPro_purch_invoices | Accounting ▸ Workspace | Supplier invoice: one amount per PO, match status, approval | cloud; never to QuickBooks
hydroPro_purch_counters | Accounting ▸ Workspace | per-device running numbers PR/RFQ/PO/GRN | cloud (max-merge → duplicates)
hydroPro_purch_audit | Accounting ▸ Workspace | audit trail (no ids) | cloud (last writer wins)
hydroPro_acct_purch_history | Accounting ▸ Quick Tools | purchase ledger: manual rows, SOS PO lines, RFQ quote rows | cloud; auto-trimmed to 250 rows
hydroPro_acct_purch_comparisons | Accounting ▸ Quick Tools | 3-quote comparison sheets | cloud
hydroPro_acct_purch_outreach | Accounting ▸ Quick Tools + Workspace | RFQ log rows with full message text | cloud
hydroPro_acct_purch_rfq_template / _base_location / _supplier_locations / _sync_meta | Accounting ▸ Quick Tools | template text; Manila default base; typed coordinates; SOS import status | cloud (sync meta device status pushed to all PCs)
hydroPro_acct_vendors | Accounting (shared) | vendors master; three writers, no duplicate check, no edit | cloud
hydroPro_inv_suppliers_v1 | Inventory ▸ Master Data | suppliers with score/lead time; no address | cloud
hydroPro_inv_requests_v1 | Inventory ▸ Requests (+ Maintenance, Warehouse, Accounting GRN) | item requests: purchase/issue/transfer/return/receipt/shipment with chain and SOS post state | cloud; SOS via per-request POST
hydroPro_inv_draft_pos_v1 | Inventory ▸ Purchase Engine | draft POs (ref POyymmdd-NNN, supplier, lines, status) | cloud only; never posted
hydroPro_inv_stock / _movements | Inventory | app-only stock rows and movements (bookLocal) | cloud only
hydroPro_emailjs_config_v1 | Quick Tools RFQ send | user's EmailJS keys | cloud (one user's keys reach every device)

## Fix plan
Phase | Version | Item | Covers findings | Owner / needs from Eyal | Status
P0 hotfix | v21.50 | Purchase requests never move stock; purchases get an "ordered" state | IV-02, IV-06, IV-11 | Nexi | Planned
P0 hotfix | v21.50 | Cumulative 3-way match (no double invoice), approve guards | PW-06, PW-24 | Nexi | Planned
P0 hotfix | v21.50 | Permissions: viewAccounting on both Accounting screens, edit gate on every mutating action, dedicated approvePurchasing, no self-approval | PW-01, PW-02, PW-03, QT-14, IV-05 | Nexi · Eyal confirms who approves (matrix) | Planned
P0 hotfix | v21.50 | Numbers from max+1 on the synced array; updatedAt on every write; audit rows with ids | PW-04, PW-05, PW-26, PW-27, IV-10 | Nexi | Planned
P0 hotfix | v21.50 | Award button name bug; PO line prices from quote lines; receiving clamp + SKU picker | PW-07, PW-08, PW-11 | Nexi | Planned
P0 hotfix | v21.50 | Quick Tools history no longer auto-trimmed; cancelled POs skipped; RFQ logged as draft not sent; QB chip removed; web-search wording removed | QT-01, QT-02, QT-03, QT-04, QT-06, QT-07 | Nexi | Planned
P1 consolidation | v21.5x | ONE Purchasing module in the rail: Requests (from any module), Approvals (matrix), Sourcing & quotes, Purchase orders, Receiving, Supplier invoices, Payments, Suppliers (one master with ids), Reports. Accounting Workspace + Quick Tools + Inventory Purchase Engine become doors into it; old stores migrated once. | PW-09, PW-10, PW-12, PW-15, PW-17–PW-23, PW-25, PW-28, QT-08–QT-13, QT-15–QT-28, IV-03, IV-04, IV-08–IV-10, IV-12, IV-13, IV-15 | Nexi · design doc sign-off by Eyal | Design (docx)
P2 integration | worker 3.8 + app | SOS APAC: create PO (/sos/create-po mapped to SOS v2 purchaseorder with vendor id + item ids + lines), create item receipt against the PO, read open POs for on-order; company guard | IV-01, IV-07, IV-14, PW-14, QT-05, QT-22 | Nexi writes the worker; Eyal deploys hnx-sync 3.8 in Cloudflare and confirms the SOS account (APAC) and a test vendor/item | Design (docx)
P2 integration | nexi-qb + app | QuickBooks: create Vendor and Bill from an approved supplier invoice (/qb/create-vendor, /qb/create-bill), store qbBillId, read bill payments back for the Paid state | PW-13, QT-06 | Nexi writes the worker; Eyal deploys nexi-qb and reconnects QB OAuth with write scope | Design (docx)
P2 integration | Gmail bridge | RFQ e-mails really sent from nexi@abapardes.com.ph with the buyer in CC and a supplier allow-list; replies parsed into quotes | QT-01, QT-15, QT-16, QT-23, PW-19 | Nexi (Apps Script) · Eyal installs the trigger under nexi@ | Design (docx)