## Summary
Item | Value
Audit | Nexi CRM — every screen, control and connection
Date | 2026-09-27
Fixed in | v21.18
Findings | 75: 65 fixed · 1 partly · 3 open · 6 not a defect
Re-walk after fixes | 16/16 screens, 263 clicks, 0 page errors; legacy qb-api calls 152 → 2; the two snag panels captured in this walk (numeric createdAt) were fixed right after it — covered by tests/payroll/crm-audit.test.js
Regression | tests/payroll/crm-audit.test.js — 6 cases; full suite run before release

## Findings
# | Severity | Screen | Finding | Where | How to reproduce | Found by | Status after v21.18
1 | HIGH | (Accounting) | The legacy qb-api worker was called 152× in one session: the 12-month backfill of 6 reports × 24 months ran at boot on every PC every day (not a loop). Now it runs only once Accounting is opened; 2 calls per session otherwise. | boot timers of the monthly QuickBooks pullers | Open Nexi, watch the network tab. | Chromium run | FIXED v21.18
2 | HIGH | crm_brain | Permission gap: crm_brain is injected into the CRM menu with `perm:null` (getVisibleViews wrapper :139464) and its switchView wrapper (:139480) short-circuits before the original switchView runs, so the guards map and can() are never consulted for any *_brain view. Any signed-in user can open the CRM cockpit (leads, quotes, orders, meetings, prospects) regardless of viewCRM. | /home/user/hydropro/index.html:139464 and :139480-139488 | As a user without viewCRM, run switchView('crm_brain') — the CRM cockpit renders with live lead/quote/order counts. | code review | FIXED v21.18
3 | HIGH | crm_cmd | Permission gap: crm_cmd is registered with perm:'viewCRM' (:21784) but is missing from the switchView guards map (:22455 lists crm_dash…crm_sales only). A direct switchView('crm_cmd'), #hash deep link, console call or Nexi navTo bypasses the viewCRM check — the same class of bug fixed for pack_cmd (v13.14 PACK-F3) and qc_cmd (QC-F5). | /home/user/hydropro/index.html:22455 (guards map) vs :21784 (registry) | Log in as a user without viewCRM, run switchView('crm_cmd') in console — the cockpit renders. | code review | FIXED v21.18
4 | HIGH | crm_cmd | 'Open leads' KPI/box/AI row counts the wrong field: leads carry `stage` ('won'¦'lost'¦'on_hold'…, CRM_STAGES :66032) and never `status` (0 uses of l.status in the base CRM). MCC_LIVE.crm_cmd filters `!/won¦lost¦closed¦converted/i.test(x.status)` so every lead — including all won and lost — is reported as open. | /home/user/hydropro/index.html:245724 | Have 3 won + 2 lost + 1 new lead; crm_cmd shows 'Open leads 6', while 🏠 Overview shows Active Leads 1. | code review | FIXED v21.18
5 | HIGH | crm_pipeline | Pipeline / Overview / lead detail crashed ("hit a snag") for any lead with a numeric createdAt (imports, Potential Customers): localeCompare / .slice on a number. | renderCRMPipelinePage, dashboard stale check, lead detail | Seed a lead with createdAt: Date.now(); open Pipeline, Overview, a lead detail. | Chromium run | FIXED v21.18
6 | HIGH | crm_potential | Permission gap: crm_potential is registered in MODULES.crm.views with perm:null (@177753) and is absent from the switchView guards map (@22455 lists crm_dash…crm_sales but not crm_potential). The only CRM screen with no 'viewCRM' gate — any signed-in role can open it via switchView('crm_potential') / Nexi navTo (VIEW_SYN maps 'potential customers' to it @180167) and edit/delete/export the prospect list. | index.html:177753 (perm:null), 22455 (guards), 177342 (EXTRA_SUBTABS entry has no perm field) | Log in as a role without viewCRM, run switchView('crm_potential') (or ask Nexi 'open potential customers'): screen renders with Add/Delete/Export buttons; crm_leads would be refused with 'Access denied'. | code review | FIXED v21.18
7 | HIGH | sales_docs | Permission gap: registered with perm:null, and the nav filter @21944 only hides a tab when v.perm is truthy, so every role — including roles with viewCRM:false (@61103, 61129) — sees and can open Sales Documents, upload/rename/delete documents and push files to R2. Every other CRM screen is perm:'viewCRM'. | index.html:244463 | Log in as a role with viewCRM:false; CRM → 📚 Sales Documents is visible and fully editable. | code review | FIXED v21.18
8 | MEDIUM | crm_brain | Duplicate renderers fighting on timers: the brain block re-installs its wrapper every 5 s (:139503), the v1900 cockpit re-hooks every 5 s (:273769) and re-renders every 400 s/60 s (:273718), and the extensions-pack hook (:115190) still paints renderModBrain with fabricated tiles ('Active customers 142', 'Active leads 38', '₱2.4M pipeline', 'Reorder rate 78%') plus canned insights naming 'Victoria Homes' and 'Pardes Distrib' (:130421) into #hnx-crm_brain-body. Which panel the user sees depends on wrapper install order in the first ~1.5 s after load (installSV retries at 300 ms, ensureHooks at 500/1500 ms); if crm_brain is opened before the brain wrapper is installed the fake numbers show and the v1900 timer then skips the body because it has content without .ceack (:273729). | /home/user/hydropro/index.html:130119-130135 (fake tiles), :130421 (fake insights), :115190, :273729 |  | code review | FIXED v21.18
9 | MEDIUM | crm_brain | crm_brain is not in the MODULES.crm registry (brain registrations are commented out at :115144) and not in SCREEN_GUIDE (:286106); the Help centre cannot list it under m_crm (guideScreens uses V.mods and SCREEN_GUIDE only, :286025-286031) and no guide describes the cockpit. | /home/user/hydropro/index.html:115144, :286106 |  | code review | FIXED v21.18
10 | MEDIUM | crm_calendar | perm:null on a CRM screen: every other CRM view carries perm:'viewCRM' but the calendar entry is pushed with perm:null (:284261) and is absent from the base switchView guard map, so any role sees CRM tasks/meetings/deadlines and can add items once it reaches the view (module rail visibility is the only gate). | index.html:284261 | Log in as a role without viewCRM and call switchView('crm_calendar'): calendar renders with all CRM items. | code review | FIXED v21.18
11 | MEDIUM | crm_cmd | 'Orders this month' peso value is always blank: valMo sums `o.total¦¦o.amount¦¦o.value¦¦o.grandTotal`, but order records store none of those — the app computes totals from items via _o_total(o) (:71481, qty×unitPrice). The KPI sub-line and the box text 'booked ₱… this month' never appear. | /home/user/hydropro/index.html:245730 (valMo) vs :71481 (_o_total) | Create an order with items this month; crm_cmd 'Orders — YYYY-MM' box shows the count but no peso amount. | code review | FIXED v21.18
12 | MEDIUM | crm_cmd | Registry title promises 'process checks + KPIs' but the middle analysis panel is a stub for CRM: MODULE_CHECKLIST_DEFAULTS has no 'crm' entry (keys are hr, it, quality, inventory, security, maintenance, logistics, packaging, production, irrigation), so _mccChecks always renders the empty 'no checklist configured' placeholder. | /home/user/hydropro/index.html:17921 (empty branch) and :104023 (defaults) | Open CRM → 🎯 Command Center; centre panel is the ☑️ empty placeholder. | code review | FIXED v21.18
13 | MEDIUM | crm_customer_care | The v21.08 Compliance dropdown grouping (hnx-cea-dropdowns-v2108) never runs on this screen after the move: ceaRoot() :283623 only accepts views whose id starts with cea_/lic_, so the ➕ New ▾ / Actions ▾ menus promised for 'every Compliance screen' are gone from Customer Care — button rows render raw. Every other CEA screen keeps them. | index.html:283623 (ceaRoot) vs :284134 (CC='crm_customer_care') | Open CRM & Sales → 🤝 Customer Care, compare the action-button row with Compliance → Regulatory: no dropdown on Customer Care. | code review | FIXED v21.18
14 | MEDIUM | crm_customer_care | Customer Care renders 226 KB of HTML with 157 controls on one screen; slow on shop-floor PCs. | ceaView_customers | Open CRM ▸ Customer Care on Edelyn's PC. | Chromium run | OPEN — performance; pagination planned
15 | MEDIUM | crm_customer_files | No help-guide mapping: no SCREEN_GUIDE entry and no mention of 'Customer 360° Files' in the m_crm guide. | index.html:286112, :285386 | Open 📁 Customer 360° Files → 🆘: no screen guide. | code review | FIXED v21.18
16 | MEDIUM | crm_customer_files | Reads customers only from hydroPro_crm_leads; records created in 🆕 Customer Master (hydroPro_crm_customer_master) and their uploaded documents (hydroPro_crm_master_docs) are invisible here — duplicate document templates in two stores. | index.html:103453–103460 | See crm_master issue 2. | code review | FIXED v21.18
17 | MEDIUM | crm_customer_matrix | No help-guide mapping (no SCREEN_GUIDE entry, not described in m_crm). | index.html:286112, :285386 | Open 📊 Customer Matrix → 🆘: no screen guide. | code review | FIXED v21.18
18 | MEDIUM | crm_customer_matrix | Same data split as 360° Files: Customer Master customers/documents are not counted, so compliance percentages ignore every customer that exists only in hydroPro_crm_customer_master. | index.html:103764–103765 | Matrix shows 'No customers yet' while Customer Master holds approved customers. | code review | FIXED v21.18
19 | MEDIUM | crm_customers | Two divergent QuickBooks customer paths: crm_customers reads the legacy qb-api worker (qb-api.eyalbenari99.workers.dev/api/qb/customers, key in hydroPro_qb_legacy_key_v1), while crm_sales_intel (v21.13) reads the nexi-qb worker /qb/customers with a realm (APAC/APTI). The two feeds can disagree and require two separate keys/setups; with no legacy key entered the customer block shows 'Could not load QuickBooks customers — HTTP 401' on every device. | index.html:66689 (QB_API_BASE), 66722 (fetch), 66693 (hnxQbKey) vs 283705 (nexi-qb loadCustomers) | Open CRM > Customers on a device where the legacy key was never entered (banner @66704 only appears for admins after 20s) — QuickBooks Customers panel errors while Sales Intel loads fine. | code review | PARTLY — keys unified; one feed once nexi-qb is deployed (your task A1)
20 | MEDIUM | crm_customers | Store hydroPro_crm_customers is read by 7 places but nothing ever writes it (only hydroPro_crm_leads stage=won and hydroPro_crm_customer_master are real). Readers always see an empty list: Nexi name suggestions @82541, custNames() @181241, contact directory @215784/215819/216201, exec metrics @245731 (falls back to master), PHOTO_SRC.crm @246342. v20.44 already fixed two other readers (28782, 179033) but left these. | index.html:82541, 181241, 215784, 215819, 216201, 245731, 246342 | grep -n "setItem('hydroPro_crm_customers'" index.html returns nothing; any feature listed reads an empty array. | code review | FIXED v21.18
21 | MEDIUM | crm_marketing | Screen is a permanent placeholder: 'Marketing tracking page coming next' with no store, no form, no data. It is still listed as a live CRM tab (📢 Marketing) with title 'Campaigns and marketing activities'; no later patch block enhances it (only base refs at 6098/21799/22636/67470). | index.html:67470-67482, 21799 | Open CRM > Marketing: only a static banner and empty-state card. | code review | FIXED v21.18
22 | MEDIUM | crm_master | No help-guide mapping: SCREEN_GUIDE :286112–286117 has no crm_master entry and the m_crm guide :285386–285417 never mentions Customer Master, so the 🆘 button on this screen offers no guide (CLAUDE.md: a screen without guide coverage is incomplete). | index.html:286112 (SCREEN_GUIDE), :285386 (m_crm) | Open 🆕 Customer Master → 🆘: no 'This screen' guide suggestion. | code review | FIXED v21.18
23 | MEDIUM | crm_master | Two parallel customer/document models: Customer Master stores customers in hydroPro_crm_customer_master and their scans in hydroPro_crm_master_docs, while 📁 Customer 360° Files / 📊 Customer Matrix read only hydroPro_crm_leads (stage won/customer/active) and hydroPro_crm_customer_files. The same document types (business_permit, bir_2303, sec_dti, nda) are stored in two shapes, and an Approved master customer never appears in 360° Files or the Matrix; there is no bridge between the stores. | index.html:155723–155724 vs :103431 and :103454 | Create + approve a customer in Customer Master with all documents uploaded; open Customer 360° Files: customer absent; Matrix shows 'No customers yet' if no won lead exists. | code review | FIXED v21.18
24 | MEDIUM | crm_orders | Store shape mismatch with a consumer: order records store no total field (record built @71776/_o_collect @72109 keeps items[] only; totals are derived by _o_total). The CRM command-center live tile MCC_LIVE.crm_cmd @245730 values the month's orders with num(o.total¦¦o.amount¦¦o.value¦¦o.grandTotal), so 'orders value this month' on crm_cmd is always ₱0 regardless of real orders (the cockpit checks @277043 do it right via oTot fallback to items). | index.html:245730 (consumer) vs 71776/72109 (record shape) | Create an order with lines qty 10 x ₱100 in Orders; open CRM → Command Center: month order value shows 0. | code review | FIXED v21.18
25 | MEDIUM | crm_potential | Duplicate renderer + double render on every navigation: window.renderPotentialCustomers is defined twice (original @177251 and pagination override @177801, both keep their own copy of the table markup, filters and STAGES), and two independent switchView wrappers (@177349 at 80ms and RMAP adapter @177767 at 60ms) each call it, so each visit renders twice, runs enrich() twice and re-injects the Map/More-leads/✎ buttons twice (injectMapBtn/injectExtras timers race with the second render). Also _pcAdd/_pcSeed/_pcDel call renderPotentialCustomers() without keep=true, which strips .active from every .view and re-activates only this one. | index.html:177251 vs 177801; 177349 and 177767; 179245/179504 | Open CRM > Potential Customers with console logging on renderPotentialCustomers: two calls per click; the ✎ Details buttons briefly appear then are wiped and re-added. | code review | FIXED v21.18
26 | MEDIUM | crm_potential | _pcToCRM pushes an incomplete/mismatched lead into hydroPro_crm_leads: no createdAt (so it never counts as 'new this week' @dashboard, stale-lead detection skips it and pipeline sort treats it as 1970), no owner/phone/email/address even though the potential record may carry phone/email/address/contact from the v3.9x drawer and enrich patch, and industry is set to r.kind ('hotel'/'restaurant', lowercase) while CRM_INDUSTRIES @66064 uses 'Hotel'/'Restaurant' — stores the lead in a second shape. | index.html:177230-177242 (_pcToCRM) vs 66028 (lead shape comment), 66064 (CRM_INDUSTRIES), dashboard createdAt checks @66218-66230 | Click '➕ Lead' on an enriched hotel row, then open CRM > Leads: contact columns are empty, industry shows lowercase 'hotel', and the lead never appears in 'New this week'. | code review | FIXED v21.18
27 | MEDIUM | crm_reminders | Dead badge: updateReminderBadge() (:73920) looks for `.module-sub-tab[data-subtab='crm_reminders']`, but sub-tabs are rendered with id="modTab-<id>" and no data-subtab attribute (:22018) — 'data-subtab' appears nowhere else in the file. The '🔔 Reminders N' count badge that dismiss/snooze/settings call (:73235, :73245, :73253, :73261, :73900) has never rendered; with 6+ CRM views the tabs are hidden behind a <select> anyway (v17.40, :22024). | /home/user/hydropro/index.html:73927 vs :22018 | Have any reminder; CRM sub-tab/drop-down never shows a count. | code review | FIXED v21.18
28 | MEDIUM | sales_docs | Duplicate rendering on a timer: render() rewrites the whole view innerHTML every 8 s (setInterval @244472) in addition to the switchView wrapper and every hnxSdRender call; while the tab is active this resets scroll position/selection and races with any other enhancer that touches #view-sales_docs. | index.html:244472 |  | code review | FIXED v21.18
29 | LOW | crm_brain | Stale 1-second timer: renderModBrain starts window._hnxMbT_crm_brain (:130286) to tick a clock element that the v1900 cockpit immediately replaces; the interval keeps running querying a removed node. | /home/user/hydropro/index.html:130285-130289 |  | code review | FIXED v21.18
30 | LOW | crm_calendar | hnx_mcal_seen_<user> is not hydroPro_-prefixed, so it is excluded from sync/backup/autoclean logic that keys on the prefix (:7009, :37209, :37271); by design it is per-device, which means the same reminder toast fires once on every device the person opens. | index.html:284271 | Open Nexi on two machines the same day: reminder toast appears on both. | code review | NOT A DEFECT — per-device by design
31 | LOW | crm_calendar | View element is appended to document.body, not #appMain (no rail offset), and regCal leaves a permanent 5 s timer (:284267) re-scanning MODULES. | index.html:284260, :284267 | See crm_customer_care layout note. | code review | NOT A DEFECT — idempotent registration sweep
32 | LOW | crm_catalog | No help guide mapping for crm_catalog in SCREEN_GUIDE or HNX_HELP_GUIDES (pricing rules, segment multipliers and supervisor-only pricing are undocumented in the Help centre). | index.html:286106 (SCREEN_GUIDE), 284753 (guides block) | 🆘 on CRM > Catalog & Pricing offers no guide. | code review | FIXED v21.18
33 | LOW | crm_catalog | Catalog is fully local — product prices/availability never reconcile with SOS Inventory items (_invLoadStock bridge) or QuickBooks products; hydroPro_crm_catalog is also used as an inventory photo source @246343, so two masters can drift. | index.html:68432-68595, 246342-246343 | Change a SKU price in SOS: CRM Catalog and any quote built from it keep the old price. | code review | OPEN — reconciliation with SOS/QuickBooks products is a later feature
34 | LOW | crm_cmd | 'Customers' box reads hydroPro_crm_customers, a key nothing writes (only read here and at :82541), then falls back to the Customer Master store — while the CRM 🤝 Customers screen defines customers as won leads. The cockpit's customer count therefore disagrees with the module's own Customers screen. | /home/user/hydropro/index.html:245731 |  | code review | FIXED v21.18
35 | LOW | crm_cmd | Static MCC_CONFIGS.crm_cmd template holds invented numbers (47 open deals, ₱284k won, ₱1.4M pipeline, 'Model accuracy 89.2%') that are shown whenever MCC_LIVE.crm_cmd throws (Object.assign merge is skipped on error, :18027) — a failure path that displays fabricated KPIs rather than an honest 'no data'. | /home/user/hydropro/index.html:17872-17875 |  | code review | FIXED v21.18
36 | LOW | crm_cmd | No help-guide mapping: SCREEN_GUIDE (:286106) has no crm_cmd entry; the screen is only reachable in Help via the generic m_crm module list, and the m_crm guide text (:285386) never mentions the Command Center. | /home/user/hydropro/index.html:286106, :285386 |  | code review | FIXED v21.18
37 | LOW | crm_contacts | Report block label says 'Recent Customer Contacts' but the case only outputs two counts (customers on master file, accounts in lead book) — it never lists contacts, touchpoints (hydroPro_crm_touchpoints) or recency. Label over-promises relative to content. | index.html:27538 (label), 28780-28790 (case) | Add the block to a scheduled report: output is two count lines, no contact names or dates. | code review | FIXED v21.18
38 | LOW | crm_contacts | If the orchestrator expected crm_contacts to be a navigable CRM screen it does not exist; switchView('crm_contacts') would hit the stale-link alias/guard path with no view. Should be tracked as a report block, not a screen. | index.html:27538, 28780 | grep -n 'view-crm_contacts' index.html returns nothing. | code review | NOT A DEFECT — report block, not a screen
39 | LOW | crm_customer_care | Stale cea_customers references remain: the Compliance shell VIEWS list :257044 still declares it (registerModule at parse-time :257282 re-adds the menu entry and creates a view-cea_customers div in #appMain :257079 with a MutationObserver), while regCC :284149 splices it out again on a permanent 4 s timer :284157. Navigation targets at :257176, :273315, :273363 still say 'cea_customers' and only work because of the alias. | index.html:257044, :257079, :257176, :273315, :273363, :284149, :284157 | Reload; for up to 4 s after login the Compliance menu can show 🤝 Customer Relations, then it disappears. | code review | FIXED v21.18
40 | LOW | crm_customer_care | Not in the base switchView role-guard map (:22443–22460 lists the 11 original crm_* views only); access relies solely on the menu entry's perm:'viewCRM' filter (:21944). A Nexi navTo / deep link for a role without viewCRM opens the screen without the 'Access denied' toast. | index.html:22443–22460 | As a user without viewCRM, call switchView('crm_customer_care') from Nexi: no denial. | code review | FIXED v21.18
41 | LOW | crm_customer_care | View element is appended to document.body (:284145), not #appMain. .app-main carries the fixed rail offset (margin-left:76px :2208; rail position:fixed :2144) while a body-level .view has margin:0 auto and no offset. Same pattern as sales_docs, crm_sales_intel and every *_calendar view; verify visually at widths under ~1750px. | index.html:284145, :2208, :2711 | Open Customer Care on a 1366px laptop and check whether the left padding sits under the module rail. | code review | NOT A DEFECT — body padding already offsets body-level views
42 | LOW | crm_customer_files | Renderer runs twice on every switch: the _customViews router calls window.renderCrmCustomerFiles at +50 ms (:85880) and _hookCrmFilesViews calls it again at +80 ms (:103814); the hook also leaves a permanent setInterval(attempt,4000) (:103819) that only re-checks a flag. | index.html:85880, :103814, :103819 | Add console.count in renderCrmCustomerFiles, click the tab: 2 renders. | code review | FIXED v21.18
43 | LOW | crm_customer_files | Permission gap: injected sub-tab has no perm, no can() check in _customViews, not in base guard map. | index.html:93730, :85834 | Any role with CRM module access can upload/remove customer documents. | code review | FIXED v21.18
44 | LOW | crm_customer_matrix | Double render per switch (+50 ms via _customViews :85880, +80 ms via hook :103815) plus the permanent 4 s hook timer :103819. | index.html:85880, :103815 | console.count in renderCrmCustomerMatrix: 2 per click. | code review | FIXED v21.18
45 | LOW | crm_customer_matrix | Permission gap: no perm on the injected tab, no base guard entry. | index.html:93731 | Deep link as a non-CRM role opens the matrix. | code review | FIXED v21.18
46 | LOW | crm_customers | Three overlapping 'customer' screens in the CRM menu (crm_customers = won leads + QBO feed; crm_master = hydroPro_crm_customer_master; crm_customer_care = ceaView_customers). Same word, three different stores; the render fallback itself tells the user to go to Customer Master instead. | index.html:21797, 66165 (fallback text), 284148 (Customer Care inserted after crm_customers) | Open CRM module: Customers, Customer Master and Customer Care tabs show different customer lists. | code review | FIXED v21.18 — documented in the new Customers guide; screens kept
47 | LOW | crm_customers | No help guide: SCREEN_GUIDE @286106 has no crm_customers entry and HNX_HELP_GUIDES (hnx-help-guides-v1991) has no guide covering this screen (only crm_customer_care and crm_sales_intel). Per CLAUDE.md every user-facing CRM screen must map to a guide. | index.html:286106-286118, 284753+ | Press the 🆘 button on CRM > Customers: no screen-specific guide is suggested. | code review | FIXED v21.18
48 | LOW | crm_customers | Customer mode classification (Fully Active / Active / Sleepy) is permanently 'pending' — _qbCustModeId() has a TODO and only assigns new/notactive; the dropdown and legend advertise modes that can never be reached. | index.html:66756-66778 | Every active QBO customer shows 'Uncategorized' mode regardless of order history. | code review | FIXED v21.18
49 | LOW | crm_dash | Reminder engine runs twice per dashboard paint: reminderActiveCount() and reminderCriticalCount() (:66346-66347) each call _r_generateAll() over every lead/touchpoint/sample/quote/order; the dashboard already iterates the same stores. Cost only, no wrong output. | /home/user/hydropro/index.html:66346 |  | code review | FIXED v21.18
50 | LOW | crm_dash | Store shape drift on hydroPro_crm_leads that this dashboard consumes: the Potential Customers push (:177240) writes leads without createdAt/owner/createdAt, so 'New This Week/This Month' and 'Avg Days to Win' silently exclude them and the stale check falls through to `_crmDaysSince(undefined)` (null). SOS reconciliation (:261444) writes stage:'won' with createdAt but no wonAt, so those customers never enter the avg-days-to-close calculation. All writers use the same key and array shape, so nothing breaks. | /home/user/hydropro/index.html:177240, :261444, consumer :66216-66231 |  | code review | FIXED v21.18 — Potential Customers writes complete leads; the SOS writer already did
51 | LOW | crm_dash | No SCREEN_GUIDE entry for crm_dash; covered only by the generic m_crm module guide (which does describe 🏠 Overview at :285396). | /home/user/hydropro/index.html:286106 |  | code review | FIXED v21.18
52 | LOW | crm_leads | Search box re-renders the whole list on every keystroke (oninput → renderCRM(), :66659), which replaces the <input> and drops keyboard focus/caret after each character on desktop; only the escaping (v13.02 CRM-F9) was fixed, not the focus loss. | /home/user/hydropro/index.html:66659 | Type two letters quickly in 🔍 Search on 🎯 Leads — focus is lost after the first. | code review | FIXED v21.18
53 | LOW | crm_leads | Lead ids are interpolated unescaped into onclick strings (`_crmSelLead='${l.id}'`, :66643); safe today because ids come from _uid()/LEAD_… generators, but the Potential-Customers and SOS writers are separate code paths — any future id containing a quote would break the row's onclick. | /home/user/hydropro/index.html:66643 |  | code review | FIXED v21.18
54 | LOW | crm_leads | No SCREEN_GUIDE entry for crm_leads; only the m_crm module guide (:285390). | /home/user/hydropro/index.html:286106 |  | code review | FIXED v21.18
55 | LOW | crm_marketing | No help guide mapping (SCREEN_GUIDE / HNX_HELP_GUIDES) — expected while the screen is a stub, but the tab should either be hidden or documented as not yet available. | index.html:286106 | 🆘 on CRM > Marketing offers no guide. | code review | FIXED v21.18
56 | LOW | crm_master | Permission gap: the injected sub-tab (:93729) has no perm, _customViews (:85849) performs no can() check and the base switchView guard map lacks crm_master; any role that can see the CRM module (or deep-links) can create/delete master customers. | index.html:93729, :85833, :22443 | Log in as a role with viewCRM only (no manageCRM): Customer Master allows Delete. | code review | FIXED v21.18
57 | LOW | crm_master | crm_master is missing from VIEW_TO_MODULE (:80307 lists only crm, crm_customer_files, crm_customer_matrix), so the open-call banner shown on other CRM views does not surface here. | index.html:80307 | Raise a CRM call, open Customer Master: no banner; open Customer Matrix: banner present. | code review | FIXED v21.18
58 | LOW | crm_orders | Overdue payment status is only recomputed by _o_autoUpdate when the Orders screen renders; Sales Analytics (@72609) and the reminders 'overdue' filter read _o_load() directly, so an unpaid order whose paymentDueDate passed shows as 'unpaid' there until someone opens Orders. | index.html:71499 _o_autoUpdate / 72657 renderCRMSales |  | code review | FIXED v21.18
59 | LOW | crm_orders | No SCREEN_GUIDE mapping for crm_orders (only the one-line bullet in m_crm guide). | index.html:286106 |  | code review | FIXED v21.18
60 | LOW | crm_pipeline | Registry/title calls it a Kanban but there is no drag-and-drop or stage-change control on the board: cards are read-only click-throughs; stage changes must be made from the lead detail. Not broken, but the 'Kanban view of leads by stage' label overstates it. | /home/user/hydropro/index.html:67488-67527 |  | code review | FIXED v21.18
61 | LOW | crm_pipeline | No SCREEN_GUIDE entry for crm_pipeline; only the m_crm module guide line (:285391). All onclick targets on this screen verified present. | /home/user/hydropro/index.html:286106 |  | code review | FIXED v21.18
62 | LOW | crm_potential | Dead button in the same script range: the Nexi Assistant voice settings view (nexi_admin_voice.js @179335) calls onclick="_nexiAdminTest()" — but window._nexiAdminTest is assigned at @179312 inside the same IIFE, so it resolves; verified NOT a defect. Listed only to document the check (no missing onclick targets in 177151-179800). For crm_potential proper every onclick target (_pcAdd,_pcSeed,_pcExport,_pcSet,_pcUpd,_pcToCRM,_pcDel,_pcGo,_pcDetail,_pcLoadMore,_pcMapOpen) is defined. | index.html:179312, 179335 | n/a | code review | NOT A DEFECT (verified)
63 | LOW | crm_potential | No help guide mapping for crm_potential (SCREEN_GUIDE @286106 and HNX_HELP_GUIDES have no entry) although the screen has a seed list, a More-leads loader, map view, details drawer and CSV export that users need explained; also the view is not in the base MODULES registry (@21779) so it depends on two timers (680ms/250ms loop) to appear in the CRM menu. | index.html:286106, 177342, 177753 | 🆘 on CRM > Potential Customers offers no guide; on a slow load the tab appears ~1s after the other CRM tabs. | code review | FIXED v21.18
64 | LOW | crm_quotes | No help-guide mapping for this screen: SCREEN_GUIDE (@286106) has no crm_quotes key, so the 🆘 'guide for this screen' fallback is empty; the only coverage is one bullet in the module guide m_crm (@285386). | index.html:286106 SCREEN_GUIDE |  | code review | FIXED v21.18
65 | LOW | crm_quotes | quoteConvertToOrder still carries the 'Sales Orders module coming in next release' placeholder branch (dead since orderFromQuote exists @71864) — harmless, but misleading if orderFromQuote is ever renamed. | index.html:71170 |  | code review | FIXED v21.18
66 | LOW | crm_reminders | All onclick targets verified present (reminderDismiss, reminderSnooze, reminderUndismiss, _r_clearAllDismissals, reminderShowSettings, _r_saveSettings, _r_resetSettings, orderSetStatus, quoteSetStatus…). Every 'View Lead' action lands on 🏠 Overview rather than the 🎯 Leads screen (switchView('crm_dash') with _crmSelLead set) — works, but leaves the user on the wrong tab when they press ← Back. | /home/user/hydropro/index.html:73322, :73423, :73584, :73609, :73629 |  | code review | FIXED v21.18
67 | LOW | crm_reminders | No SCREEN_GUIDE entry; only the m_crm module guide paragraph at :285397. | /home/user/hydropro/index.html:286106 |  | code review | FIXED v21.18
68 | LOW | crm_sales | Overdue receivables KPI reads o.paymentStatus without running _o_autoUpdate first, so it lags until the Orders screen has been opened (see crm_orders issue). | index.html:72657 |  | code review | FIXED v21.18
69 | LOW | crm_sales | No SCREEN_GUIDE mapping and no dedicated help guide for Sales Analytics (m_crm guide summary only mentions 'the analytics'); crm_sales_intel has one but crm_sales does not. | index.html:286106 |  | code review | FIXED v21.18
70 | LOW | crm_sales_intel | Two QuickBooks credential stores coexist: this screen reads hydroPro_qbw_cfg_v1 while the older hnxQbKey() helper reads hydroPro_qb_legacy_key_v1. A machine that only has the legacy key configured gets the 'SETUP' error here even though other QuickBooks screens work. | index.html:283665 (cfg) vs :66693 (hnxQbKey) | Configure only the legacy QB key, open Sales & Order Intelligence: setup message instead of data. | code review | FIXED v21.18
71 | LOW | crm_sales_intel | Not in the base switchView role-guard map (:22443–22460); permission is enforced only by the menu filter on perm:'viewCRM'. | index.html:22443–22460 | switchView('crm_sales_intel') from Nexi as a non-CRM role opens the screen. | code review | FIXED v21.18
72 | LOW | crm_sales_intel | View element is appended to document.body instead of #appMain (no rail offset). | index.html:283907 | See crm_customer_care layout note. | code review | NOT A DEFECT — body padding already offsets body-level views
73 | LOW | crm_sales_intel | Without the nexi-qb link key the screen shows no data and no "not connected" banner on first open. | hnx-crm-sales-intel-v2113 | Fresh device, open Sales & Order Intelligence. | Chromium run | OPEN (LOW) — banner on first open planned
74 | LOW | sales_docs | Script block has no id attribute (bare <script> @244220) unlike other patch blocks, so it cannot be targeted by id for extraction/node --check per CLAUDE.md workflow; the view div is appended to document.body rather than beside the static CRM views (same pattern as crm_sales_intel, works because .view.active is display:block, but it is outside the normal view container). | index.html:244220 / 244459 |  | code review | FIXED v21.18
75 | LOW | sales_docs | No SCREEN_GUIDE mapping for sales_docs; the m_crm guide (@285399) does document the screen, so the 🆘 fallback should point at m_crm. | index.html:286106 |  | code review | FIXED v21.18

## Re-walk v21.18
View id | Rendered (chars) | Controls clicked | Clicks with error | Page errors | Snag panel | Outbound calls during visit
crm_potential | 353 | 8 | 0 | 0 | no | https://unpkg.com/leaflet@1.9.4/dist/leaflet.css; https://unpkg.com/leaflet@1.9.4/dist/leaflet.js
crm_cmd | 1210 | 2 | 0 | 0 | no | https://hnx-sync.eyalbenari99.workers.dev/auth/app-login
crm_dash | 295 | 2 | 0 | 0 | yes: l.createdAt.slice is not a function | —
crm_reminders | 459 | 9 | 0 | 0 | no | —
crm_leads | 13282 | 60 | 0 | 0 | no | https://hnx-sync.eyalbenari99.workers.dev/auth/app-login
crm_pipeline | 611 | 8 | 0 | 0 | no | —
crm_quotes | 3748 | 2 | 0 | 0 | no | —
crm_orders | 3863 | 2 | 0 | 0 | no | —
crm_sales | 1248 | 8 | 0 | 0 | no | https://hnx-sync.eyalbenari99.workers.dev/auth/app-login
crm_sales_intel | 1261 | 9 | 0 | 0 | no | —
crm_customers | 535 | 8 | 0 | 0 | no | https://hnx-sync.eyalbenari99.workers.dev/auth/app-login; https://qb-api.eyalbenari99.workers.dev/api/qb/customers
crm_customer_care | 29416 | 60 | 0 | 0 | no | https://hnx-sync.eyalbenari99.workers.dev/auth/app-login; https://hnx-sync.eyalbenari99.workers.dev/sos/customers; https://hnx-sync.eyalbenari99.workers.dev/sos/invoices; https://hnx-sync.eyalbenari99.workers.dev/sos/sales-orders; https://nexi-qb.eyalbenari99.workers.dev/qb/health
crm_catalog | 4025 | 43 | 0 | 0 | no | https://hnx-sync.eyalbenari99.workers.dev/auth/app-login
crm_marketing | 300 | 2 | 0 | 0 | yes: lead.createdAt.slice is not a function | —
sales_docs | 884 | 5 | 0 | 0 | no | —
crm_calendar | 453 | 35 | 0 | 0 | no | https://hnx-sync.eyalbenari99.workers.dev/auth/app-login