## Read me
Nexi - all of Eyal's requests of 9 Oct 2026, audited status and plan
Prepared 09 Oct 2026 10:21 UTC. Every status was checked on disk (branches, commits, test logs, review verdicts), not from memory.
Live for everyone today: v22.20 (sound off). Everything else is built but NOT on your screen - the irrigation release (v22.22) is step 1 and ships today.
Sheets: Requests 9 Oct (one row per request) · Plan - order of work · Alert audit (89 faulty producers of 123) · Eyal - your side.

## Requests 9 Oct
# | Request from Eyal (9 Oct 2026) | What exactly must happen | Where it stands TODAY (verified on disk / live) | Status | Work done (branch · commits · tests) | What is still missing / blocking | Plan (step by step) | Release | Eyal side
1 | Trip incentives: Jinky cannot approve, "logistics check still pending" although Syra checked | Syra's checks stick; Jinky approves; payroll 1-7 Oct locks | LIVE v22.18 since 01:04 (Netlify 3f8a753). Trips bridge rewritten + Data Safety lets Syra's bulk check through. | DONE - LIVE | branch merged #503 · trip-check-sticks 21/21 · push-guard-forward 13/13 | Nothing. Jinky confirms the Excel export. | 1 Reload (Cmd+Shift+R) 2 Syra presses "Check all" if any day still pending 3 Jinky approves 4 Eyal/Dr Amy Approve & Lock 5 Jinky re-exports | v22.18 (live) | Confirm payroll went out
2 | Critical: "don't do the noise, just blink" | No beep, silent pop-ups, criticals not spoken; cards + bell still blink | LIVE v22.20 since 07:22 (Netlify 032286e). Verified: beeps 0, pop-ups silent, "Play sound" greyed. | DONE - LIVE | PR #504 merged · quiet-alerts-v2220 2/2 on index+next, fails on v22.18 · CI 25/25 green | Nothing. | - | v22.20 (live) | Press Cmd+Shift+R; title bar = v22.20
3 | Irrigation 4x-daily pool table: cannot type/save, EC "1" saved, readings wiped, no dosing recommendation | Readings save only on Tab/Enter/blur, cursor kept; no wipe by first cloud download; Manila date; typo check; dosing matrix (your v21.69 workbook) back | BUILT on branch hotfix/irr-pool (worktree wf_aa1e5c2b-673-6): 5 commits + 5 files uncommitted (the first-pull race gate - finished, syntax OK, not yet committed). Suite on next.html 20/22; the 2 red are test-side (date mask / 11-s wait). Review r1: 8 must-fix, all addressed in round 2; final review not finished. | BUILT - NOT YET LIVE | hotfix/irr-pool 770348e · irr-pool-hotfix 20/22 next, 18/21 index (older run) · irr-dose 2/2 · sensor-merge 7/7 · quiet-alerts 2/2 · screens 47/47 | (a) commit the gate edits (b) make the 2 red cases green on both pages (c) prev.html == v22.20, versions 22.22/22.23 (d) PR, CI 25 jobs, merge, Netlify | TODAY, first: I do (a)-(d) myself, no more review rounds. ~1.5 h incl. CI. | v22.22 stable / v22.23 trial | Nothing until live; then Cmd+Shift+R
4 | Your ranges: EC 1.70-1.90 ok · 1.50-1.69/1.91-2.00 warn · <1.50/>2.00 crit; pH 5.80-6.50 ok · 5.50-5.79/6.60-6.80 warn · <=5.49/>=6.81 crit; level GH1-6+10 30-60 · GH7-8 40-100 · GH9 30-50 (warn/crit bands) | One range table used by the screen colours, chips, calls, Smart Dosing, legend, Nexi answers | IN the same branch: IRR_LEVEL_BANDS_BY_GH + EC/pH bands seeded exactly as you wrote; the old private _IRR_RANGES (EC 1.2-3.2 / pH 5.5-6.5) deleted. Test "🎨 Eyal's ranges" passes at every boundary (1.49 crit, 1.50 warn, 1.69 warn, 1.70 ok, 1.90 ok, 1.91 warn, 2.00 warn, 2.01 crit ...). | BUILT - NOT YET LIVE | same branch · case "🎨 Eyal's ranges" ✓ · "💧 Water level alarms on Eyal's bands" ✓ (2nd run) | Ships with #3 | with #3 | v22.22 | -
5 | Target cm wrong: daily targets GH1 60 · GH2 60 · GH3&4 60 · GH5 60 · GH6 60 · GH7&8 100 · GH9 50 · GH10 60 (130/120/... = cleaning) | Daily rounds, colours, FILL hint, dose use the DAILY target; cleaning level kept separately; admin-editable, synced | IN the same branch: IRR_DAILY_TARGET_BY_GH exactly as you wrote; dim.target kept as the cleaning level; Smart Dosing uses the same engine (Pool 1 at 54 cm -> gap -6, 121 L, not -76/1,537 L). | BUILT - NOT YET LIVE | same branch · "🎯 Dose = Eyal's workbook" ✓ | Ships with #3 | with #3 | v22.22 | -
6 | Dosing per your v21.69 workbook (Export for Reven) | Water L, A=B from the EC matrix x template x source factor, C acid, one-meter rule, CALIBRATE rule, >2.35 water only | IN the same branch; v21.71 "1 L per 10 cm morning only" rule no longer the default (switch back per pool in Pool & Drum Setup if wanted). | BUILT - NOT YET LIVE | same branch · "🎯 Dose" ✓, irr-dose 2/2 | Ships with #3 | with #3 | v22.22 | Confirm the v21.71 rule is retired (default: yes)
7 | Gauges: animated tank + fill valve with drips (litres to target, A/B/C drums), 3D pH column 0-8 yellow level, EC column 0-5 with lightning | Above Water level / pH / EC of every pool row; moves on committed values; still in Lite | Component finished and judged (3 prototypes, 2 judges); INLINED in the same branch as <script id="hnx-irr-viz-v2222"> in index.html + next.html. Live smoke screenshots taken on the real table (sent to you 07:55). Test "🎛 Gauges" ✓ after the kept-assertion fix. | BUILT - NOT YET LIVE | same branch · "🎛 Gauges" ✓ · demo + screenshots scratchpad/irrviz/final | Ships with #3 - the ONLY reason you do not see them is that v22.22 is not published | with #3 | v22.22 | -
8 | Old irrigation criticals keep coming back from other days although fixed | Every pool alarm judged from the LATEST reading only; one call per pool+problem; auto-closed when back in range; stale red cards removed | IN the same branch: engine rewritten (latest reading, Manila day, hold/newer/full gate so a stale computer cannot close a live alarm), old auto calls closed once as "superseded by a newer reading", cards taken down, alarms in the Alerts panel. Tests "🚨 Latest reading only" ✓, "🃏 Stale cards" ✓. | BUILT - NOT YET LIVE | same branch | Ships with #3 | with #3 | v22.22 | -
9 | Audit ALL critical/warning: dynamic - if data changes, messages must follow (not only irrigation) | Every automatic alert in Nexi judged from latest data, auto-resolves, no duplicates | AUDIT DONE on 123 producers: 89 NOT OK. ROOT CAUSE 1: the shared helper _autoCloseCall never really closes a call (status stays open) -> everything "never clears". ROOT CAUSE 2: raisers loop every stored day/round or use the UTC date -> stale + duplicates. Reproduced live: pool sensors, production checklist, checklist click-raiser, big fans, escalations, room checklist, drum levels, meter drift, T-72 watch. 11 of ~24 live verifications done before I stopped it. | AUDITED - FIX TO BUILD | report partial in wf_39c69ec0-d24 journal; scratchpad/alertaudit/* | Build the shared fix: hnxAutoAlert(key, condition, text) with real close + per-producer "latest data only"; one-time cleanup of the flood (merge duplicate auto calls, hand-raised untouched) | After #3 ships: 1 finish the 13 remaining live checks 2 write the fix list 3 build on branch alerts/v2221 (same release as #10) 4 review 5 trial | next trial (v22.24) | -
10 | Critical/warning only in the modules each user can open; ⚠ Alerts drop box at the top that blinks only on a critical in MY modules | Router + access check = the gate's own function; every surface filtered; dropdown; blink rule | BUILT on branch alerts/v2221 (worktree wf_16ab8009-f22-14): 2 commits (router, drop box, guide) + 4 files uncommitted (flood fix: per-user seen list, real +N count, one open call per condition). Inventory found 51 surfaces leaking (bell, My Calls, Brain, cockpits, Manager Summary, Ops Wall, Daily Summary, report builder...). Design reviews r1 rejected (10 must-fix) -> design revised -> build. Code reviews NOT run yet. | BUILT - UNREVIEWED | alerts/v2221 6dd6a90 + uncommitted · alerts-by-module-v2221.test.js | Commit the flood fix; run the 3 reviews (leak / ux / regress); fix; combine with #9 | After #3: 1 commit 2 reviews 3 fixes 4 trial PR | next trial (v22.24) | -
11 | +39,058 alerts / My Calls 3,162 / Open calls 7,567 flood | Real counts; duplicates merged; auto calls close themselves | Causes found (syncAllAutoTasks every 5 s raises new calls; __hnxHiddenAlerts counts forever; seen list synced company-wide and trimmed to 300). Fix is inside #10's uncommitted work + #9's shared helper. | IN PROGRESS (inside #10 + #9) | - | Ships with #10 | with #10 | next trial | Run the "close criticals up to 30 Sep" console script now (sent 06:22) - it clears the backlog today
12 | Purchasing: go back a step in the process; add more suppliers to an open RFQ | ➕ add supplier / ✕ remove unquoted / ↩ back one step with reason + audit; data rules | BUILT on branch v2220/purchasing (worktree -6): 1 commit; review r1 data lens rejected 1 must-fix (not yet fixed); flow review not finished. | BUILT - 1 REVIEW FIX PENDING | 435cf2d · purch-v2220.test.js | Fix the data must-fix; finish flow review | After #3: part of the v22.20-areas trial combine | next trial | -
13 | In one RFQ: option to add more items | Add items from SOS, NOT-TOLD suppliers + 📣 send update, offers per item, award locked until checked, SOS-only + red chip | DESIGNED (3 designs judged) and BUILT on branch rfqitems/v2221 (worktree wf_47d1a3fd-fcc-1): 3 commits + 2 files uncommitted (round-2 fixes in progress). Reviews r1: money rejected 1 (short offers can win the award), control rejected 2 (Jinky blocked after Dr Amy checks; phone layout cuts ✕/SOS chip). | BUILT - ROUND-2 FIXES PENDING | rfqitems/v2221 9e4d0c0 + uncommitted · purch-rfq-additems.test.js | Finish the 3 round-2 fixes; regress review; merge with #12 (same screen) | After #3 | next trial | Defaults in use: Jinky content check; limit 20% / ₱50,000; suppliers told before the check; short offer -> PO at offered qty; no split award
14 | Item request: multi items in one request (one project/location); items only from SOS; red CRITICAL note if not in SOS; buying goes to Purchasing as URGENT task | lines[] per request, SOS picker, red chip, approval on the total, one urgent PR + buyer task | DESIGNED (2 reviews, 14 must-fix folded in) and BUILT on branch requests/v2221 (worktree wf_3d706a94-7ba-12): 1 commit + 1 file uncommitted. Code reviews NOT run. | BUILT - UNREVIEWED | requests/v2221 0e8b7db · requests-multi-v2221.test.js | Commit; 3 reviews (data / flow / regress); fixes | After #3 | next trial | -
15 | Employee work schedule: start/finish per employee (default = 9 Oct memo), different hours need Jinky's approval, bio scans judged on time / late against own hours | emp.workSchedule + history + change requests; seed from memo; Jinky approves; attendance chips; pay unchanged before 9 Oct | DESIGNED (2 reviews, 11 must-fix folded in) and BUILT on branch sched/v2223 (worktree wf_eada7da1-444-8): 3 commits, clean. Tests written; the test run was cut off twice (interrupt / load). Code reviews NOT run. | BUILT - TESTS + REVIEW PENDING | sched/v2223 f4a048f · work-schedule-v2223.test.js | Run the suite; 3 reviews (pay / people / regress) - pay-affecting, must be green | After #3 | next trial | Decide: can Eyal / Dr Amy also approve, or only Jinky? (default: Jinky + both of you)
16 | Fixed assets 2026 file: upload to Nexi; new QB accounts + numbers recommended; JE per asset; recurring JE for depreciation | Import both sheets; propose free account numbers in the file's families; reclass JE where posted wrongly; catch-up; recurring monthly schedule; QB CSV; "for Review" POs | File read (34 + 23 assets, 166 POs). Found: many 2026 assets posted to Consumables / R&M / COS / Advances-to-Eyal (Chery PHEV ₱3.56 M) -> reclass JEs needed. Nexi already has the lapsing importer (v20.80) + New-asset JE package (v20.98). Workflow started (discover step) and stopped for the audit. | STARTED - NOT BUILT | scratchpad/assets/ref/lapsing-2026.xlsx + .txt · script scratchpad/wf/fixed-assets-2026.js | Run the file through the existing importer live; build the recurring-JE schedule + CSV + "for Review" screen; accountant review; deliver the Excel package | After #3 and the alert fix: ~4 h | next trial + Excel package to you | Defaults: depreciation from the file's start month; cost as given (no VAT change); no salvage
17 | Red "Nexi was blocked" box false alarms (13 s with a confirm open; 3806 s = laptop asleep) | Dialog time never counted; any gap > 5 min = "computer asleep", never a red STALL; slowest-jobs never shows sleep time | Root causes confirmed in code (wasHidden only checks a hidden tab). Branch stall/v2222 created from hotfix/irr-pool (worktree stall-fix), NO commits yet - the builder was stopped at the start. | NOT BUILT | - | Build + test (3 cases) + review | After #3 (small, ~1 h); can ride the same stable hotfix line as a v22.24 hotfix | v22.24 hotfix or next trial | Close the red box with ✕ when it appears
18 | New computers / tablets / phones not getting access after admin approval | Invite link keeps department/role; grants really grant; sign-in retries the cloud; SIGN IN reachable on phones; default-admin security | BUILT on 5 branches v2220/invite, grants, signin, secapp, speed (45-50 commits each on the old base). Reviews: grants accepted twice then regress rejected 1; invite rejected (2 + 1 + 2); signin rejected (1 + 2, phone 1); secapp attack rejected 1 (lockout accepted); speed review not finished. Round-2 fixers were running when stopped (invite r2 committed 4379651; grants r2 uncommitted). | BUILT - ROUND-2 FIXES PENDING | v2220/* branches · *-v2220.test.js files | Finish round-2 on invite/grants/signin/secapp; review speed; combine into one trial commit | After #3: ~3 h | next trial | Then: paste worker v3.7.2 in Cloudflare; change the admin/admin123 password first
19 | Data Safety: 2 "Upload anyway" clicked by mistake - undo | Restore the cloud version from just before each click | Console script written + tested on a copy (uses the worker's version history, 30 versions kept). | READY - YOUR ACTION | scratchpad/undo/undo-upload.js | - | Paste the script (sent 06:22) in the console; press OK twice | - | DO IT TODAY (versions expire)
20 | Clear all criticals up to end of September (already fixed) | Close every open CRITICAL call raised up to 30 Sep as Finalized with your note | Console script written + tested on a copy (uses hnxOldCritical.close; only criticals, only up to 30 Sep). | READY - YOUR ACTION | scratchpad/undo/close-sept.js | - | Paste the script (sent 06:22); press OK; after 30 s press OK on "Upload calls" | - | DO IT TODAY
21 | Memo "Official time schedule" (Dr Amy, 9 Oct) | Seed the schedules of #15 from it | Memo read; mapping Admin 7:00-17:30 · Maintenance 7:00-17:00 · Lee Borreta Thu 8:00-17:00 · Production & Packaging 6:45-17:00 · Drivers & Helpers 5:00-16:00 · Antonio Garcia 6:00-17:00 · Contractors 8:00-17:00 is in #15's seed. | IN #15 | - | - | with #15 | next trial | Tell HR which people Nexi could not place in a memo group (list comes with #15)

## Plan - order of work
Step | What | Requests covered | Release | Est. time | Gate before next step
1 | Irrigation stable hotfix: commit the last gate edit, make the 2 red test cases green on both pages, PR, CI (25 jobs), merge, verify Netlify | #3 #4 #5 #6 #7 #8 | v22.22 stable (prev.html = v22.20) / v22.23 trial | ~1.5 h | Eyal sees the gauges + daily targets on his screen
2 | Stall-box false alarms (small) | #17 | v22.24 stable hotfix | ~1 h | 3 tests green on both pages
3 | Alert chain: finish the 13 remaining live checks; build the shared hnxAutoAlert fix (real close, latest-data-only, dedupe); one-time cleanup of the flood | #9 #11 | trial | ~3 h | Reviewer reproduces: 0 stale alerts across 10 modules
4 | Alerts by module + ⚠ drop box: commit, 3 reviews, fixes | #10 #11 | trial | ~2 h | No leak with 3 test users
5 | v22.20 areas: finish round-2 (invite, grants, signin, secapp), review speed, purchasing data fix | #18 #12 | trial | ~3 h | All 6 areas accepted
6 | RFQ add items: 3 round-2 fixes, regress review, merge with #12 on the same screen | #13 | trial | ~2 h | money + control + regress accepted
7 | Multi-item requests: commit, 3 reviews, fixes | #14 | trial | ~2 h | data + flow + regress accepted
8 | Work schedules: run suite, 3 reviews (pay first), fixes | #15 #21 | trial | ~2 h | Payroll suite green; pay reviewer recomputes 4 people by hand
9 | Fixed assets 2026: live import, recurring JE engine, QB CSV, for-Review screen, accountant review, Excel package | #16 | trial + Excel to Eyal | ~4 h | Accountant recomputes 6 assets to the centavo
10 | TRIAL COMBINE: one next.html with steps 3-9, renumbered, CI 25 jobs, merge; trial computers get it; promote after a few green hours with your OK | all trial items | v22.24+ trial -> stable | ~2 h | CI green on both pages

## Alert audit (89 of 123)
Producer | Module | Verdict | Reproduced live | Fix (smallest change)
syncPoolSensorsToMaintenance — pool EC/pH out of range → maintenance task + irrigation call (KNOWN CASE, being fixed in hotfix/irr-pool commit 8d33058) | irrigation | STALE + DUPLICATES | YES - high | Smallest change in syncPoolSensorsToMaintenance (L107860): (1) today = hnxLocalToday() (Manila), not toISOString(); (2) per pool, pick ONLY the latest slot that has a numeric reading (sort IRR_POOL_TIMES, take the last with !isNaN(parseFloat(r.EC)) resp. r.pH) and judge that one value; (3) key 'pool::'+poolId+'::'+param with no date, so an existing open task/call is reused while the condition persists and closed once when the latest reading is in range (the close note should quote the clearing reading and slot); (4) read the band from window.IRR_RANGES[param] (criticalMin/criticalMax → urgent, min/max → priority) and delete the private _IRR_RANGES; (5) in _autoCloseCall really close (status 'closed_finalize', closedAt, closedBy 'system') so raw-status readers do not count it as urgent/new. Same latest-slot + shared-band change for the EC/pH Watch tile scan() at L159084-159100. Add a tests/payroll case: 08:00 out of range + 11:00 in range → 0 tasks, 0 calls after 15 s; 08:00 ok + 11:00 out of range → exactly 1 task + 1 call, still 1 after 15 s; then 14:00 ok → both closed with a history line, none re-raised.
syncProductionToMaintenance — daily checklist warn/danger item → maintenance task + paired production call | production | MIXED (STALE 00:00-08:00, NEVER-CLEARS after day change, DUPLICATES with the click call) | YES - high | Smallest change, all in index.html (bump APP_VERSION, guide line, a tests/payroll case): (1) L107649: read the lists the way the matrix does — `const CATS=(typeof CATEGORIES!=='undefined'?CATEGORIES:window.CATEGORIES_SUP); const GH=(typeof GREENHOUSES!=='undefined'?GREENHOUSES:window.GREENHOUSES_SUP);` (the IIFE at L98312 is in the same classic-script scope as the v94 consts, so the lexical names resolve) — this revives the producer. (2) L107651: `const today=hnxLocalToday();` (Manila day, matches SKEY) and use it for the task scheduledDate; same in _autoCloseCall/_autoCloseTask history dates. (3) Key the registry WITHOUT the date: `'prod::'+gh+'::'+cat.id+'::'+i` (and `'prod::'+gh+'::pipes'`), migrating old `YYYY-MM-DD::prod::…` entries on first tick; at the end of each tick walk every `prod::` registry entry whose gh/cat/item is NOT danger/warn in TODAY's state (including 'no entry today') and resolve it with the history line 'status cleared / not flagged on <today>' — this closes day-D leftovers the moment the latest data is clean. (4) Drop the second call: in setStatusUI L19681-19683 stop calling _autoCreateCallFromChecklist (or make it a no-op when the producer is alive), so one critical = one task + one paired call that auto-resolves. (5) In _autoCloseCall L107296 set `c.status='closed_fixed'; c.closedAt=Date.now(); c.closedBy='system'; c.closeNote=reason` (keep autoResolved for the dialog hint) so the 2 h escalator and open-call counts stop seeing resolved calls. Until (1) ships, a one-line interim is to exclude the click-raised production calls from auto-escalation and auto-close them from setStatusUI when newVal is ok/null (find call by autoKey for today).
_autoCreateCallFromChecklist — every 'danger' click on the daily checklist raises a 'critical' call (second call for the same item) | production (department from category: production or maintenance L19821) | NEVER-CLEARS + DUPLICATES | YES - high | Smallest change, in the checklist block (index.html ~L19667-19815): make the click-raiser the single owner of its call and give it the missing close path. 1) Add `_autoResolveChecklistCalls(gh,cat,idx,reason)`: `const calls=(window.loadCalls¦¦loadCalls)(); let ch=false; calls.forEach(c=>{ if(c.autoKey&&c.autoKey.indexOf('checklist_'+gh+'_'+cat+'_'+idx+'_')===0 && !c.autoResolved && !(window.__hnxCallStatus&&window.__hnxCallStatus.closed(c))){ _autoCloseCall(calls,c.id,reason); ch=true; } }); if(ch)(window.saveCalls¦¦saveCalls)(calls);` — prefix match on the key WITHOUT the date, so a call raised on an older day resolves from today's data; `_autoCloseCall` (L107296) already writes the "🤖 Underlying issue appears resolved — …" history line and flags it for human close. 2) In setStatusUI (L19680): `if(newVal==='danger'){…raise…} else {try{_autoResolveChecklistCalls(gh,cat,idx,'status cleared in checklist ('+(newVal¦¦'unflagged')+')');}catch(e){}}` — so OK / ⚠ / un-flag resolves the moment the data changes. 3) Once-per-boot sweep (e.g. in the carry-forward boot at ~L290359 or a 60-s timer): for every open call with autoKey starting 'checklist_', parse gh/cat/idx and resolve it unless TODAY's store (hydroPro_<hnxLocalToday()>) still says 'danger' for that item — this clears the backlog of calls from older days whose item is OK or unflagged today. 4) Do NOT "revive" syncProductionToMaintenance by exposing window.CATEGORIES/GREENHOUSES unless its per-item `_addPairedCall` is removed — otherwise every ✕/⚠ would get a second call (it would also raise calls for carried-forward flags). Add a tests/payroll case: danger click → 1 open critical call; OK click → autoResolved=true with history line; yesterday's call + today OK → resolved on boot; second ✕ same day → still 1 call.
syncProductionToMaintenance — pipes not clean (supervisor check) | production | MIXED | YES - high | Smallest change, in the same block (L107646-107770), and a test: 1. Revive: replace `const CATS=window.CATEGORIES;const GH=window.GREENHOUSES;` with `const CATS=(typeof CATEGORIES!=='undefined')?CATEGORIES:window.CATEGORIES;const GH=(typeof GREENHOUSES!=='undefined')?GREENHOUSES:window.GREENHOUSES;` (or add `window.CATEGORIES=CATEGORIES;window.GREENHOUSES=GREENHOUSES;` right after L15985). Do NOT revive without 2-4, or the stale-day behaviour the owner complains about appears here too. 2. Local day: `const today=(typeof hnxLocalToday==='function')?hnxLocalToday():new Date().toISOString().slice(0,10);` (L107651) so the sync reads the same hydroPro_<Manila date> file the screen writes. 3. Normalise the value: `const pv=fs.pipesClean===true?'all':fs.pipesClean===false?'notyet':fs.pipesClean;` then raise on pv==='notyet' (priority) — optionally 'some' as warn — and resolve on anything else that is set ('all'/'most'/null = cleared). 4. Dateless key + resolve from today's state: use `'prod::'+gh+'::pipes'` (no date) so one open task per greenhouse carries across days and is closed by today's latest value; on first run migrate/close any old `<date>::prod::<gh>::pipes` entries whose date !== today (close task + call with reason 'day rolled over, judged from today's check'). Apply the same three changes to the item/seedlings/fans branches, which share the bug. 5. Add a tests/payroll-style case: yesterday file notyet + today file 'all' → no open pipes task/call; today 'notyet' → exactly one task+call; then today 'all' → task done, call autoResolved, no duplicate on the next tick. Bump APP_VERSION, update the Production/Maintenance guide text in hnx-help-guides-v1991, and fix the inventory.json entry (currently lists this producer as live).
syncProductionToMaintenance — seedlings warn/danger | production | MIXED | YES - low | For the owner's complaint: nothing — this producer is not firing at all. Two-part smallest fix if it is meant to work: (1) in syncProductionToMaintenance replace `const CATS=window.CATEGORIES;const GH=window.GREENHOUSES;` with the lexical constants (`const CATS=(typeof CATEGORIES!=='undefined')?CATEGORIES:window.CATEGORIES;` same for GREENHOUSES and FAN_PARTS), and (2) make it latest-data only before enabling it: compute `today` with hnxLocalToday() (Manila) instead of toISOString, drop the date from the auto keys (`'prod::'+gh+'::seedlings'`, same for item/pipes/fan keys) so one open task/call per subject follows the latest checklist, and at the end of each run auto-close (with the existing _autoCloseTask/_autoCloseCall history line) and delete every registry entry whose subject is not an issue in today's checklist (seedlings not 'warn'/'danger', including undefined/null) — same pattern as the pool fix in hotfix/irr-pool. Add a tests/payroll case: D1 danger → task+call; D2 ok → both auto-closed with history, no second call at 02:00 Manila. Guide (HNX_HELP_GUIDES) must then say Seedlings Critical raises a Production call.
syncProductionToMaintenance — big-fan part 'danger' (checklist fan inspection) | production | MIXED | YES - low | Smallest change: delete the big-fan block (index.html L107803-107848, "4) BIG FANS") — it judges a data model no screen writes since v2.46.31 and the Big Fans module (syncFanIssueToCall L20747) is already the single fan raiser; do NOT "revive" it by exporting window.GREENHOUSES/CATEGORIES/FAN_PARTS, because the forced-globals probe shows it would then double-raise checklist items (already raised directly at L19810) and multiply fan calls. Preferably remove the whole dead syncProductionToMaintenance body (L107646-107849) or make it a no-op, and keep only the pool-sensor sync in syncAllAutoTasks (L107949-107952). If any part of it is kept: (a) key on gh+fan+part with no date and, at the top of each run, sweep every registry entry whose key date != today and auto-close its task/call ("not flagged in today's inspection"); (b) use hnxLocalToday() (L17441) instead of toISOString() for both the state key and the registry key; (c) treat an existing call that is autoResolved but not closed, or a deleted task, as "already raised" instead of creating new ones. Add a tests/payroll-style case: older-day danger + today OK → the old call carries an auto-resolved history line within one cycle and nothing new is raised.
syncFanIssueToCall — Big Fans module defect → call (critical/high/…) | production (Big Fans), department maintenance | OK (inherits NEVER-CLEARS from _autoCloseCall) | YES - high | Smallest change, all in index.html (bump APP_VERSION + guide + a test): (1) In syncFanIssueToCall and closeFanIssueCall stop relying on bare isCallClosed/_autoCloseCall: use `window.__hnxCallStatus.closed` for closed-ness and export the auto-close helper once (`window._autoCloseCall=_autoCloseCall;` right after L107307) — or inline the close. (2) Make the OK/removed path really CLOSE the call, not just flag it: set status='closed_finalize', closedAt=Date.now(), closedBy='system', closeNote=reason, push the history line ("🤖 … marked OK by supervisor"), then window.saveCalls(calls) and saveState() so issue.callId=null persists (the same change in _autoCloseCall fixes the flag-only behaviour for every producer that calls it; keep autoResolved=true so the close modal still shows the reason). (3) Treat a closed call as non-existing so a re-flagged fan raises a fresh call: `const existing=calls.find(c=>c.autoKey===autoKey&&!closed(c));` and drop the `if(_isClosed(existing))return;` at L20785. (4) Keep syncFanIssueToCall as the only fan raiser: remove or key the checklist fan raiser (L107804) off the dated key, or at least skip parts that already have an open fan_<gh>_big_<issue> call.
_autoCloseCall — the shared 'auto-resolve' helper used by every auto producer | all (shared helper) | NEVER-CLEARS (root cause 1) | YES - high | In _autoCloseCall (L107296): really close the call — set c.status='closed_fixed', c.closedAt=Date.now(), c.closedBy='system', c.closeNote='Auto-resolved: '+reason, keep c.autoResolved/autoResolvedAt/autoResolvedReason, and push the history line (updates note '🤖 Auto-resolved — '+reason) so every raw-status reader (Brain L92014, GH cmd L127597, cockpits L131118/131315, etc.) and My Calls agree and the detail shows who/when. Keep a human 'verify' list by filtering calls with autoResolved && closedBy==='system' instead of leaving them open. Also expose the helpers next to _addPairedCall (L106552): window._autoCloseCall=_autoCloseCall; window._autoCloseTask=_autoCloseTask; window.isCallClosed is deliberately not exported (v22.12 note), so change closeFanIssueCall L20865-20867 to use window.__hnxCallStatus.closed and window._autoCloseCall. Keep the existing 'closed_fixed' guard so it never double-closes; do not re-fix syncPoolSensorsToMaintenance (hotfix/irr-pool), but after the helper truly closes, that per-cycle churn also stops showing as critical. Add a tests/payroll case: out-of-range then in-range → call status closed_fixed, closedBy 'system', one history line, Brain open/critical count 0.
checkEscalations — bumps idle calls to URGENT (incl. auto-resolved and automatic calls) | per call (production/irrigation/maintenance) | STALE | YES - high | Smallest change, in _shouldEscalate (live index.html L80501-80503, scratch copy): treat an auto-resolved call as not escalatable and never judge an automatic call past the moment its data cleared — function _shouldEscalate(call,rules){ if(call.escalated)return null; if(call.autoResolved)return null; /* cause already cleared by the latest data — waiting only for human verification */ if(isCallClosed(call))return null; ... Optionally (same spirit, one more line) skip automatic calls whose linked task is 'done' even if the call record says otherwise — already covered by getCallStatus. Also add a payroll-suite-style case: seed an autoResolved call 3 days old, boot, assert escalated===false and priority unchanged. Note: the pool-sensor churn in syncPoolSensorsToMaintenance (known case, branch hotfix/irr-pool) is separate; this fix is needed regardless because fan calls (closeFanIssueCall) and any call whose task was deleted hit the same escalator. Bump APP_VERSION and the 📞 Calls / escalation guide text in hnx-help-guides-v1991 ('auto-resolved calls are never auto-escalated').
Irrigation pool monitor — EC/pH out of range → warning issue on every save | irrigation | DUPLICATES + NEVER-CLEARS | YES - high | Smallest change, all inside irrSavePool's "Raise issue if out of range" block (L39984-40000); keep the pool sync (hotfix/irr-pool) as the task/call producer: 1. Judge only the LATEST data: skip the block entirely when _irrDate !== hnxLocalToday() (editing a past day never raises or changes anything), and when the value is still partial/invalid (hotfix #63 validation; e.g. defer until the round is finished or the value passes the same check the screen uses for ecStatus). 2. One issue per subject, no date in the key: compute key='irr-pool::'+poolId+'::'+field; find existing = loadIssues().find(i=>i.autoKey===key && i.status==='open'); if out of range and none exists → createIssue({...as today, autoKey:key}) (add autoKey passthrough in createIssue L26669, one line: autoKey:data.autoKey¦¦null); if out of range and one exists → update its description/value in place (no new record). 3. Auto-resolve with history: if the value is back in range and an open issue with that key exists → updateIssueStatus(existing.id,'resolved','reading back in range '+v) — this already pushes a history line (L26839). 4. Optional one-liner: drop "Date:" from the description or use hnxLocalToday() so the card never carries another day. Add a tests/payroll-style case: seed yesterday OUT / today IN, edit yesterday → 0 issues; type today 1 then 1.7 → 1 issue created then status resolved with a history entry; irr_cmd Open calls tile reads 0. Update the Irrigation Pool Monitor guide in hnx-help-guides-v1991, bump APP_VERSION.
Irrigation room checklist — item FAIL → critical issue | irrigation | NEVER-CLEARS + DUPLICATES | YES - high | Smallest change, all inside irrSaveItem (index.html ~L39085-39128): 1. Give the issue a stable key: createIssue({..., sourceKey:'irr_check:'+_irrCurrentRoom+':'+itemNum}) (createIssue copies unknown fields? it does not — add `sourceKey:data.sourceKey¦¦null` to the issue object at L26672, one line). 2. Before creating on FAIL: const open=loadIssues().find(i=>i.sourceKey===key&&!['resolved','approved','cancelled'].includes(i.status)); if(open){ open.history.push({action:'re-failed',by:user,at:Date.now(),date:_irrDate}); saveIssues(all); } else createIssue(...). One open issue per room+item, never a duplicate while the cause persists. 3. On OK (field==='status'&&value==='ok'): if _irrDate >= the latest date on which this room+item has any status in loadIrrChecklist() (i.e. the OK is the latest data, Manila date via hnxLocalToday()), find the open issue with that sourceKey and set status='resolved', resolvedAt=Date.now(), push history {action:'auto-resolved', by:user, at, note:'item OK on '+_irrDate}, saveIssues. An OK typed on an older date than the latest FAIL must not resolve it. 4. Use hnxLocalToday() instead of new Date().toISOString().slice(0,10) for the _irrDate default at L38665 so the key/date is the Manila day. Add the matching guide line in hnx-help-guides-v1991 (Rooms Checklist: "a FAIL raises one critical issue per room+item; marking the item OK on the latest date closes it automatically") and a tests/payroll screen case asserting: fail x2 → 1 open issue; OK today → 0 open, history has auto-resolved.
Drum level — below warning/critical litres → issue (+toast) | irrigation | DUPLICATES + NEVER-CLEARS | YES - high | In saveDrumLevel (index.html L43133-43197), smallest change, all inside the existing function: 1. Judge from the per-room thresholds like the screen: const newStatus=drumStatus(value,roomId,drum) (and fold critical_max/warning_max into critical/warning). Drop prevVal/prevStatus entirely — the previous day's value must not matter. 2. One issue per room+drum: const key='drum_low:'+roomId+'/'+drum; const issues=loadIssues(); const open=issues.filter(i=>i.module==='irrigation'&&i.sourceId===key&&!['resolved','approved','cancelled','closed'].includes(i.status)). (Add source:'drum_low', sourceId:key to the createIssue data; createIssue L26669 must copy data.source/data.sourceId onto the issue — a 1-line addition.) Back-compat for issues raised before the fix: also match titles with new RegExp('Drum '+drum+' in '+room.label+' below'). 3. If newStatus is warning/critical: if open.length and open[0].priority===newStatus → nothing (no duplicate, no toast); if open.length and priority differs → set priority/title, push history {action:'escalated'¦'downgraded', by, at, note:value+' L on '+_irrDate}, saveIssues; else createIssue once. 4. If newStatus is 'ok' (value above the warning level): for every open match set status='resolved', resolvedAt=Date.now(), push history {action:'auto_resolved', by:'system', at:Date.now(), note:'Drum '+drum+' read '+value+' L on '+_irrDate+' — above the warning level'}, saveIssues, showToast('✓ Drum '+drum+' refilled — issue resolved','ok'). Empty value: leave as is (no reading, no change). 5. Initialise _irrDate (L38665) from hnxLocalToday() instead of toISOString() so the "today" used for the key is Manila's day. Also add a case to tests/payroll (screens) with the three numbers in its name: "drum 150 L yesterday + 150 L today = 1 open issue, 800 L = 0 open", and update the Irrigation Drum Levels guide in hnx-help-guides-v1991 (issue resolves itself on refill). The pool producer (syncPoolSensorsToMaintenance) is being fixed separately in hotfix/irr-pool; the Nexi "Drum levels today" report L278990 should call drumStatus(v,room,letter) instead of its own 300/200.
EC / pH meter drift > 0.2 → warning issue | irrigation (sensor calibration) | DUPLICATES + NEVER-CLEARS | YES - medium | Smallest change, all inside savePoolSensor / togglePoolCalib (index.html ~L40876-40945): 1. Replace the two inline createIssue blocks with one helper `_irrDriftIssue(poolId,param /*'EC'¦'PH'*/,p,m)`: key = `irr_drift:${poolId}:${param}`; find `open=loadIssues().find(i=>i.status==='open'&&i.source==='irr_drift'&&i.sourceId===poolId+':'+param)` (pass source/sourceId through createIssue; old issues can be matched by title prefix `${param} drift in ${pool.label}`). - drifted (¦p−m¦>0.2) and no open issue → createIssue once (with source/sourceId); - drifted and an open issue exists → update its title/description to the latest pair (no new issue); - not drifted (both values present, ¦p−m¦≤0.2) and an open issue exists → updateIssueStatus(open.id,'resolved',`auto: ${param} pool ${p} vs meter ${m} within 0.2 on ${_irrDate}`) (history line is added by updateIssueStatus). 2. Only judge when `_irrDate===hnxLocalToday()` (edits of an older day never raise or resolve), and initialise `_irrDate` from hnxLocalToday() instead of toISOString() so the key date is Manila local. 3. In togglePoolCalib, when a calibration is logged (cur empty → time set), resolve any open irr_drift issue for that pool with note "meter calibrated at HH:MM". 4. Add a tests/payroll case: older-day pair 2.0/2.5 → 1 open issue; today 2.0/2.05 → that issue resolved with history line; re-editing the older day → still 0 open, no duplicates; update the Irrigation calibration guide text in hnx-help-guides-v1991 and bump APP_VERSION.
T-72 EC/pH Watch — banner on Irrigation dashboard, hourly nudge toast, manual 'raise call' (critical issue) | irrigation | STALE | YES - high | Smallest change, all inside the T-72 block (index.html L159068-159199): 1. scan(): per pool, take only the LATEST slot of the day (sort Object.keys(slots) by time, use the last one that has an EC or pH number) and judge that reading only; drop the per-slot loop so one pool contributes at most one EC row and one pH row. 2. Replace ecSev/phSev with the screen's bands: var R=window.IRR_RANGES¦¦{}; crit if v<R.EC.criticalMin¦¦v>R.EC.criticalMax, warn if v<R.EC.min¦¦v>R.EC.max (same for pH); build the "target a–b" text from R.EC.min/max and R.pH.min/max instead of the literal "1.2–3.2"/"5.5–6.5" (three places: rowHTML, raise() description, modal header). 3. Dates: use hnxLocalToday() (Manila/local day) instead of toISOString() in hnxIrrWatchBanner default, __hnxIRR.open default and nudge(); keep _irrDate as the banner date. 4. Auto-resolve: in render()/nudge() (or a 60 s timer), for every key in hydroPro_irr_call_created_v1 whose pool's latest reading is now in range, find the issue by the stored id in loadIssues(), set status 'resolved' (closed), push history {action:'auto_resolved', by:'system', note:'latest reading EC x.x in range', at:Date.now()}, saveIssues(), and delete the key — so the call closes with a history line the moment the data is good, and re-raising is only possible if a NEW latest reading is out of range. Change the created-key to pool¦kind (no date/slot) so one open call per pool+parameter exists while the cause persists. 5. Nudge: fire only when s.crit>0 after step 1, and re-check the flag per local day. Also update the Irrigation guide text in hnx-help-guides-v1991 (EC/pH Watch now judges the latest round and closes its call automatically) and bump APP_VERSION.
Irrigation Matrix / Command Center checks (_irrCheckIssue: reading_today, ec_in_range, ph_in_range, water_level, drums, calib, filter, pump_ok, leaks_none, no_critical_calls) | irrigation (irr_cmd / irr matrix) | STALE + NEVER-CLEARS |  | latest round per pool; isCallClosed() for calls; read drums/calibration from the real date-keyed stores; share IRR_RANGES.
MCC_LIVE.irr_cmd — Irrigation Command Center KPI tiles (Pools off-target, Open calls, Drums low) | irrigation | MIXED |  | use hnxLocalToday(); use IRR_RANGES; count open issues only after producers resolve them (or count calls via isCallClosed).
Production cockpit v1908 (Greenhouses today, Checklist items today, Harvest & plantings, Seedling plan, Seed studies, Supervisor report, Open issues, Tech issues per GH, Production calls, Recurring tasks, Daily GH log, Process checklist) + KPIS.production | production / harvest | MIXED (checklist/harvest OK; calls and open issues inherit roots 1 and 2) |  | closes with the _autoCloseCall fix; make computeOpenIssues treat an explicit OK on the latest date as resolved immediately.
Generic module cockpit v1900 (KPI strip, critical ticker, per-screen tiles) — prio()/closed() | irrigation, production, maintenance (all modules) | MIXED (NEVER-CLEARS inherited + misclassification) |  | prio: urgent→crit, priority→warn; closed: also autoResolved.
GH Command Center criticals — _hnxGhHasCritical / ghFilteredIssues / ghFilteredCalls, 'critical' KPI, rotate-critical-only, pool EC/pH tile, static profile alerts | production (GH) / irrigation (FR mode) | NEVER-CLEARS (+ dead pool tile, static demo insights) |  | match facility exactly (word boundary), exclude autoResolved, read the pool tile from hydroPro_irr_pool[localToday][pool] latest round, delete the static 'alert' fields.
Nexi Cockpit · Digital Twin per-GH criticals (R.critical, emergency, insights) | production | MIXED |  | exclude autoResolved calls; follows roots 1-2.
HydroNexis Brain (renderHydroBrain) — checklist counts, drums low, pools critical, calls criticality | overview container (production + irrigation items) | MIXED |  | hnxLocalToday(); label the pool figure as 'trend'; exclude autoResolved.
T-111 Company Risk gatherRisk / hnxRiskBox (irrigation 'severe EC/pH today', critical issues per module, beds past harvest) | overview; items irrigation / production / maintenance | STALE |  | latest round per pool; issue counts only after producers resolve.
Daily Reports rollup — Overview 'N issues logged · N critical statuses', Executive summary 'Open critical actions' ('STILL present, 3 days running'), Brain report insights (HN_MODULE_BRAINS source 'reports') | production (reports) | STALE |  | count only the latest report per facility (lastDateForGH); drop a pattern when the latest report for that GH no longer mentions it; never seed demo reports in production.
Overview Daily Summary briefing (collectBriefingData: irrigation drums, pool cleaning, issues) | overview container; items irrigation / production | MIXED |  | use per-room thresholds; issues after producers resolve.
Operations Wall KPIs / End-of-shift report / global search — production checklist danger/warn and urgent/priority calls | company-wide (production checklist + calls) | MIXED |  | hnxLocalToday(); exclude autoResolved.
Bell scanner hnxScanForAlerts (gh_critical, machine_call) + hnxRefreshAlerts | production (GH) / irrigation (FR) | OK (gh_critical dead) |  | if GH criticals are wanted in the bell, expose the detector on window and apply the GH Command Center fixes first.
Predictive Insights auto-actions (drum runout / pool drift → maintenance call, department maintenance, sourceModule irrigation) | irrigation (irr_predictions) | DUPLICATES + NEVER-CLEARS (off by default) |  | mark the action resolved and close its call when the prediction no longer crosses the threshold; dedupe on the synced calls store by predictionKey.
Maintenance equipment check — warning/critical result → task + paired call | maintenance (equipment used by irrigation/production) | DUPLICATES + NEVER-CLEARS |  | look up open tasks by autoKey before creating; when a later check of the same item/check is OK, close the task and call with a history line.
PM scheduler pmRunScanner — PM overdue/due → task + paired call | maintenance | NEVER-CLEARS |  | on service log (_addOrUpdateService L45098) close open auto_pm_scheduler tasks/calls for that item.
NFT weekly pipe count — lost pipes → task + paired call | maintenance (subject: production pipes) | OK (minor DUPLICATES) |  | check autoKey before creating.
raiseFault / clearFault canonical helper (issue + task; callers: tool defective L51558/51576, CEA licences L258722) | caller's module | MIXED |  | dateless dedupe on open tasks; clearFault also resolves the linked issue (linkedIssueId) with a history line.
Pool-cleaning prep auto task (runPoolPrepAutoCheck) | production (prod_pool_cleaning) | DEAD / broken (writes a shape the task board never reads) |  | use loadMaintTasks/saveMaintTasks with a tag check, or delete.
GH daily log (hydroPro_gh_daily_v1) AI-parsed open issues | production | OK (human-confirmed close by design) |  | none required; show 'suggested resolved' differently from open.
Sensors — calibration/morning calibration screens (hydroPro_sensor_inventory_v1 / hydroPro_sensor_morning_v1) and drift trend | irrigation (sensors) | OK (matrix cell dead) |  | point the matrix calib/filter checks at hydroPro_irr_calibration.
syncITIssuesToMaintenance (IT devices/CCTV/radios) — shares the same registry, date and _autoCloseCall design (noted, outside this sweep) | it (department written as maintenance) | MIXED (listed for completeness; audited by the IT sweep) |  | same remedies as rows 1-3.
syncPoolSensorsToMaintenance (KNOWN CASE - being fixed in hotfix/irr-pool, listed only) | irrigation (call department 'irrigation', task sourceModule irr_pools) | STALE + DUPLICATES (already being fixed) |  | as the hotfix does: one key per pool+param, judge the latest slot only, Manila day, field-level merge; additionally treat autoResolved calls as cleared downstream (see checkEscalations row)
syncITIssuesToMaintenance: CCTV / IT device / PRJ11 device marked offline-issue-down → maintenance task + paired call | it (call department written as 'maintenance' in _createPairedCall L107340; sourceModule 'it') | NEVER-CLEARS + DUPLICATES |  | key the ledger by item only ('cctv::'+camId like radios do L107527) and look up the open task by itAutoKey in the tasks store as a fallback when the ledger lacks it; judge from the LATEST check across dates (as T-84 latestCheck does L159481-159485), close when that latest check is ok/online, add the history line, use hnxLocalToday, and prune ledger entries whose task is done
syncITIssuesToMaintenance: Radios daily check (damaged/missing/broken) → task + call | it (sourceModule it_radios; department 'maintenance' via _addPairedCall default) | MIXED |  | use hnxLocalToday; also close when the LATEST dated check (any day) is working/ok; the paired call should be closed outright when its task is done, not left 'pending verification' for ever
Maintenance equipment check: result 'critical' → URGENT task + call, 'warning' → PRIORITY task + call (saveEquipCheck) | maintenance (sourceModule maint_equipment, department maintenance, group operations) | DUPLICATES + NEVER-CLEARS |  | before pushing, look for an open task with the same autoKey (drop the date from the key: equip_check_cat_item_check) and skip; when a later check for the item has no critical/warning for that check line, auto-close the open task + paired call with history 'check passed on <date>'
PM scheduler pmRunScanner: overdue PM → URGENT task + call, due within PM_SOON_DAYS → PRIORITY task + call | maintenance (sourceModule maint_equipment) | NEVER-CLEARS |  | in _addOrUpdateService (and whenever nextService changes) auto-close open auto_pm_scheduler tasks + paired calls for that cat/item whose key nextDate != the new nextService, with history 'PM logged <date>'; key by cat+item only so a slipped date updates the existing task's title/priority instead of adding one; use hnxLocalToday
Spare part fell to/below reorder point on a decrement → task + call (_partsAdjust) | maintenance (sourceModule maint_parts; stock side is inventory) | NEVER-CLEARS |  | on an increment that lifts onHand above reorderPoint, auto-close open auto_parts_reorder tasks + paired calls for partId with history 'restocked to N'; dedupe on an open task with the same partId before creating
NFT weekly pipe count: negative variance → task + call (lost ≥10 URGENT) | maintenance (sourceModule maint_nft) | MIXED (event alert; dedupe missing) |  | skip when an open task with the same autoKey exists; when a later count for the same gh+variety is ≥ the prior, auto-resolve the open task/call 'pending verification' with a history line
raiseFault canonical helper (issue + urgent/high maintenance task + toast) - callers: CEA renewalTick, maintenance tool defective | caller's args.module (cea at L258718; maintenance at L51645) | NEVER-CLEARS |  | add resolveFault(source,sourceId) that closes the open issue + task with a history line, call it from the same places that detect the clear (CEA tick when days>14 or expiry changed; tool marked OK); dedupe on faultSource+faultSourceId regardless of date; map 'warning' to task priority 'priority'
CEA renewalTick: renewal case auto-create + §6.2 escalation + expired COMPLIANCE INCIDENT + raiseFault critical issue/task; follow-up desk and cockpit read the same register | cea / compliance (owner edelyn) | MIXED (live grading OK; persisted case/issue/task NEVER-CLEARS after renewal) |  | in renewalTick, for every open REG-RNW/CEA-INC whose extra.regItemId's current expiry ≠ the expiry in its id, auto-close with history 'renewed - new expiry <date>'; resolve the raiseFault issue/task when d>14 or expiry changed; gate the toast to CEA owners/admins
Admin-AI buildAlerts: licence expiring/expired, asset maintenance due/overdue, vehicle registration/insurance, employee requirement expired/missing, recurring not done after 16:00, admin-fleet PMS / LTO registration overdue | admin (items belong to licenses, maintenance, fleet, hr) | OK (derived) with ack caveat |  | include sev and the expiry/due value in the ack id (lic_<id>_<expiry>_<sev>) so a worsened or repeated condition surfaces again
Call auto-escalation checkEscalations: bumps priority → URGENT, marks escalated, toast 'N calls auto-escalated' | per call (module of the escalated call) | STALE (re-raises as urgent from a cleared condition) |  | in _shouldEscalate return null when call.autoResolved, when call.automatic && its maintTaskId task is done, or when the paired producer's ledger no longer holds it; never escalate 'need'; and have _autoCloseCall actually close automatic calls (closed_finalize, closeNote with the reason) so the whole stack treats a cleared reading as closed
Bell scanner v2.32 hnxScanForAlerts + hnxRefreshAlerts: delivery overdue (crit >3 d), cold storage ≥90/98 %, crates missing (crit ≥5), crates damaged, machine CALL_RAISED (crit), customer loss, GH critical (dead branch) | logistics (delivery_overdue), packaging (cold_storage_full, crates_*), production/irrigation (machine_call), crm (customer_loss) | MIXED (auto-resolve OK; re-occurrence never re-raises) |  | when a found alert matches an entry with resolvedAt set, clear resolvedAt/dismissedAt (or append the resolve date to the id) and re-notify; prune resolved entries after N days
IT Daily Checklist FAIL autoRaiseCall (P19): URGENT 'call' record in hydroPro_issues_v2 (module it, type call) | it | DUPLICATES + NEVER-CLEARS |  | dedupe on an open issue with history.sourceItemId === item.id for todayKey(); on PASS/N/A for that item close the open auto-raised issue with a history line
T-84 Device Health watch: banner (down / issue / not checked 7 d), hourly nudge toast, one-tap 'Raise call' → critical IT issue | it | MIXED |  | key the ledger by device id; when latestCheck becomes working, close the open issue with a history line
T-79 PM work-order lookahead: 'Create work order' → maintenance issue (warning ≤1 d / info), daily nudge toast | maintenance | MIXED (minor) |  | when getRecurringCompletion(...).status==='done' for a pmKey with a created issue, close that issue with history
MCC_LIVE module command centres: inv_cmd (out of stock crit, stock-out forecast, below target, pending requests), pack_cmd (W&T alerts, materials low, urgent packaging calls), log_cmd (failed deliveries crit, open logistics calls >5 crit, warehouse low, low fuel), sec_cmd (missed rounds crit, coverage <80 %, incidents 24 h, no patrol report today), maint_cmd (priority/urgent open work orders crit, flagged checks), fleet_cmd (in maintenance), lic_cmd (expired crit, due 60 d) | inventory / packaging / logistics / security / maintenance / fleet / licenses | OK (derived) / MIXED for maint_cmd and log_cmd via inherited open records |  | exclude autoResolved calls and done tasks from open counts (shared helper); grade urgent=crit, priority=warn in maint_cmd
Per-module live cockpits (<mod>_brain): maintenance v1903 (PM tasks overdue/urgent, equipment bad + latest critical check, parts out/low, recurring missed, open calls, RO latest reading, radios today), inventory/logistics/fleet/licenses v1914, packaging v1915, security v1916 (incidents, checkpoints), IT v1917 (devices down, CCTV down, licences), CEA v1899 | each module | OK (derived) / MIXED via inherited records and the v1900 prio() grading |  | shared 'isOpenAlert' helper that excludes autoResolved calls and done tasks; align v1900 prio() with cPrio (urgent/critical=crit, priority/high/need=warn)
Daily Summary briefing collectors - maintenance (tasks, ozone machines down) and security (RFID patrol missed scans crit >3, patrol report OVERDUE after 08:00, incidents today); Ops Wall _opsCollectKpis (urgent/priority/blocked calls, SIM expiring/expired, RFID %, recurring, driver hours); sec_patrol screen OVERDUE banner | maintenance / security / company-wide (Ops Wall) | OK (derived) / MIXED on the UTC day and inherited open calls |  | use hnxLocalToday in both; exclude autoResolved calls
T-111 Company Risk gatherRisk: critical/open issues per module + severe EC/pH today + missed recurring + HR overdue + beds past harvest | overview (per issue.module, irrigation, maintenance, hr, production) | STALE (inherited + all-rounds) |  | judge irrigation from the latest slot per pool; once the producers above close their issues the module scores follow
_checkNewNotifications: toast/sound/OS notification for every NEW urgent/priority call and urgent task (feeds '+N more alerts — open My Calls') | per call/task | MIXED |  | skip calls with autoResolved or whose maintTask is done; dedupe toasts by subject+area within a window
Production dashboard 'escalate recurring task' (_escalateRecurring) - noted for the Production sweep: manual button that writes a call with an autoKey per day but no dedupe | production (owners include Logistics/Maintenance) | DUPLICATES (manual) |  | skip when an open call with the same autoKey exists; close when the recurring completion is done
syncProductionToMaintenance - listed for the Production sweep as the same family as the IT sync: production checklist danger/warn, pipes, seedlings, fans → task + call | production | NEVER-CLEARS + DUPLICATES (same pattern as IT sync) |  | same as the IT sync row
KNOWN — syncPoolSensorsToMaintenance: pool EC/pH out of range → maintenance task + paired call (being fixed in hotfix/irr-pool; listed, not re-fixed) | irrigation (out of this sweep; listed as instructed) | MIXED (STALE + DUPLICATES) |  | judge only the LATEST slot per pool/param, key by pool+param (no date), use hnxLocalToday(), read the screen's shared EC/pH ranges — already in branch hotfix/irr-pool
Attendance deviations (2+ morning / 2+ evening scans, 5+ scans) — synced record + red frame + Matrix banner + e-mail | hr / attendance | NEVER-CLEARS |  | in ingest(), for every open deviation whose date is inside the pulled window and that detect() no longer returns, set status 'cleared' with a history line (who: system, why: scans no longer show it) and drop its frame; scope the banner count to the viewed month (keep a 'N older' link); add a 'cleared' filter to the panel
Attendance Integrity owners' daily toast ('N critical finding(s)') | hr / attendance | STALE |  | persist seen finding ids (date¦clockId¦kind) in localStorage and toast only unseen ones; restrict the toast to findings dated today/yesterday; use hnxLocalToday()
T-87 Attendance Anomaly Watch — HR dashboard 'Attendance' card + hourly nudge toast | hr / attendance | MIXED |  | when today has no records show 'no scans yet today' instead of falling back to the previous day (or print the day in the card and toast); skip rest days
MCC_LIVE.hr_cmd — 'No attendance scans today' (crit), memos pending FINAL, contact gaps (warn) | hr | MIXED |  | skip the no-scan critical on non-working days (hydroPro_holidays / weekday rule) and before the first bio pull; scope memos to the open cut-off or show their period
MCC_LIVE.pay_cmd — 'N memo(s) block the salaries' (crit) / 'N trip(s) not yet approved' (warn) | payroll | STALE (not scoped to the latest cycle) |  | count only memos/trips whose period overlaps the open labor week / office period (HNXPayCut), label older ones 'N older items' with a warn tone, and show the oldest date in the message
MCC_LIVE.overview_cmd — company roll-up (critical issues, salary blockers, no attendance scans, licences, cloud) | overview (items belong to production, payroll, hr, licenses, admin) | MIXED |  | same scoping as pay_cmd/hr_cmd; count only severity critical/urgent
Proactive Nexi digest + '🔴 New:' critical pushes (chat bubble + toast) | assistant (items from every MCC_LIVE module the user can see) | DUPLICATES |  | key by module+title (without the count), keep the key until liveCrits no longer returns it, then post one '✅ cleared: …' line; drop the daily reset of sent[]
T-110 Weekly Executive Summary (Monday digest, Manager Summary top chips 'N open critical') | reports / overview | MIXED |  | render the chips live (recount at paint) and keep only the AI text as the snapshot; count only issues opened or still open inside the week
Daily Summary briefing — Attendance ('Attendance only X% — N absent' crit, 'N late' warn) | hr (inside the Overview briefing) | MIXED |  | skip non-working days and before-first-pull hours; say 'no scans yet' instead
v2.32 bell scanner alerts incl. delivery_overdue (logistics) and customer_loss (crm) — bell badge, toast, browser notification | crm / logistics / packaging / production | MIXED (NEVER RE-RAISES) |  | in the merge: if existing.resolvedAt && found → clear resolvedAt, set reopenedAt, push a history line and treat it as new (toast/notify); write a 'resolved' line into the alert history when resolvedAt is set
Storage rescue — '🚑 Storage rescue (reason): X% → Y%' toast + owner-inbox item | admin / system (storage) | DUPLICATES |  | one inbox item per computer per local day (id RSC_<device>_<day>), update it in place with the latest %; post a single 'storage back under 80%' line when it recovers; keep the toast throttled to once per hour
Save guardian — red top bar 'N change(s) were NOT saved on this computer' + toast every 20 s | admin / system (storage) | NEVER-CLEARS (per session) |  | on each 45-s pass also probe a write; if it succeeds and no parked item remains, clear FAILS, remove #hnxSaveAlarm and audit 'saves working again'
Data Safety — held uploads (banner, owner screen, non-owner notice, owner-inbox alert), big-download undo notices | admin / system (sync) | MIXED (daily re-alert only) |  | optional: re-send only when the hold's stats changed, and add an inbox line when the hold is released/decided
Stale-build bar 'You are running an OLD Nexi' + upload pause (__hnxStaleApp) | admin / system (release) | MIXED |  | word the bar by direction (server newer vs older), clear __hnxStaleApp and remove the bar when a later check finds marker == mine
KNOWN CASE (being fixed in hotfix/irr-pool): syncPoolSensorsToMaintenance — pool EC/pH out of range → urgent/priority maintenance task + paired irrigation call | irrigation (call department 'irrigation', sourceModule 'irr_pools') | DUPLICATES |  | (hotfix branch) judge each pool+param once from its LATEST slot of the Manila day, keep one open item per pool+param across days, close it (call status too, with a history line) the moment the latest reading is in range, and read IRR_RANGES instead of a private table
Critical/warning toast cards + '+N more alerts — open My Calls' (#notifToastHost, _checkNewNotifications → _fireNotification) | all (toast per urgent/priority call and urgent task) | NEVER-CLEARS |  | key cards by subject (pool+param), remove a card when isCallClosed(call) becomes true (sweep every tick), recount __hnxHiddenAlerts from the cards actually hidden, and make hnxItemAgeH read raisedAt
🔎 Review old critical button + modal (hnx-critical-close-v2189) | all (open urgent calls > 7 days) | MIXED |  | hnxItemAgeH must read raisedAt first; then the modal works as designed
🔔 Alerts bell #hnxAlertBell badge + panel (hydroPro_alerts_v1) | production (GH critical, dead), logistics, packaging, crm — never irrigation calls/issues | MIXED |  | when a found alert matches a resolved record, clear resolvedAt (and log a re-raise line); route irrigation calls/issues through the same scanner or drop the bell
Irrigation Command Center MCC_LIVE.irr_cmd: 'Open calls N (N urgent)' KPI, 'N urgent irrigation call(s)' crit alert, 'Pools monitored · off-target' — the source of the rail chips, Nexi proactive pushes, CEO brief, subject strip and sitBoard department boxes | irrigation | STALE |  | count calls (open, latest condition) not issues, or give irrigation issues a dedupe key + auto-resolve on the next in-range reading; use the Manila today, never _irrDate; read IRR_RANGES
MCC_LIVE.overview_cmd 'Critical issues N' KPI / '📞 Open calls N' row (+ Nexi subject strip COMPANY OVERVIEW tile, Reports rep_cmd '1 critical issue(s) open') | overview (items belong to the issue's module) | NEVER-CLEARS |  | use isCallClosed/getCallStatus for calls; count issues only after the producers dedupe+resolve them
🎛 CEO Cockpit sitBoard: 'Production issues N — N CRITICAL', 'Open calls (14d)', NEXI EXECUTIVE BRIEF, department boxes + floating pill | overview (issues of every module are labelled 'Production issues') | NEVER-CLEARS |  | isCallClosed + raisedAt; label the tile by issue.module; count issues only once producers resolve them
🚨 Critical Summary view (renderCriticalSummary) + Overview → Modules Rollup KPI strip and per-module cards (liveItemsForModule) + T-111 Company Risk box (gatherRisk) + Daily Summary briefing 'N critical issue(s) open' | per issue.module; rollup maintenance card also lists calls by raw status | NEVER-CLEARS |  | rollup: use isCallClosed; risk: judge each pool from its latest slot with IRR_RANGES; all three depend on issue dedupe + auto-resolve at the producers
🧠 HydroNexis Brain view (hydro_brain): 'Open Calls N · N critical' tile, 'Maintenance 🔴 N critical' domain card, irrigation card | overview container; calls company-wide | NEVER-CLEARS |  | use isCallClosed(c)
Nexi chat answers: 'what is critical' (v1896), 'how many open calls', 'what needs my attention', 🔔 'Release critical alerts' overlay (gatherCriticals), cloud snapshot | all | NEVER-CLEARS |  | use window.__hnxCallStatus.closed(c) in all three predicates
Nexi left-rail live attention chips (.hnx-live-chip) + Nexi proactive pusher (chat bubble + warn toast, morning digest) | per MCC_LIVE cockpit | STALE |  | fix irr_cmd's source; key pusher dedupe by subject not title
🧠 Brain pill #hnBrainPill (URG N), sidebar .hn-mod-badge red badges, Overview brain rollup panel (buildOverviewRollupPanel / hnAggregateAcrossModules), production matrix brain overlay | all 16 brains | NEVER-CLEARS |  | drop the demo insights (count only source:'reports') or feed the pill from the normalised live alert set
Old per-module brain: computeBrainInsights URGENT card + lifecycle layer (hnxModuleCalls / drawGenericBrainEnhancement) | currentModule | NEVER-CLEARS |  | filter issues by open status and calls by isCallClosed before picking
💧 Irrigation Dashboard (irr_dash) 'warnings' count and T-72 EC/pH Watch banner / nudge toast / 'Raise call' modal | irrigation | MIXED |  | judge per pool from the latest slot; resolve the raised issue when the next slot is in range; use IRR_RANGES
Overview → 🌅 Daily Summary (collectBriefingData) irrigation collector + TOOLS Daily Summary / Operations Wall | overview container; irrigation items | MIXED |  | read r.EC / r.pH, judge per pool from the latest slot with IRR_RANGES
Production dashboard matjump 'Open Calls' tile and _renderDbOpenCalls list | production | MIXED |  | route by _moduleOfView(sourceModule) only; remove the dead getAllCalls tile or point it at loadCalls
Call auto-escalation checkEscalations (bumps open 'priority' calls to URGENT after N hours/days, toast 'N calls auto-escalated') | per call | STALE |  | never escalate auto-raised (raisedBy 'system') calls whose condition can be re-checked; re-check the subject before bumping

## Eyal - your side
# | Action | Why | When | How
1 | Undo the 2 "Upload anyway" clicks | Those two stores overwrote everyone's data with this computer's copy | TODAY | Console (Cmd+Option+J): paste the undo script sent 06:22, press OK twice
2 | Close criticals up to 30 Sep | Clears the backlog that keeps the counts high | TODAY | Console: paste the close-September script sent 06:22
3 | Take the cloud copy on the held uploads (not "Upload anyway") | pa inbox / recurring / issues holds are space clean-ups, not your edits | when the banner shows | Administration -> Data Safety -> "Take the cloud copy" per row
4 | Change the admin / admin123 password | Worker v3.7.2 will refuse that login | before step 5 | Administration -> Users
5 | Paste worker v3.7.2 into Cloudflare (hnx-sync) | Default admin can no longer get a cloud token; KV cursor past 1,000 keys | after #18 ships | Cloudflare -> hnx-sync -> paste workers/hnx-sync-worker.js; /health shows 3.7.2-nexi
6 | Mark trial computers | So the trial release reaches them first | before the trial release | TOOLS -> 🚦 Release control -> trial
7 | Answer 3 defaults if you disagree | RFQ check limit 20% / ₱50,000; schedules approver = Jinky + Eyal + Dr Amy; assets: no VAT change, no salvage | any time | Reply here
8 | Confirm v21.71 fill rule retired | Pool dosing goes back to your matrix for all pools | any time | Reply here