## Summary
Nexi — Maintenance module audit |  | v20.07 · 14 Sep 2026 · prepared for Eyal
Scope |  | Every Maintenance screen (12 tabs + 5 hidden register views), every control handler the rendered screens call, every localStorage store the module touches, every cross-module link, run in a real browser as System Admin on seeded data
Screens rendered | 17 | all 17 active, no page error attributable to a screen
Handlers checked | 56 | every one defined after v20.07 (2 were dead before: Radio add / delete)
Stores | 42 | all cloud-synced (hydroPro_ prefix)
Cross-module links | 16 | 10 verified · 4 built/fixed · 2 design items
Findings | 11 | 6 fixed (v20.04–20.07) · 4 design / to do · 1 cosmetic
Status legend | ✅ | verified — works as designed, proven in the browser or in the code
| 🔧 | fixed or built in the version named
| ⚠ | defect or smell not yet fixed
| ❓ | to confirm with you, or a design item carried into the Maintenance proposal
Method |  | Static scan of index.html for the module’s views, stores and functions; Playwright sweep switching to every view, recording render, handler existence on window, page errors and text smells; targeted probes with seeded tasks, calls, stock and schedule; each finding fixed then re-swept.
Companion |  | Design proposal “Maintenance, Rebuilt”: https://claude.ai/code/artifact/43aad302-5996-4550-aa54-1528731ade04

## Screens
View id | Label | Permission | Placement | Renders as admin | HTML bytes | Handlers referenced | Dead handlers | Page errors | Text smells (undefined / NaN / [object]) | First line of screen | Notes | Status
maint_cmd | 🎯 Command Center | viewMaintenance | tab | yes | 27274 | 0 | — | — | no | ── ¦ HYDRONEXIS-AI BRAIN ¦ · ¦ MAINTENANCE · COMMAND CENTER ¦ ANALYZING LIVE ¦ A | Cockpit boxes are built by the v19.00 cockpit engine: 12 boxes, each with a go: target. Box counts verified against stores; the Open calls box counts every open call on the site — the screen behind it now matches (v20.07). Design proposal replaces the 12 boxes with 4 tabs. | ✅ verified — renders as admin, every handler defined, no page error
maint_dash | Dashboard | viewMaintenance'} | tab | yes | 25877 | 6 | — | — | no | 📞 Reactive (Calls) ¦ 🔁 Recurring Tasks ¦ ➕ Additional Tasks ¦ 🔧 ¦ HYDRONEXI |  | ✅ verified — renders as admin, every handler defined, no page error
maint_tasks | ✅ Task Board | viewMaintenance | tab | yes | 22849 | 7 | — | — | no | 📞 OPEN CALLS (ALL DEPARTMENTS) ¦ View My Calls → ¦ 📞 TOTAL OPEN ¦ 2 ¦ 📞 NEW |  | 🔧 fixed v20.06 — adding a material to an existing task was silently lost on redraw (openMaintTask replaced the draft); the material box is now the SOS drop box
maint_calendar | 📅 PM Calendar | viewMaintenance | tab | yes | 19581 | 4 | — | — | no | 📅 PREVENTIVE MAINTENANCE CALENDAR ¦ 📅 Schedule overview. All maintenan | Reads hydroPro_maint_tasks with a scheduledDate and status ≠ done; a task due tomorrow renders on its day (verified in HTML). “Nothing due this week” beside “66 overdue” is consistent but confusing — design item. | ✅ verified — renders as admin, every handler defined, no page error
maint_materials | 📦 Material Requests | viewMaintenance | tab | yes | 4764 | 5 | — | — | no | 📦 MATERIAL REQUESTS — PREP & TRACKING ¦ 📦 Pre-task material prep. When |  | 🔧 fixed v20.06 — material name was free text with no SOS link and nothing reached the warehouse; SOS type-ahead on the task, 📦 Raise item request per line / all pending, request number written back; PLUS a pre-existing defect: openMaintTask() discarded the draft so an added material vanished — fixed
maint_equipment | ⚙️ Equipment & Machines | viewMaintenance | tab | yes | 49217 | 3 | — | — | no | ⚙️ EQUIPMENT & MACHINES ¦ ← Maintenance ¦ 📏 ¦ NFT Pipes Count ¦ 📦 8146 pipes | Hub for radios / ozone / RO / tools / NFT — the five hidden views are reached from here only. | ✅ verified — renders as admin, every handler defined, no page error
maint_parts | 🔩 Spare Parts | viewMaintenance | tab | yes | 45607 | 3 | — | — | no | 🔩 SPARE PARTS INVENTORY ¦ ← Maintenance ¦ 📋 Reorder needed ¦ 0 parts OUT o |  | ✅ verified — renders as admin, every handler defined, no page error
maint_matrix | 📊 Calls Matrix | viewMaintenance | tab | yes | 574989 | 5 | — | — | no | DAILY FOLLOW-UP ¦ 🕘 History · date to date ¦ per GH · category · CSV ¦ 📊 M | Calls × department board; shows the critical checklist-raised call. 575 KB of HTML per render — heavy but renders in ~1.4 s. | ✅ verified — renders as admin, every handler defined, no page error
maint_recurring | 🔥 Recurring Tasks | viewMaintenance | tab | yes | 30956 | 2 | — | — | no | 🔥 RECURRING TASKS MANAGEMENT ¦ — 50 TASKS · 92 DUE TODAY · VIEWING MAIN |  | 🔧 fixed v20.07 — a Maintenance-OWNED long-cadence task classified under Irrigation (overhead tank, 10K drums) was hidden on this hub while the follow-up strip counted it; the owner’s hub shows it. Also carries v20.04/20.05 (next-due schedule, follow-up strip, Today grid grouped by owner)
maint_open_calls | 📞 Open Calls | viewMaintenance | tab | yes | 6076 | 0 | — | — | no | 📞 ¦ 2 open calls on the site — Maintenance handles all calls · 1 raised |  | 🔧 fixed v20.07 — showed only calls raised from Maintenance screens while the cockpit box counted every open call on the site (68 critical vs a handful); now every open call with the module it came from; tab badge uses the same rule
maint_tech_per_gh | 🔧 Tech Issues per GH | viewMaintenance | tab | yes | 392581 | 1 | — | — | no | 🔧 TECH ISSUES MATRIX — 22 CATEGORIES × 14 FACILITIES ¦ ✓ ALL CLEAR ¦ 📞 R | A view over open calls with sourceModule prod_tech_per_gh (shared renderer with Production). Fan issues from the checklist (hydroPro_fan_issues_v1) are a separate store and do not appear here — design item: merge in Open work. | ✅ verified — renders as admin, every handler defined, no page error
maint_irr_rooms | 💧 FR Matrix | viewMaintenance | tab | yes | 112671 | 2 | — | — | no | DAILY FOLLOW-UP ¦ 🕘 History · date to date ¦ per GH · category · CSV ¦ 💧 I | Same FR matrix as Irrigation (shared renderer). | ✅ verified — renders as admin, every handler defined, no page error
maint_ozone | 🌀 Ozone | viewMaintenance | tab | yes | 9946 | 2 | — | — | no | ← Back to Equipment Hub ¦ · ¦ 🌀 Ozone ¦ 🌀 OZONE MACHINES — HEALTH MONITOR ¦ |  | ✅ verified — renders as admin, every handler defined, no page error
maint_ro | 💧 RO | viewMaintenance | tab | yes | 8610 | 3 | — | — | no | ← Back to Equipment Hub ¦ · ¦ 💧 Reverse Osmosis ¦ 💧 REVERSE OSMOSIS MACHIN |  | ✅ verified — renders as admin, every handler defined, no page error
maint_radio | 📻 Radio | viewMaintenance | tab | yes | 45485 | 5 | — | — | no | ← Back to Equipment Hub ¦ · ¦ 📻 Radio ¦ 📻 DAILY RADIO REPORT ¦ 📻 Daily radi |  | 🔧 fixed v20.07 — ➕ Add Radio Unit and row ✕ called addRadioUnit()/deleteRadioUnit(), never defined (dead buttons); implemented on the custom unit store
maint_tools | 🔧 Tools | viewMaintenance | tab | yes | 88200 | 6 | — | — | no | ← Back to Equipment Hub ¦ · ¦ 🔧 Tools ¦ 🔧 TOOLS & EQUIPMENT ¦ 📋 Inventory ( |  | ✅ verified — renders as admin, every handler defined, no page error
maint_nft | 📏 NFT Pipes | viewMaintenance | tab | yes | 34240 | 2 | — | — | no | 📏 NFT PIPES INVENTORY ¦ + NFT Pipes Add Call ¦ 📏 Run Weekly Count ¦ 📊 Exp |  | ✅ verified — renders as admin, every handler defined, no page error

## Handlers
Screen | Handler called from the screen | Defined | Status
maint_dash | _setRecurringMode | yes | ✅ defined on window
maint_dash | switchView | yes | ✅ defined on window
maint_dash | _drillTasks | yes | ✅ defined on window
maint_dash | openMaintTask | yes | ✅ defined on window
maint_dash | maintExportTasks | yes | ✅ defined on window
maint_dash | maintBulkImport | yes | ✅ defined on window
maint_tasks | _drillModuleCalls | yes | ✅ defined on window
maint_tasks | viewCallDetail | yes | ✅ defined on window
maint_tasks | hnxMaintAI | yes | ✅ defined on window
maint_tasks | switchView | yes | ✅ defined on window
maint_tasks | maintExportTasks | yes | ✅ defined on window
maint_tasks | openMaintTask | yes | ✅ defined on window
maint_tasks | _maintGanttNav | yes | ✅ defined on window
maint_calendar | _maintCalNav | yes | ✅ defined on window
maint_calendar | switchView | yes | ✅ defined on window
maint_calendar | openMaintTask | yes | ✅ defined on window
maint_calendar | _maintCalDayDrill | yes | ✅ defined on window
maint_materials | hnxMaintMatRaiseAll | yes | ✅ defined on window
maint_materials | _maintMatBulkPrep | yes | ✅ defined on window
maint_materials | _maintMatExport | yes | ✅ defined on window
maint_materials | maintTogglePrepared | yes | ✅ defined on window
maint_materials | openMaintTask | yes | ✅ defined on window
maint_equipment | switchView | yes | ✅ defined on window
maint_equipment | openNftCountModal | yes | ✅ defined on window
maint_equipment | exportNftCSV | yes | ✅ defined on window
maint_parts | switchView | yes | ✅ defined on window
maint_parts | openPartEdit | yes | ✅ defined on window
maint_parts | exportPartsCSV | yes | ✅ defined on window
maint_matrix | switchView | yes | ✅ defined on window
maint_matrix | _exportMaintMatrixCSV | yes | ✅ defined on window
maint_matrix | _maintMatrixDrillDept | yes | ✅ defined on window
maint_matrix | _maintMatrixDrillSubject | yes | ✅ defined on window
maint_matrix | hnxOpenCellBox | yes | ✅ defined on window
maint_recurring | _setRecurringHubTab | yes | ✅ defined on window
maint_recurring | hnxOpenCellBox | yes | ✅ defined on window
maint_tech_per_gh | _openUnifiedProdTechCall | yes | ✅ defined on window
maint_irr_rooms | _openUnifiedIrrCall | yes | ✅ defined on window
maint_irr_rooms | hnxOpenCellBox | yes | ✅ defined on window
maint_ozone | switchView | yes | ✅ defined on window
maint_ozone | openMaintOzone | yes | ✅ defined on window
maint_ro | switchView | yes | ✅ defined on window
maint_ro | maintExportRO | yes | ✅ defined on window
maint_ro | maintSaveROParam | yes | ✅ defined on window
maint_radio | switchView | yes | ✅ defined on window
maint_radio | addRadioUnit | yes | ✅ defined on window
maint_radio | maintExportRadio | yes | ✅ defined on window
maint_radio | maintSaveRadio | yes | ✅ defined on window
maint_radio | deleteRadioUnit | yes | ✅ defined on window
maint_tools | switchView | yes | ✅ defined on window
maint_tools | switchToolsTab | yes | ✅ defined on window
maint_tools | exportToolsInventory | yes | ✅ defined on window
maint_tools | toolCheckoutPrompt | yes | ✅ defined on window
maint_tools | toolMarkDefectivePrompt | yes | ✅ defined on window
maint_tools | toolMarkRepairedPrompt | yes | ✅ defined on window
maint_nft | openNftCountModal | yes | ✅ defined on window
maint_nft | exportNftCSV | yes | ✅ defined on window

## Stores
localStorage key | References in index.html | First line | What it holds | Cloud-synced | Status
hydroPro_calls | 64 | 17435 | every call on the site | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_fan_issues_v1 | 3 | 16614 | fan defects from the Production checklist | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_inv_requests_v1 | 15 | 18152 | item requests (Maintenance materials raise into it since v20.06) | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_inv_stock | 18 | 62815 | manual stock list merged with the SOS cache (the type-ahead reads the merge) | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_issues_v2 | 65 | 18426 | issue tracker | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_issues_v2_PRE_P1_ | 1 | 143620 |  | yes (hydroPro_ prefix) | ❓ referenced once — confirm it is still used
hydroPro_it_radios | 13 | 36692 | IT radio register (daily status reuses hydroPro_maint_radio) | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maint_custom_names | 1 | 48471 |  | yes (hydroPro_ prefix) | ❓ referenced once — confirm it is still used
hydroPro_maint_equipment_checks_v1 | 3 | 43282 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maint_equipment_seed_version | 1 | 43286 |  | yes (hydroPro_ prefix) | ❓ referenced once — confirm it is still used
hydroPro_maint_equipment_v1 | 4 | 43281 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maint_imported_ | 2 | 42303 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maint_locations_custom | 1 | 42135 |  | yes (hydroPro_ prefix) | ❓ referenced once — confirm it is still used
hydroPro_maint_nft_counts_v1 | 3 | 28180 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maint_nft_storage_v1 | 2 | 46408 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maint_nft_variance_threads_v1 | 2 | 46435 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maint_ozone | 2 | 42356 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maint_parts_seed_version | 1 | 44282 |  | yes (hydroPro_ prefix) | ❓ referenced once — confirm it is still used
hydroPro_maint_parts_usage_v1 | 2 | 44281 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maint_parts_v1 | 3 | 44280 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maint_radio | 11 | 36697 | daily radio check status | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maint_radio_custom | 2 | 36697 | added/removed radio units (written by the v20.07 handlers) | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maint_ro | 2 | 42358 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maint_tasks | 17 | 28198 | Task Board tasks (materials live inside each task) | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maint_tasks_v1 | 1 | 239852 |  | yes (hydroPro_ prefix) | ❓ referenced once — confirm it is still used
hydroPro_maintenance_checklist | 4 | 101119 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_maintenance_checklist_config | 2 | 101119 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_pm_last_scan | 1 | 44166 |  | yes (hydroPro_ prefix) | ❓ referenced once — confirm it is still used
hydroPro_pm_nudge | 1 | 154176 |  | yes (hydroPro_ prefix) | ❓ referenced once — confirm it is still used
hydroPro_pm_wo_created_v1 | 4 | 75376 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_recurring_completions_v1 | 6 | 17014 | recurring task ticks per day × task × GH | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_recurring_defs | 2 | 104417 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_recurring_instances | 5 | 104422 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_recurring_migrated_v2 | 1 | 104424 |  | yes (hydroPro_ prefix) | ❓ referenced once — confirm it is still used
hydroPro_recurring_occurrences | 3 | 104418 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_recurring_seed_v1 | 2 | 104419 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_recurring_tasks_custom_v1 | 2 | 135416 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_recurring_v1 | 3 | 214433 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_rt_schedule_v1 | 1 | 6764 | v20.04 next-due / last-done / note per long-cadence task | yes (hydroPro_ prefix) | ❓ referenced once — confirm it is still used
hydroPro_tools_checkouts | 4 | 50214 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen
hydroPro_tools_history | 1 | 50366 |  | yes (hydroPro_ prefix) | ❓ referenced once — confirm it is still used
hydroPro_tools_overrides | 2 | 50365 |  | yes (hydroPro_ prefix) | ✅ read/written by a live screen

## Links
Area | Link | Mechanism | How verified | Status
Calls | Maintenance Open Calls ← every open call (any module) | renderModuleOpenCalls / tab badge | Browser: checklist-raised critical and Maintenance-raised call both listed with origin badge | 🔧 fixed v20.07 — screen now matches the cockpit box
Calls | Tech Issues per GH ← calls with sourceModule prod_tech_per_gh | renderProdTechPerGh (shared with Production) | Browser: renders; fan issues from the checklist store are not part of it | ❓ design — merge fan issues into Open work (proposal)
Calls | Calls Matrix ← all open calls by subject × department | renderMaintMatrix | Browser: shows the seeded critical call | ✅ verified
Inventory / SOS | Task material ← SOS item list (type-ahead) | hnxSosTypeahead → _invLoadStock (SOS cache + manual) | Browser: “pvc” lists “4 inch PVC pipe” first; “valve” finds “Gate valve 1 inch”; sku/number/unit filled | 🔧 built v20.06
Inventory / SOS | Material Requests → Item Requests | hnxMaintMatRaise → __hnxInvReq.createExternal | Browser: IR0914-26-001 created (module maintenance, chain Department Manager, link maint_task:MT1), number written back, no duplicate | 🔧 built v20.06
Inventory | Spare Parts low → reorder | maint_parts screen; cockpit box “Spare parts · low” | Browser: renders; reorder is a manual step | ❓ design — a low part should raise an item request with one press (proposal: Open work → next step)
Production | Recurring hub shared (Today grid, Week, Month) | renderRecurringHub + GH-matrix override, filter pinned to Maintenance | Browser: Maintenance-owned tank task now visible on this hub | 🔧 fixed v20.07
Production | Tech Issues per GH shared renderer | renderProdTechPerGh renders into whichever view is active | Browser: renders in the Maintenance view | ✅ verified
Irrigation | FR Matrix shared | maint_irr_rooms | Browser: renders (106 KB) | ✅ verified
IT | CCTV stays with IT; Radios shared register | it_cctv view exists; hydroPro_it_radios vs hydroPro_maint_radio | Static: both keys live; daily check reuses the maintenance key | ✅ verified — design: show read-only in Radios & devices section
HR | Assignees on tasks ← employees | _fleetEmployees / employees store | Static + browser: task editor assignee picker renders | ✅ verified
Overview | Task Calendar ← long-cadence due dates | hnxRtDueOn (v20.04) | Browser (v20.04 test): 🔁 chip on the due day, ✓ Done in the day drill | ✅ verified
Digital Twin | GH twin → fan issues / calls per GH | __n2Real exposed (v20.03) | Browser (v20.03 test): fan issue row and call row open their detail | ✅ verified
Cockpit | 12 cockpit boxes → their screens | go: targets in the cockpit engine (maint_tasks, maint_calendar, maint_equipment, maint_parts, maint_materials, maint_recurring, maint_open_calls, maint_tech_per_gh, maint_ozone, maint_ro, maint_radio, maint_nft) | Static: every box has a go: target that exists in the view list | ✅ verified
Label printer | Print QR tags | _hnxOpenLabelPrinter | Static: function present | ✅ verified
Cloud sync | All maintenance stores | shouldSync accepts any hydroPro_ prefix | Static | ✅ verified

## Findings
# | Finding | Where | Detail | Raised by | Status
1 | Material Requests not connected to Item Requests / SOS | maint_tasks · maint_materials | Free-text material names; nothing reached the warehouse; no SOS identity | Eyal | 🔧 fixed v20.06 — SOS type-ahead on the task; Raise item request (one / all); request number written back; linked to the task
2 | Adding a material to a task was lost on redraw | maint_tasks | openMaintTask() replaced the in-memory draft with the stored copy after every sub-action, so maintAddMaterial() pushed and the redraw discarded it (5 call sites) | audit | 🔧 fixed v20.06
3 | Cockpit “Open calls” box ≠ Open Calls screen | maint_cmd · maint_open_calls | Box counted every open call on the site (68 critical); screen showed only calls raised from Maintenance screens | audit | 🔧 fixed v20.07 — screen and tab badge use the cockpit rule; origin badge per call
4 | Radio Add / Delete buttons dead | maint_radio | addRadioUnit() and deleteRadioUnit() referenced by the buttons but never defined anywhere | audit (handler sweep) | 🔧 fixed v20.07
5 | Maintenance-owned tasks hidden on the Maintenance hub | maint_recurring | overhead tank / 10K drums are classified under Irrigation in RECURRING_TASK_MODULES; the hub filter hid them while the follow-up strip counted them | audit | 🔧 fixed v20.07 — owner’s hub shows them; the section field (design Phase 1) is the proper home
6 | 66 PM tasks overdue, oldest 120 days; critical calls 134 days old | maint_cmd · maint_tasks · calls | Not a code defect — records nobody closed. A list that old is not worked from | Eyal’s screenshot | ❓ to do with Jomel — the design’s 60-day review (Open work) clears it and keeps it clear
7 | Long-cadence tasks with no schedule, follow-up or calendar place | maint_recurring | Cards with a cadence word only | Eyal | 🔧 fixed v20.04 (schedule + follow-up + calendars) and v20.05 (Today grid grouped by owner)
8 | Fan issues (checklist) and tech issues (calls) live apart | maint_tech_per_gh | Two stores, two screens for the same kind of thing | audit | ❓ design — one Open work list (proposal Phase 2)
9 | Spare parts low → no action path | maint_parts | A low part is a number on a box; reorder is manual | audit | ❓ design — one press raises an item request (proposal Phase 2)
10 | 12 cockpit boxes, 12 questions | maint_cmd | No order to work through; registers as boxes | Eyal | ❓ design — 4 tabs (Today · Sections · Open work · Calendar), registers inside their section
11 | Page error at load: NotSupportedError (media source) | global | An <audio>/<video> element with no playable source at boot; not Maintenance code | audit | ⚠ cosmetic — no functional effect; noted for the global audit