## Summary
Nexi Purchasing audit — re-audit against v22.28 (10 Oct 2026)
Findings | 84
Fixed | 13
Partly fixed | 9
Open | 62
Shipped since the v21.49 audit
v21.53 Department dropdown; tab bar never folds
v21.54 Sourcing shows only suppliers that fit the item; web suggestions; add supplier
v21.55 Supplier 360° relevant-first history; SOS uom fix
v21.64 Apple-to-apple offers: unit price, VAT, delivery, spec, validity, landed ₱/unit, flags, score, Excel
v21.65 ONE Purchasing module (From Inventory, Suppliers & tools tabs); local vs import sourcing; edit gate; numbering; sync stamps; audit ids
v22.28 Approvals by Eyal / Dr Amy only, Jinky checks first, no self-approval (PW-02, LV-04); cumulative invoice match and invoice approval permission (PW-06)
Still open — needs decisions / next phases
Approval by amount band and multi-level chain (PW-03, IV-05) — needs the bands from Eyal (signers and no-self-approval done in v22.28)
Payment stage / AP ageing (PW-12, LV-03) — the cumulative invoice match is done (v22.28)
PO line prices from the offer, not scaled estimates (PW-07)
Edit / cancel of PR, RFQ, PO (PW-10); receiving checks (PW-11)
QuickBooks bill / SOS PO push (PW-13/14, IV-01/03/07/14) — needs the QB-by-Nexi decision
RFQ e-mail/SMS through a Nexi worker instead of mailto: (QT-01/02, PW-19)
Purchase history slimming and SOS import filters (QT-03/04/22)

## Findings
ID | Area | Severity | Status (5 Oct 2026) | Status note | Finding | Scenario | Fix
PW-01 | permissions | critical | Fixed v21.65 | Every mutating action now needs Accounting / Purchasing EDIT (canEditPurch); approve / award / issue stay with managers + Admin. View perm left open so Purchasing staff can read. | View is perm:null and only Approve / Award / Issue PO check canApprovePurch(). Save, submit, AI override, every stage advance, RFQ, quotes, amend PO, GRN, 'Complete anyway', add invoice and Force-approve invoice have no role check. | Any operator opens Accounting → Purchasing, logs a fake invoice against an issued PO and clicks Force approve: it shows Approved with their name. The same user can type quotes, record a GRN that raises SOS stock, or close a PR. | Give the view a real permission (viewAccounting) and a second gate (purchasing edit) on every mutating action; keep invoice approval behind the approver gate.
PW-02 | approval gate | high | Fixed v22.28 | Approve, award and issue: Eyal or Dr Amy only (plus approvers added in 👥 Purchasing roles); Jinky checks the content first and gets an inbox notice; nobody approves or awards a PR they raised (test purch-chain-v2228). | canApprovePurch() = admin, admin_secondary or anyone with Payroll EDIT (managePayroll). deptApprove never compares the requester with the approver. | A payroll clerk is a purchasing approver. One admin creates a ₱500,000 PR, submits, approves, awards and issues the PO alone; nothing stops it. | Dedicated approvePurchasing permission on the Accounting/Purchasing module; refuse approval/award by the requester.
PW-03 | approval gate | high | Open |  | AI 'not required' verdict lets any user close the PR as Completed, skipping Department Approval. No amount threshold, no multi-level chain; the override of the AI verdict is ungated. | The AI substring match (PW-16) says stock covers the need; a user clicks 'close as not required' and a legitimate ₱200k request vanishes without a manager seeing it. | Route 'not required' through the approval gate and add an amount-based chain stored on the PR.
PW-04 | numbering | critical | Fixed v21.65 | num() = max(existing synced numbers, counter)+1 per prefix and year. | Document numbers come from a per-device counter in localStorage; the counter object merges as max(), while records merge per random id, so two records with the same number both survive. A lost counter restarts at 000001. | Eyal creates PR-2026-000007 in the office while Accounting creates one on a laptop → both are PR-2026-000007, both stay, the next is 000008. | Next number = max existing in the synced array + 1, re-checked after each cloud pull; one-time renumber of collisions.
PW-05 | sync | high | Fixed v21.65 | savePR / saveRFQ / savePO stamp updatedAt; inventory links stamped too. | PR/RFQ/PO/GRN/invoice writes never set updatedAt, so the cloud merge ties on createdAt and keeps each device's own copy; stage and status are scalars that never converge. | Device A approves PR-7; device B still holds the old stage; after sync both machines disagree permanently and the cockpit counters differ per device. | Stamp updatedAt=Date.now() on every write.
PW-06 | invoice 3-way match | critical | Fixed v22.28 | Cumulative per PO: invoiced-to-date + this invoice ≤ PO total, so a second invoice for an amount already billed shows Exception; approving an invoice needs Eyal or Dr Amy and re-runs the match first (test purch-chain-v2228). | An invoice is matched against the WHOLE PO total ±1% and the GRN value ±2%; previously logged invoices are not summed. Duplicate check is invoice number only. | INV-1 for ₱100,000 (PO total) → Matched. INV-2, different number, same ₱100,000 → also Matched and approvable: double payment. Two honest partial invoices (₱40k + ₱60k) both show Exception. | Cumulative match: invoiced-to-date + this ≤ PO total; this ≤ received value not yet invoiced; per-line when lines exist.
PW-07 | PO | high | Open |  | PO line prices are invented: PR estimates scaled by quote total ÷ estimate. With no estimates every PO line is ₱0 while the total is the quote. | PR lines entered without Est ₱ → PO issued with ₱0 unit prices; the supplier e-mail shows '@ 0'; GRN value stays 0; every invoice is 'Waiting GRN' forever. | Capture per-line unit prices on the quote and build the PO from them; refuse award when no prices exist.
PW-08 | award | high | Partly | Award passes a quote-stripped name; names with quotes still risky. Scheduled with the Purchasing rebuild. | The award button passes the supplier name inline; esc() turns ' into &#39; which the browser decodes back inside the onclick, so the JS string breaks. | Recommended supplier 'D'Agro Supply' → 'Approve award → generate PO' throws and nothing happens; the PR is stuck. | Pass only the PR id and recompute the recommended supplier inside award().
PW-09 | quotes | medium | Fixed v21.64 | Offer form: qty, unit price, VAT in/out, delivery, brand/spec, validity, file; apple-to-apple evaluation, score, Excel. | A quote is one typed total plus lead days/terms/warranty: no per-line prices, no VAT-inclusive flag, currency, validity or attachment. Ranking is by total only; late quotes are accepted silently. | Supplier A ₱98,000 ex-VAT vs B ₱105,000 VAT-inclusive: A is 'cheapest' though B is cheaper. | Quote lines, vatIncluded, currency, validUntil; normalise before ranking; block quotes after closing date without a reason.
PW-10 | PR | high | Open |  | No edit of an existing PR; rejection sends it to Draft with only a Submit button; no cancel/void for PR, RFQ or PO; 'Amendment' appends a sentence and changes nothing. | Manager rejects 'qty too high' → requester can only resubmit the same PR. Supplier delivers 80 of 100 → the PO stays 100 and can never be closed. | Editable Draft with revision, Cancel request, Cancel/close PO with reason, real PO revisions.
PW-11 | receiving | high | Open |  | No over-receipt check; PO flips to Partially Delivered even when only rejected qty was entered; date cannot be back-dated; catalogue match uses a field PO lines never carry, so matching falls back to exact name equality. | Receiver types 1000 instead of 100 → posted to history and SOS. 'PVC pipe 2in' vs catalogue 'PVC Pipe 2" Sched 40' → 'not in catalogue — stock not raised': receiving almost never updates inventory. | Clamp to remaining, carry the SKU from a catalogue picker on the PR line, match on SKU first.
PW-12 | payment | high | Open |  | The flow ends at invoice Approved: no payment record, due date, AP ageing, partial payment or Paid state; payTerms captured on the quote is never used. | Accounting approves 30 invoices; nobody can see which are paid or due this week. | Payment stage: due date from terms, Record payment, Paid state, AP-due alert.
PW-13 | QuickBooks | medium | Open |  | Nothing in the Workspace references QuickBooks; no code anywhere creates a QB Bill or PO (the QB worker is read-only: query/entity/reports). | A user assumes approving an invoice posts a bill to QuickBooks; the books must be updated by hand and nothing flags it. | Add /qb/create-bill (and vendor) to the QB worker and a 'Post bill to QuickBooks' action storing qbBillId; until then say 'QB posting is manual' on screen.
PW-14 | SOS Inventory | medium | Open |  | SOS is only read for on-hand hints and written for catalogue-matched receipts. The PO itself is never pushed to SOS although /sos/create-po exists. | After issuing PO-2026-000003 the user looks for it in SOS APAC — it is not there; the receipt later arrives without a PO. | On Issue PO build the SOS purchase-order payload and call /sos/create-po; store sosId and show push state.
PW-15 | sourcing | medium | Partly v21.54/65 | Vendor master gets category; Import class and Imported-before suppliers; still name-keyed. | Suppliers are free-text names everywhere (RFQ, PO, scorecard, history). The gather function unions two supplier stores by name and creates new vendor rows for every new spelling. | 'ACME Trading' and 'Acme Trading Corp' appear twice; the scorecard shows two suppliers with half the orders each. | supplierId on every record pointing at one canonical vendors store; de-duplicate by normalised name.
PW-16 | AI gate | medium | Open |  | The catalogue hint matches the FIRST item whose name merely contains the PR text; if its on-hand ≥ qty the verdict is 'No purchase — stock covers need' at 95% confidence. | PR 'Filter' matches 'Filter housing 10in' with 500 on hand → 'Purchase not required', and PW-03 lets the PR be closed on that. | Match SKU/code first, exact name second; substring hits are 'possible matches' only; a human picks the item.
PW-17 | PR | medium | Open |  | 'Purchasing Review' and 'Inventory Verification' are one-click pass-throughs; no buyer assigned, no verification result stored. | Any user clicks through both stages in two seconds; nobody can later see who verified stock or what was on hand. | Persist buyer and a stock-check snapshot before advancing.
PW-18 | PR | medium | Open |  | 'Complete anyway' closes a PR with nothing received; the PO stays Issued and Mission Control keeps alerting 'PO past delivery date' forever. | After 20 completed-anyway PRs the Alerts box is permanently full of stale POs and real ones are cut off. | Require a reason, set PO 'Closed – short', exclude closed POs from alerts.
PW-19 | RFQ | medium | Open |  | 'SENT' is stamped as soon as a mailto:/sms: link opens; nothing confirms a send. Reply rate divides by these. | No mail client on the PC → nothing sent, RFQ shows SENT, supplier later scored 0% reply. | Distinguish confirmed sends from opened drafts; count only confirmed.
PW-20 | scorecard | medium | Open |  | On-time uses the PR need-by date, not the supplier's promised lead time; each GRN counts as a sample. | Supplier promised 5 days, delivered in 25, PR need-by was 30 days out → scored on-time. | Promised date = issued + lead days; compare with the first/completing GRN.
PW-21 | UI | medium | Open |  | innerHTML rewritten on every action; a 600 ms injector and a 4 s interval run forever; in-progress GRN/quote inputs live only in the DOM. | User fills six GRN boxes, a re-render fires, all inputs are blank again. | Keep in-progress values in state; drop the intervals (the view div is static).
PW-22 | UI | low | Open | Signature still AteretPaz in RFQ text. | Every RFQ e-mail/SMS is signed 'AteretPaz'. | Suppliers receive RFQs from ABA Pardes signed by another company. | Use the active company name.
PW-23 | analytics | low | Open |  | 'Negotiation savings' = highest quote − awarded; 'Open value' uses PR estimates after a PO exists. | One absurd quote inflates savings to millions; open value disagrees with the PO list. | Savings vs estimate and vs second-lowest; PO total once a PO exists.
PW-24 | invoice 3-way match | low | Open |  | Rematch can flip an Approved invoice to Exception with no audit; approve does not refuse an already-approved invoice or a Draft/Closed PO; a ₱0 PO always gives Exception. | Approved + Exception shown side by side; cockpit counts it as failed. | Skip rematch for Approved (or audit it); guard approve.
PW-25 | help | medium | Partly v21.64/65 | Guide covers offers, local/import, one module, who may change; the 13-stage list itself still to write. | No in-app guide describes the 13-stage Workspace (CLAUDE.md requires one). | Help on the Workspace finds nothing on stages, who approves, match rules. | Add the guide entry; regenerate nexidoc.
PW-26 | audit trail | low | Fixed v21.65 | Audit rows carry an id. | Audit rows have no id so the sync treats the list as 'last writer wins'; who() falls back to 'user'. | Two devices append; the last pusher's list replaces the other's approval trail. | Give audit rows an id; refuse actions without a signed-in user.
PW-27 | sync | low | Fixed v21.65 | Sv() schedules the cloud sync on every write. | Writes never call hnxScheduleSync; rely on the 20 s dirty scan. | An approval seconds before closing the laptop never leaves the device. | Call hnxScheduleSync(k) in Sv().
PW-28 | tests | low | Fixed v21.53–65 | tests/payroll/purch-dept, purch-sourcing, purch-a2a, purch-onemodule. | No regression test covers any purchasing store or screen. | Any fix can silently regress. | tests/purchasing suite driving a PR through all stages.
QT-01 | RFQ outreach | high | Open |  | 'Send RFQ' says Nexi dispatches e-mail; it uses the user's own browser EmailJS keys if pasted, else just opens mailto: and logs 'sent'. No Nexi worker, no nexi@ mailbox, no server log. | Buyer ticks 4 suppliers → toast 'RFQ dispatched · 4 email'; the popup blocker allowed one mailto; 3 suppliers get nothing but the log shows 4 sent. | Real sender route (Gmail bridge under nexi@abapardes.com.ph with buyer in CC, supplier allow-list); until then log 'draft opened', not 'sent'.
QT-02 | RFQ outreach | high | Open |  | SMS 'send' opens an sms: link with the + of +63 URL-encoded; desktop PCs have no SMS handler; errors are swallowed; logged as sent. | Office PC: nothing opens, no error, RFQ Log says SMS sent. | Disable SMS on desktop or use a gateway route with a message id.
QT-03 | history | high | Open |  | hydroPro_acct_purch_history is on the auto-slim list (keep newest 250 rows once >120 KB, every 45 s) while the SOS importer writes one row per PO line; the importer then re-adds what was trimmed. | After a year of POs, 'total logged spend' and 'times bought' silently exclude older purchases and change between refreshes. | Remove the key from the slim rules or import incrementally into per-product×supplier aggregates.
QT-04 | history | medium | Open |  | Every SOS PO line is imported as a purchase: cancelled/voided POs included, ordered qty used instead of received. | A cancelled ₱180,000 PO shows as a real purchase and drives 'cheapest historically'. | Skip cancelled/void; use received qty (or /sos/item-receipts).
QT-05 | integration | medium | Open |  | The screen never shows which SOS account the single token is on (APAC per CLAUDE.md); rows carry no company tag. | Supply POs raised in APTI → import returns the other company's POs or nothing and the buyer cannot tell. | Show accountInfo.companyName in the banner; stamp company on rows; block import when unknown.
QT-06 | integration | medium | Open |  | Banner says 'QuickBooks ● cached' as a history source; nothing reads QuickBooks. | User expects QB bills in history; they never appear. | Remove the chip or implement a QB bills import.
QT-07 | supplier search | medium | Partly v21.54/65 | Curated web suggestions per item family; Alibaba / Made-in-China / 1688 search links for import items; no live API. | 'Add a supplier Nexi found on the web' — there is no web search, no API, no geocoding; the typed name is saved with source 'nexi-web'. | Manager asks for rockwool suppliers near Tarlac; only already-typed vendors appear; the buyer assumes a search ran. | Rename to 'Add a supplier manually' or implement a real search.
QT-08 | supplier search | medium | Open |  | Default base location is Manila (14.600, 120.984) labelled 'AteretPaz farm'. | Every distance and radius tier is measured from Manila; a Pampanga supplier 20 km away shows ~70 km. | Seed from Geographic Setup or show 'base not set' and disable radius filtering.
QT-09 | supplier search | low | Open |  | Coordinates captured with three prompt() dialogs keyed by lowercased name. | Rename a vendor → coordinates orphaned; comma decimals give NaN silently. | Small form keyed by vendor id.
QT-10 | supplier search | low | Open |  | Address fallback reads fields neither supplier master has: dead code. | None visible. | Add address to the vendor master or delete the branch.
QT-11 | supplier master | medium | Open |  | Two supplier masters reconciled by name only; some helpers read one, some both. | A supplier maintained in Inventory ▸ Master Data shows NEW on a comparison but EXISTING in outreach. | One merged helper; one canonical master with ids.
QT-12 | supplier master | medium | Open |  | Three writers append vendors with no duplicate check; the Vendors list has no edit. | 'Acme Hydro' added twice with a typo; only remedy is delete and re-add. | Upsert by normalised name; inline edit.
QT-13 | UI | medium | Open | acct_vendors links still target an unregistered view. | Links to switchView('acct_vendors') target a view registered in no module, so the header flips to PRODUCTION. | Click 'Add vendors in Vendors' → module header says Production. | Register acct_vendors under Accounting.
QT-14 | permissions | medium | Open |  | perm:null: every role can open the screen, delete comparisons/history, clear SOS history, rewrite the RFQ template and send RFQs in the company's name. | A greenhouse user finds the screen via search and clears all SOS history. | perm viewAccounting; destructive buttons behind a manage permission.
QT-15 | RFQ outreach | medium | Open |  | Banner promises ranking by reply rate; the sort never uses it. | A supplier that never answered stays above one that always quoted. | Add responseRate to the sort or drop the claim.
QT-16 | RFQ outreach | medium | Open |  | A quote mirrors into history only when 'quoted' is selected AFTER the price is typed; the UI order is the reverse; re-selecting duplicates. | Buyer marks 3 replies quoted then types prices → no quote rows; later re-selecting inserts duplicates. | Mirror on either change; upsert by id.
QT-17 | comparison | medium | Open |  | Quote rows (qty 0) sit in the same history store and are counted as purchases. | A supplier who merely quoted shows EXISTING '1× before · 0 units'. | Exclude source rfq-quote from purchase counts.
QT-18 | help | medium | Partly v21.65 | Guide rewritten for one module; SOS import / tiers still thin. | The Help guide has the two Purchasing screens' descriptions swapped and covers no SOS import, outreach or tiers. | Staff open the wrong screen. | Swap and extend the guide; regenerate nexidoc.
QT-19 | RFQ outreach | low | Open |  | Preview uses alert(). | 15-line RFQ in a native alert; disappears under 'prevent dialogs'. | In-app modal with copy.
QT-20 | comparison | low | Open |  | Validation via alert(). | Inconsistent with toasts on the same screen. | showToast + focus.
QT-21 | history | low | Open |  | Sync meta 'running' is written before the fetch and synced cloud-wide. | Second PC shows 'syncing…' for days after the first PC closed mid-import. | Keep running state in memory with a stale timeout; device-local key.
QT-22 | integration | low | Open |  | Import pulls every PO in the account on every click (up to 45×200), no cursor. | Tens of seconds per click; SOS throttling. | Pass from=<last sync> and store a high-water mark.
QT-23 | RFQ outreach | low | Open |  | EmailJS keys sync to every device; reply_to defaults to the supplier's own address. | Supplier hits Reply and mails themselves; the buyer never sees the quote. | Default reply-to to the requester / nexi@; keep keys device-local.
QT-24 | UI | low | Open |  | toISOString() on a missing sentAt throws and blanks the RFQ Log tab. | One bad row blanks the whole tab. | Guard the date.
QT-25 | comparison | low | Open |  | 'Ask Nexi for more quotes' passes no estimated value, so the radius tier defaults to the smallest. | A ₱500k comparison starts at 25 km. | Pass the estimated value.
QT-26 | UI | low | Open |  | Company signature hard-coded 'AteretPaz' in three places. | APAC RFQs go out signed AteretPaz. | Active company legal name.
QT-27 | UI | low | Open |  | Filter box rebuilds the whole view per keystroke and relies on the global caret-keeper. | Focus loss returns if that list is edited. | Filter the table body in place.
QT-28 | UI | low | Fixed v21.65 | One name: 🛒 Purchasing; Quick Tools = 🧰 Suppliers & tools tab. | Three different names for one screen; the Workspace is also titled 'Purchasing'. | Users cannot tell which purchasing screen they are on. | Use the nav label as the title.
IV-01 | worker /sos/create-po | critical | Open |  | The worker forwards the app's generic request body verbatim to SOS /purchaseorder with a literal 'TODO(verify): transform body': no vendor id, no item id, no lines[]. Same for adjustment/transfer/shipment. | Procurement approves a Purchase Request, warehouse presses 'Confirm issued → post to SOS'; SOS rejects it; the clerk is told to create the PO by hand and paste a reference. | Implement the SOS v2 mapping in the worker (vendor by name, item by SKU, lines[], date, comment=ref), idempotency on idemKey, clear errors back to the app.
IV-02 | confirmIssue for purchase | critical | Partly v21.65 | Purchase-type requests now flow to Purchasing via 📥 From Inventory; the Inventory-side stock-OUT booking is still there if someone confirms there. | A 'purchase' request for an app-only item is booked as a stock OUT and marked completed; no PO is ever raised. | Live test: Purchase Request for 20 Test Gloves (2 on hand) → Confirm issued → on hand 2 → −18, movement 'out', status completed. | Purchases never move stock: status 'ordered' / 'awaiting-sos'; stock rises only on receipt.
IV-03 | Purchase Engine → SOS | high | Partly v21.65 | Draft POs become Purchase Requests with one click; still no SOS push. | Draft POs are never sent anywhere: no /sos/create-po call, no hand-off to Accounting or Requests; 'Mark ordered' is a flag. | User generates a draft PO and marks it ordered; nothing is ordered in SOS; the cockpit counts it as a PO. | Convert 'Generate draft PO' into creating the one PO lifecycle (Purchasing module) that posts to SOS.
IV-04 | reorder list | high | Open |  | Ordered/draft local POs do not offset the reorder list; the same item is suggested again and duplicates are generated. | Live: Acme Supply generated twice → PO261004-001 and -003 with the same line; after Mark ordered the item is still listed. | Count local draft/ordered POs as on-order; warn on duplicate SKU.
IV-05 | approval chain | high | Open |  | Every chain level (Dept Manager, Division Head, VP/COO, Procurement, Accounting, HR) is approved by whoever has manageInventory; requester may approve own request. | Live: one admin approved all four levels in 4 clicks then confirmed the issue himself. | Approval matrix mapping levels to people/roles; no self-approval; exec override admin only.
IV-06 | Warehouse reorder | high | Open |  | Warehouse 'reorder' prefills a request without a type, so it defaults to Stock Issue and posts a NEGATIVE adjustment instead of a PO. | Warehouse clicks reorder on a low item, submits, approves, confirms: stock is deducted further. | Prefill type 'purchase' and supplier.
IV-07 | worker receipt mapping | high | Open |  | /sos/create-receipt maps to '/receivinginventory' (marked VERIFY) while the read route uses the real entity 'itemreceipt'. | Every Accounting GRN receipt will 404 in SOS once the worker is reachable. | Map to /itemreceipt with vendor, lines and PO reference; test in sandbox.
IV-08 | retry / duplicates | medium | Open |  | Retry on a completed request regresses it to awaiting-sos on failure and creates a second SOS document on success. | Live: completed with PO-MANUAL-1 → Retry → status back to awaiting-sos. | Restore status on failure; worker dedupe on idemKey.
IV-09 | offline message | medium | Open |  | The real error text is wiped by the immediate re-render; no 'cloud unreachable' detection. | Any worker outage looks like 'not configured'. | Store sosError on the record and render it.
IV-10 | numbering | medium | Partly v21.65 | PR numbers fixed; Inventory request numbers unchanged. | Request numbers = today's local count+1; PO refs = array length+1. | Two devices raise IR1004-26-001; deleting a draft then generating reuses an existing ref. | max existing +1 or cloud counter.
IV-11 | completion semantics | medium | Open |  | Pasting any text as SOS reference marks a purchase 'completed'; nothing links it to a receipt; the request leaves the open queue before goods arrive. | Procurement pastes a PO number; the warehouse has no signal the goods are expected. | 'ordered' state; close only on receipt.
IV-12 | open-PO offset | low | Open |  | After one failed SOS fetch the offset is never retried for the session. | Worker briefly down at first render → whole session without on-order offset. | Retry after N minutes / Refresh.
IV-13 | data typing | low | Open |  | qty and unitCost stored as strings. | Any arithmetic without num() concatenates. | Coerce in submit().
IV-14 | account | medium | Open |  | One SOS token for all writes; a PO would land in whichever account the worker is on (APAC) with no selector. | An APTI purchase posts into APAC. | Company field on the request; refuse writes that do not match the token's account.
IV-15 | help | low | Open |  | Guide says a Purchase Request moves nothing until received and the Engine produces POs ready for sign-off; neither matches the code. | Users trust the guide. | Update after IV-02/03.
LV-01 | UI | high | Fixed v21.53 | Tab bar never folds. | The Workspace's 9-tab bar is swallowed by the global 'All tools' collapser 2–5 s after render: the 8 workflow tabs vanish into a dropdown under 'More'. | Open Purchasing, wait a few seconds, try to click RFQs or Invoices: the tabs are gone (live: click timed out, element hidden). | Exclude the purchasing nav from the collapser.
LV-02 | UI | high | Open |  | The Supplier 360° modal's ✕ sits under the fixed 'Cloud worker unreachable' banner and there is no Escape / backdrop close, so the whole screen is blocked once it opens. | Click any supplier name at Sourcing while a cloud banner shows: nothing on the screen can be clicked any more (live: run stopped here). | Backdrop click + Escape to close; modal above banners; same for the outreach and location modals.
LV-03 | payment | high | Open |  | No payment stage exists: the chain advertised as PR → … → payment ends at invoice Approved. | Approve an invoice and look for Pay / Mark paid: nothing. | Paid state with date, reference, method; shown in cockpit and analytics.
LV-04 | permissions | high | Fixed v22.28 | The requester can no longer approve, award or issue their own PR; approvers are Eyal / Dr Amy, not the accounting role (test purch-chain-v2228). | Live: the admin created, submitted, AI-accepted and approved his own PR with no warning; the whole accounting role has managePayroll, so every accountant is a purchasing approver. | Jinky creates a PR and approves it herself. | Refuse approve/award/issue by the requester; dedicated approver permission.
LV-05 | UI | medium | Open |  | Approve, Reviewed, Verified and Run AI advance the stage silently (no toast); Submit, Accept and Override do. | Click Approve at Department Approval: nothing visibly happens except a chip change. | Toast on every stage change.
LV-06 | UI | medium | Open |  | Invoices tab shows an empty PO select on a fresh install; the only guard is 'PO, invoice number and amount are required.' | Fresh install → Invoices → Log & match → cryptic alert. | Show 'Issue a purchase order first' and disable the button.
LV-07 | sourcing | medium | Fixed v21.54 | Inline ➕ Add supplier with category. | With an empty vendor master, Sourcing shows 'Nexi found 0 candidates' and offers no way to add a supplier; the only exit is 'Pick at least one supplier.' | First procurement on a device with no vendors is a dead end. | 'Add supplier' inline and a link to the supplier master.
LV-08 | cockpit | medium | Open |  | All three Accounting cockpit boxes (Purchase requests, POs & receiving, Supplier invoices) open the same Mission Control tab. | Click 'Supplier invoices' on the cockpit → lands on Mission Control, numbers do not match. | Open the matching tab (pos / invs).
LV-09 | AI gate | medium | Open |  | 'AI Validation' is a rules check (stock hint, history average, duplicate PR); with no data it always says 'Purchase required. 88%'. | Every first PR shows a confident percentage that means nothing. | Label it 'Rules check' or route through the Nexi brain worker.
LV-10 | dates | low | Open |  | Dates use UTC toISOString, not hnxLocalToday(); after 16:00 Manila every date is one day early. | GRN recorded at 19:00 PHT gets yesterday's date. | Use hnxLocalToday().
LV-11 | 3-way match | low | Open |  | Scaled, rounded line prices no longer sum to the PO total; rounding alone can push a correct invoice into 'Waiting GRN'. | Estimate ₱2,500, quote ₱2,599.99, 3 lines → mismatch. | Match by quantity, or put the rounding remainder on the last line.
LV-12 | duplication | medium | Partly v21.65 | Quick Tools folded into the module; its own comparison award still does not create a PR. | Quick Tools has its own comparisons / outreach / history with its own 'award'; an awarded comparison never creates a PR or PO; Workspace RFQ sends land in the outreach log with qty 0. | Award a comparison in Quick Tools, then look at Purchase Orders: nothing. | 'Convert to request' on an awarded comparison; one outreach record shape.
LV-13 | UI | low | Open |  | The red 'Cloud worker unreachable' banner stays pinned over every screen and overlaps modals. | Any offline minute makes modals unclosable (LV-02). | Collapse to a status chip after first dismissal; keep it below modals.