## Summary
ABA PARDES AGRITECH CORP. — CONTAINER 1 & 2 INVENTORY AUDIT
2026-08-11 · Myxl container packing lists (PDF) vs team allocation file 08.09.2026 · matched item-by-item by name & order
Container 1 — items on the manufacturer list | 247
Container 2 — items on the manufacturer list | 99
Rows with MISSING / unaccounted quantity | 171
Container 1 — unaccounted units total | 10490
Container 2 — unaccounted units total | 926
Rows with NO DATA AT ALL in the team file (names copied, nothing tracked) | 158
Lines completely absent from the team file | 1
Rows with a book gap (received ≠ transfers + ending) | 49
Rows where team quantity differs from the container list | 3
• READ ME: every item of both manufacturer packing lists appears once on its container sheet, matched to the team's allocation row (Project 15 / Project 12 / warehouses / returns / ending balance).
• RED row = line completely absent from the team file. ORANGE row = the team copied the item name but recorded NOTHING (no received, no location) — these need a physical recount, they are the biggest part of the gap.
• MISSING column = container quantity minus everything the team file accounts for (received, or transfers+warehouse stock+ending). This is the number to hunt physically.
• “Book gap” = the team's own numbers do not close (received ≠ projects + ending − returns) — a bookkeeping error inside their file, listed in the Status column.
• Warehouse columns are stock locations (not consumption); Projects 15/12 are installations. The audit counts BOTH as accounted-for.
• The team workbook's older sheets (“Container 1” unnumbered) were superseded by “Copy of Container 1/2” and are not part of this audit.

## Container 1
No | Section | Item (container list) | Unit | Container Qty | Team Listed | Received | → Project 15 | → Project 12 | Warehouse C | Warehouse E | Doc's WH | Warehouse | Return | Ending Bal | MISSING / UNACCOUNTED | Status / Audit note
1 | Greenhouse Main Structure Pipe | Reinforcement bar φ12 | M | 1100 | 1100 | [8 empty] | 1100 |  | OK · RECEIVED not recorded
2 | Greenhouse Main Structure Pipe | Ring beam stirrup φ6 | Pcs | 1150 | 1150 | 1150 | 441 | [5 empty] | 7 | 716 |  | OK
3 | Greenhouse Main Structure Pipe | Reinforcement bar φ8 | M | 3200 | 3200 | 3200 | 700 | [6 empty] | 2500 |  | OK
4 | Greenhouse Main Structure Pipe | Gutter stirrup φ6 | Pcs | 1200 | 1200 | 1200 | [7 empty] | 1200 |  | OK
5 | Greenhouse Main Structure Pipe | Steel pin 25 | Pcs | 4 | 4 | 4 | [7 empty] | 4 |  | OK
6 | Greenhouse Main Structure Pipe | Flat iron S4*40 | M | 180 | 180 | 180 | 376 | [5 empty] | 6 | 6 | -196 | EXCESS 196 · book gap: received 180 vs accounted 376
7 | Greenhouse Main Structure Pipe | Point foundation | Pcs | 440 | 440 | [8 empty] | 0 | 440 | NO DATA in team file — physically recount
8 | Greenhouse Main Structure Pipe | Corner column 120*120*3 4 | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
9 | Greenhouse Main Structure Pipe | Main column 120*120*3 4 | Pcs | 30 | 30 | [8 empty] | 0 | 30 | NO DATA in team file — physically recount
10 | Greenhouse Main Structure Pipe | End column 120*60*3 6 | Pcs | 12 | 12 | 12 | [7 empty] | 12 |  | OK
11 | Greenhouse Main Structure Pipe | End column 120*60*3 5.38 | Pcs | 12 | 12 | [8 empty] | 0 | 12 | NO DATA in team file — physically recount
12 | Greenhouse Main Structure Pipe | Side column 120*60*3 4 | Pcs | 26 | 26 | [8 empty] | 0 | 26 | NO DATA in team file — physically recount
13 | Greenhouse Main Structure Pipe | Side secondary column 120*60*3 4 | Pcs | 52 | 52 | [8 empty] | 0 | 52 | NO DATA in team file — physically recount
14 | Greenhouse Main Structure Pipe | Door beam 120*60*3 1.94 | Pcs | 2 | 2 | 2 | [7 empty] | 2 |  | OK
15 | Greenhouse Main Structure Pipe | Door column 120*60*3 2 | Pcs | 4 | 4 | 4 | [7 empty] | 4 |  | OK
16 | Greenhouse Main Structure Pipe | Gutter k500-2 4 | Pcs | 24 | 24 | 24 | [7 empty] | 24 |  | OK
17 | Greenhouse Main Structure Pipe | Gutter k500-2 2 | Pcs | 4 | 4 | 4 | [7 empty] | 4 |  | OK
18 | Greenhouse Main Structure Pipe | End beam/inner beam 50*30*2 9.88 | Pcs | 45 | 45 | 45 | [7 empty] | 45 |  | OK
19 | Greenhouse Main Structure Pipe | End girt beam K50*30*1.5 8 | Pcs | 24 | 24 | [8 empty] | 0 | 24 | NO DATA in team file — physically recount
20 | Greenhouse Main Structure Pipe | End girt beam K50*30*1.5 2 | Pcs | 24 | 24 | [8 empty] | 0 | 24 | NO DATA in team file — physically recount
21 | Greenhouse Main Structure Pipe | End girt beam K50*30*1.5 6 | Pcs | 6 | 6 | [8 empty] | 0 | 6 | NO DATA in team file — physically recount
22 | Greenhouse Main Structure Pipe | Fan column K50*30*1.5 1.45 | Pcs | 30 | 30 | 30 |  | 30 | [5 empty] | 30 | -30 | EXCESS 30 · book gap: received 30 vs accounted 60
23 | Greenhouse Main Structure Pipe | Middle arch 1 51*1.5 5.5 | Pcs | 45 | 45 | [8 empty] | 0 | 45 | NO DATA in team file — physically recount
24 | Greenhouse Main Structure Pipe | Middle arch 2 51*1.5 5.5 | Pcs | 45 | 45 | 45 | [7 empty] | 45 |  | OK · matched to team row "Middle Arc 2 51x1.5" — verify
25 | Greenhouse Main Structure Pipe | Middle arch 3 48*2 5.54 | Pcs | 78 | 78 | [8 empty] | 0 | 78 | NO DATA in team file — physically recount
26 | Greenhouse Main Structure Pipe | Middle arch 4 48*2 5.54 | Pcs | 78 | 78 | 78 | [7 empty] | 78 |  | OK · matched to team row "Middle Arc 4 48x2" — verify
27 | Greenhouse Main Structure Pipe | Side arch 1 51*1.5 4.9 | Pcs | 30 | 30 | [8 empty] | 0 | 30 | NO DATA in team file — physically recount
28 | Greenhouse Main Structure Pipe | Side arch 2 48*2 5 | Pcs | 52 | 52 | [8 empty] | 0 | 52 | NO DATA in team file — physically recount
29 | Greenhouse Main Structure Pipe | Wind brace 40*2 5.5 | Pcs | 12 | 12 | 12 | [7 empty] | 12 |  | OK
30 | Greenhouse Main Structure Pipe | Roof beam 1 40*2 5.5 | Pcs | 81 | 81 | [8 empty] | 0 | 81 | NO DATA in team file — physically recount
31 | Greenhouse Main Structure Pipe | Roof beam 2 40*2 3.3 | Pcs | 9 | 9 | 9 |  | 9 | [5 empty] | 9 | -9 | EXCESS 9 · book gap: received 9 vs accounted 18
32 | Greenhouse Main Structure Pipe | Inner support beam 1 32*2 2.31 | Pcs | 39 | 39 | [8 empty] | 0 | 39 | NO DATA in team file — physically recount
33 | Greenhouse Main Structure Pipe | Inner support beam 2 32*2 3.09 | Pcs | 78 | 78 |  |  | 56 | [5 empty] | 0 | 22 | MISSING 22 · RECEIVED not recorded
34 | Greenhouse Main Structure Pipe | Inner support beam 3 32*2 1.81 | Pcs | 78 | 78 | 80 |  | 80 | [5 empty] | 80 | -82 | EXCESS 82 · book gap: received 80 vs accounted 160
35 | Greenhouse Main Structure Pipe | Column brace 32*2 5 | Pcs | 16 | 16 | 16 | [7 empty] | 16 |  | OK
36 | Greenhouse Main Structure Pipe | Anti-wind support beam 32*32 4 | Pcs | 82 | 82 | [8 empty] | 0 | 82 | NO DATA in team file — physically recount
37 | Greenhouse Accessories | Anchor bolt M16*320 | Pcs | 792 | 792 | 582 | 467 | [6 empty] | 130 | 195 | MISSING 195 · book gap: received 582 vs accounted 597
38 | Greenhouse Accessories | Foundation plate 150*150 | Pcs | 207 | 207 | 153 | 113 | [6 empty] | 46 | 48 | MISSING 48 · book gap: received 153 vs accounted 159
39 | Greenhouse Accessories | Gutter bracket 80*40, 80 | Pcs | 83 | 83 | 83 |  |  |  | 22 |  |  |  | 83 |  | OK
40 | Greenhouse Accessories | Gutter connector k500 | Pcs | 31 | 31 | 31 |  |  |  | 20 |  |  |  | 31 |  | OK
41 | Greenhouse Accessories | End beam clamp 120*120 double head | Pcs | 5 | 5 | 5 | [7 empty] | 5 |  | OK
42 | Greenhouse Accessories | End beam clamp 120*120 single head | Pcs | 5 | 5 | 5 | [7 empty] | 5 |  | OK
43 | Greenhouse Accessories | Fixing clamp 50*30 | Pcs | 26 | 26 | [8 empty] | 0 | 26 | NO DATA in team file — physically recount
44 | Greenhouse Accessories | Girt beam connector K50*30 | Pcs | 30 | 30 | [8 empty] | 0 | 30 | NO DATA in team file — physically recount
45 | Greenhouse Accessories | Girt beam clamp 120*120 double head | Pcs | 18 | 18 |  |  |  |  | 18 |  |  |  | 0 |  | OK · RECEIVED not recorded
46 | Greenhouse Accessories | Girt beam clamp 120*120 single head | Pcs | 18 | 18 |  |  |  |  | 18 |  |  |  | 0 |  | OK · RECEIVED not recorded
47 | Greenhouse Accessories | Girt beam clamp 60*120 double head | Pcs | 112 | 112 | [8 empty] | 0 | 112 | NO DATA in team file — physically recount
48 | Greenhouse Accessories | Girt beam clamp 60*120 double head | Pcs | 14 | 14 | [8 empty] | 0 | 14 | NO DATA in team file — physically recount
49 | Greenhouse Accessories | End column clamp (120*60)*(51) | Pcs | 24 | 24 | 24 | [7 empty] | 24 |  | OK
50 | Greenhouse Accessories | Top connect clamp 48*40,short | Pcs | 53 | 53 | 126 |  |  |  | 126 |  |  |  | 126 | -73 | EXCESS 73
51 | Greenhouse Accessories | Top connect clamp 48*40,long | Pcs | 106 | 106 | 254 |  |  |  | 254 |  |  |  | 254 | -148 | EXCESS 148
52 | Greenhouse Accessories | Plastic cover 40 | Pcs | 20 | 20 | 20 |  |  |  | 20 |  |  |  | 20 |  | OK
53 | Greenhouse Accessories | End clamp 51 | Pcs | 259 | 259 |  | 30 |  |  | 283 |  |  |  | 0 | -54 | EXCESS 54 · RECEIVED not recorded
54 | Greenhouse Accessories | End clamp 48 | Pcs | 110 | 110 | 110 |  |  |  | 67 |  |  |  | 110 |  | OK
55 | Greenhouse Accessories | End clamp 30*50 | Pcs | 121 | 121 | [8 empty] | 0 | 121 | NO DATA in team file — physically recount
56 | Greenhouse Accessories | Side column - inner beam connector | Pcs | 28 | 28 | [8 empty] | 0 | 28 | NO DATA in team file — physically recount
57 | Greenhouse Accessories | Middle column- inner beam connector | Pcs | 28 | 28 | [8 empty] | 0 | 28 | NO DATA in team file — physically recount
58 | Greenhouse Accessories | End clamp 60*120 | Pcs | 28 | 28 | 28 |  |  |  | 28 |  |  |  | 28 |  | OK
59 | Greenhouse Accessories | End clamp 120*120 | Pcs | 4 | 4 | 4 |  |  |  | 4 |  |  |  | 4 |  | OK
60 | Greenhouse Accessories | Double head clamp 60*120 | Pcs | 16 | 16 | [8 empty] | 0 | 16 | NO DATA in team file — physically recount
61 | Greenhouse Accessories | Double head clamp 120*120 | Pcs | 48 | 48 | [8 empty] | 0 | 48 | NO DATA in team file — physically recount
62 | Greenhouse Accessories | U-bolt 48*40 | Pcs | 12 | 12 | 12 |  |  |  | 12 |  |  |  | 12 |  | OK
63 | Greenhouse Accessories | U-bolt 51 | Pcs | 64 | 64 | 64 |  |  |  | 64 |  |  |  | 64 |  | OK
64 | Greenhouse Accessories | U-bolt 48 | Pcs | 108 | 108 | 108 | 50 |  |  | 108 |  |  |  | 58 | -50 | EXCESS 50 · book gap: received 108 vs accounted 158
65 | Greenhouse Accessories | Corner connector 70*80*95 | Pcs | 104 | 104 | [8 empty] | 0 | 104 | NO DATA in team file — physically recount
66 | Greenhouse Accessories | Turnbuckle M10 | Pcs | 16 | 16 | 16 |  |  |  | 16 |  |  |  | 16 |  | OK
67 | Greenhouse Accessories | Gutter sealing tape | M | 150 | 150 |  |  |  |  | 150 |  |  |  | 0 |  | OK · RECEIVED not recorded
68 | Greenhouse Accessories | Downspout K500 | Pcs | 4 | 4 | 4 | [7 empty] | 4 |  | OK
69 | Ventilation System | Roll-up device 230V 60HZ 100W | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
70 | Ventilation System | Roll-up device connector 36 | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
71 | Ventilation System | Climber | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
72 | Ventilation System | Climbing pole 25*2 4.5 | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
73 | Ventilation System | Insert pipe 25*2 4.5 | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
74 | Ventilation System | Rolling pipe P36-1 6 | Pcs | 35 | 35 | [8 empty] | 0 | 35 | NO DATA in team file — physically recount
75 | Ventilation System | Rolling pipe connector 36 | Pcs | 40 | 40 |  |  |  |  | 80 |  |  |  | 0 | -40 | EXCESS 40 · RECEIVED not recorded
76 | Ventilation System | Double lock channel S1.2 with coating | M | 420 | 420 | [8 empty] | 0 | 420 | NO DATA in team file — physically recount
77 | Ventilation System | Double lock channel connector | Pcs | 70 | 70 | 70 | [7 empty] | 70 |  | OK
78 | Ventilation System | Wiggle wire | M | 3656 | 3656 | 3656 | [7 empty] | 3656 |  | OK
79 | Ventilation System | Self-drilling screw M5*19 | Pcs | 7700 | 7700 | 7700 |  |  |  | 7700 |  |  |  | 7700 |  | OK
80 | Ventilation System | Fixing film rope White | M | 2400 | 2400 | [8 empty] | 0 | 2400 | NO DATA in team file — physically recount
81 | Ventilation System | Film hook | Pcs | 300 | 300 | [8 empty] | 0 | 300 | NO DATA in team file — physically recount
82 | Ventilation System | Small L-bar L30*30 | Pcs | 120 | 120 | 498 |  |  |  | 160 |  |  |  | 498 | -378 | EXCESS 378
83 | Ventilation System | Hinge | Pcs | 32 | 32 |  |  |  |  | 32 |  |  |  | 0 |  | OK · RECEIVED not recorded
84 | Ventilation System | knob | Pcs | 10 | 10 | 10 |  |  |  | 10 |  |  |  | 10 |  | OK
85 | Ventilation System | Window frame 1 5.6 | Pcs | 2 | 2 | 2 | [7 empty] | 2 |  | OK
86 | Ventilation System | Window frame 2 6.3 | Pcs | 2 | 2 | 2 | [7 empty] | 2 |  | OK
87 | Ventilation System | Square pipe K50*30*1.5 1.7 | Pcs | 4 | 4 |  |  | 4 | [5 empty] | 0 |  | OK · RECEIVED not recorded
88 | Drainage System | Downspout φ110 4 | Pcs | 4 | 4 | 4 | [7 empty] | 4 |  | OK · matched to team row "Dowspout 110" — verify
89 | Drainage System | Pipe clamp φ110 | Pcs | 8 | 8 | 8 |  |  |  | 8 |  |  |  | 8 |  | OK
90 | Drainage System | Elbow φ110 | Pcs | 4 | 4 | 4 |  |  |  | 4 |  |  |  | 4 |  | OK
91 | Drainage System | Pipe clamp connector φ20 | M | 2 | 2 |  |  |  |  | 15 |  |  |  | 0 | -13 | EXCESS 13 · RECEIVED not recorded
92 | Drainage System | PVC glue | Pcs | 1 | 1 | 1 |  |  |  | 1 |  |  |  | 1 |  | OK
93 | Cooling System | Cooling pad sealing edge C1*60*120*60 1.91 | Pcs | 12 | 12 | 12 | [7 empty] | 12 |  | OK
94 | Cooling System | Cooling pad sealing edge C1*60*120*60 1.94 | Pcs | 18 | 18 | 18 | [7 empty] | 18 |  | OK
95 | Cooling System | Cooling pad sealing edge C1*60*120*60 1.75 | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
96 | Cooling System | Corner connector | Pcs | 290 | 290 | [8 empty] | 0 | 290 | NO DATA in team file — physically recount
97 | Cooling System | Cooling pad bracket | Pcs | 40 | 40 | 40 |  |  |  | 40 |  |  |  | 40 |  | OK
98 | Roof Fan System | Roof fan frame | Pcs | 36 | 36 | 36 | [7 empty] | 36 |  | OK
99 | Shading System | Inner longitudinal beam 40*1.5 5 | Pcs | 6 | 6 | [8 empty] | 0 | 6 | NO DATA in team file — physically recount
100 | Shading System | Inner longitudinal beam 40*1.5 3.7 | Pcs | 12 | 12 |  |  | 12 | [5 empty] | 0 |  | OK · RECEIVED not recorded
101 | Shading System | Double head clamp 32 | Pcs | 36 | 36 | [8 empty] | 0 | 36 | NO DATA in team file — physically recount
102 | Shading System | Motor 0.75kw,230V,60HZ | Pcs | 1 | 1 | 1 | [7 empty] | 1 |  | OK
103 | Shading System | Motor seat | Pcs | 1 | 1 |  |  |  |  | 1 |  |  |  | 0 |  | OK · RECEIVED not recorded
104 | Shading System | Motor seat bolt M10*140 | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
105 | Shading System | Gear seat | Pcs | 9 | 9 | [8 empty] | 0 | 9 | NO DATA in team file — physically recount
106 | Shading System | Gear seat bolt U30*50 | Pcs | 18 | 18 | [8 empty] | 0 | 18 | NO DATA in team file — physically recount
107 | Shading System | Shaft pipe 33.4*2.75 3.57 | Pcs | 7 | 7 | [8 empty] | 0 | 7 | NO DATA in team file — physically recount
108 | Shading System | Shaft pipe 33.4*2.75 0.97 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
109 | Shading System | Shaft pipe 33.4*2.75 2.34 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
110 | Shading System | Rack 2.75 3.95 | Pcs | 9 | 9 | 9 |  | 9 | [5 empty] | 9 | -9 | EXCESS 9 · book gap: received 9 vs accounted 18
111 | Shading System | Rack connector 32 | Pcs | 18 | 18 | [8 empty] | 0 | 18 | NO DATA in team file — physically recount
112 | Shading System | Push-pull pulley | Pcs | 90 | 90 |  |  |  |  | 91 |  |  |  | 0 | -1 | EXCESS 1 · RECEIVED not recorded
113 | Shading System | Push-pull pipe | Pcs | 90 | 90 |  |  | 58 | [5 empty] | 0 | 32 | MISSING 32 · RECEIVED not recorded
114 | Shading System | Self-tapping screw stainless steel M5.5*19 | Pcs | 570 | 570 | [8 empty] | 0 | 570 | NO DATA in team file — physically recount
115 | Shading System | Push net rod ZM33-D 5.8 | Pcs | 60 | 60 | [8 empty] | 0 | 60 | NO DATA in team file — physically recount
116 | Shading System | Push net rod ZM33-D 1 | Pcs | 12 | 12 | [8 empty] | 0 | 12 | NO DATA in team file — physically recount
117 | Shading System | Push net rod connector | Pcs | 120 | 120 |  |  |  |  | 120 |  |  |  | 0 |  | OK · RECEIVED not recorded
118 | Shading System | Push net rod clamp 32 | Pcs | 108 | 108 | [8 empty] | 0 | 108 | NO DATA in team file — physically recount
119 | Shading System | Curtain support wire White | M | 7000 | 7000 |  |  |  |  | 7000 |  |  |  | 0 |  | OK · RECEIVED not recorded
120 | Shading System | Presser | Pcs | 1000 | 1000 | 1000 |  |  |  | 1000 |  |  |  | 1000 |  | OK
121 | Shading System | Small net clip grey | Pcs | 500 | 500 | 500 |  |  |  | 500 |  |  |  | 500 |  | OK
122 | Shading System | Counterweight | Pcs | 156 | 156 |  |  |  |  | 156 |  |  |  | 0 |  | OK · RECEIVED not recorded
123 | Buffer Room | Main column 1 120*60*3 2.2 | Pcs | 4 | 4 | 4 | [7 empty] | 4 |  | OK
124 | Buffer Room | Main column 2 120*60*3 2.4 | Pcs | 2 | 2 | 2 | [7 empty] | 2 |  | OK
125 | Buffer Room | Roof truss 120*60*3 2.94 | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
126 | Buffer Room | Roof beam 50*30*2 1.94 | Pcs | 9 | 33 | [8 empty] | 0 | 9 | NO DATA in team file — physically recount · team qty differs
127 | Buffer Room | Buffer connection plate 1 | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
128 | Buffer Room | Buffer connection plate 2 | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
129 | Buffer Room | PC sheet 10mm 3 1.99 | Pcs | 3 | 3 |  |  | 4 | [5 empty] | 0 | -1 | EXCESS 1 · RECEIVED not recorded
130 | Buffer Room | Upper panel connector YG-JP-A08 3 | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
131 | Buffer Room | Lower panel connector YG-JP-A09 3 | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
132 | Buffer Room | Bottom part JP-J06 6 | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
133 | Buffer Room | PC sheet sealing strip JP-J02 | M | 15 | 15 | [8 empty] | 0 | 15 | NO DATA in team file — physically recount
134 | Buffer Room | Aluminum washer | Pcs | 20 | 20 | 20 |  |  |  | 20 |  |  |  | 20 |  | OK
135 | Buffer Room | Rubber washer | Pcs | 20 | 20 | 20 |  |  |  | 20 |  |  |  | 20 |  | OK
136 | Buffer Room | Self-drilling screw Square head M5.5*38 | Pcs | 300 | 300 | [8 empty] | 0 | 300 | NO DATA in team file — physically recount
137 | Buffer Room | Aluminum foil tape | M | 12 | 12 | [8 empty] | 0 | 12 | NO DATA in team file — physically recount
138 | Buffer Room | Black structural adhesive | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
139 | Buffer Room | Roof truss edge sealing sheet L1*50*50 4 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
140 | Buffer Room | Roof truss edge sealing sheet L1*50*50 2 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
141 | Buffer Room | Roof truss edge sealing sheet L1*50*50 3.05 | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
142 | Buffer Room | Roof truss edge sealing sheet L1*75*50 4 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
143 | Buffer Room | Roof truss edge sealing sheet L1*75*50 2 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
144 | NFT Table | Table leg | Pcs | 102 | 102 | 306 | [7 empty] | 306 | -204 | EXCESS 204
145 | NFT Table | Table bracket | Pcs | 66 | 66 | 86 | [7 empty] | 86 | -20 | EXCESS 20
146 | NFT Table | Expansion bolt M8*60 | Pcs | 648 | 648 |  |  |  |  | 651 |  |  |  | 0 | -3 | EXCESS 3 · RECEIVED not recorded
147 | NFT Table | Adjusting bolt 40*20 | Pcs | 306 | 306 |  |  |  |  | 248 |  |  |  | 0 | 58 | MISSING 58 · RECEIVED not recorded
148 | NFT Table | Horizontal and vertical rod connector | Pcs | 408 | 408 | [8 empty] | 0 | 408 | NO DATA in team file — physically recount
149 | NFT Table | Leg brace 25*2 3 | Pcs | 24 | 24 |  |  | 24 | [5 empty] | 0 |  | OK · RECEIVED not recorded
150 | NFT Table | Double head clamp 20*40 | Pcs | 48 | 48 |  |  |  |  | 30 |  |  |  | 0 | 18 | MISSING 18 · RECEIVED not recorded
151 | NFT Table | Longitudinal tube 1 42*2 5.5 | Pcs | 240 | 240 | [8 empty] | 0 | 240 | NO DATA in team file — physically recount
152 | NFT Table | Longitudinal tube 2 42*2 4.72 | Pcs | 30 | 30 | [8 empty] | 0 | 30 | NO DATA in team file — physically recount
153 | NFT Table | Longitudinal tube 3 25*2 6 | Pcs | 126 | 126 | 127 | [7 empty] | 127 | -1 | EXCESS 1 · matched to team row "Longhitudinal Tube 3 25x2" — verify
154 | NFT Table | Longitudinal tube 4 25*2 6.63 | Pcs | 18 | 18 | 18 | [7 empty] | 18 |  | OK · matched to team row "Longhitudinal Tube 4 25x2" — verify
155 | NFT Table | Fixing clamp 42 | Pcs | 530 | 530 |  |  |  |  | 634 |  |  |  | 0 | -104 | EXCESS 104 · RECEIVED not recorded
156 | NFT Table | Fixing clamp 25 | Pcs | 334 | 334 | 334 | [7 empty] | 334 |  | OK
157 | NFT Table | Hook | Pcs | 400 | 400 | 1800 | [7 empty] | 1800 | -1400 | EXCESS 1400
158 | Irrigation Room | Main column 120*60*3 5.15 | Pcs | 5 | 5 |  |  | 5 | [5 empty] | 0 |  | OK · RECEIVED not recorded
159 | Irrigation Room | Main column 120*60*3 4 | Pcs | 5 | 5 |  |  | 5 | [5 empty] | 0 |  | OK · RECEIVED not recorded
160 | Irrigation Room | Main column 120*60*3 4.575 | Pcs | 2 | 2 |  |  | 2 | [5 empty] | 0 |  | OK · RECEIVED not recorded
161 | Irrigation Room | End roof truss 120*60*3 7 | Pcs | 2 | 2 | 2 |  | 2 | [5 empty] | 2 | -2 | EXCESS 2 · book gap: received 2 vs accounted 4
162 | Irrigation Room | Middle roof truss 120*60*3 7 | Pcs | 3 | 3 | 3 |  | 3 | [5 empty] | 3 | -3 | EXCESS 3 · book gap: received 3 vs accounted 6
163 | Irrigation Room | Double corner connector | Pcs | 96 | 96 | [8 empty] | 0 | 96 | NO DATA in team file — physically recount
164 | Irrigation Room | Roof truss connector | Pcs | 12 | 12 |  |  |  |  | 12 |  |  |  | 0 |  | OK · RECEIVED not recorded
165 | Irrigation Room | Self-drilling screw Square head M5.5*25 | Pcs | 1000 | 1000 | [8 empty] | 0 | 1000 | NO DATA in team file — physically recount
166 | Irrigation Room | Fertilizer tank platform 50*30*2 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
167 | Irrigation Room | corrugated tile 0.6 7 0.9 | Pcs | 10 | 10 | 10 |  | 10 | [5 empty] | 10 | -10 | EXCESS 10 · book gap: received 10 vs accounted 20
168 | Irrigation Room | Door 50*30 2 1.16 | Pcs | 2 | 2 | 2 |  |  |  | 2 |  |  |  | 2 |  | OK
169 | Irrigation Room | Hinge | Pcs | 4 | 4 | 4 |  |  |  | 4 |  |  |  | 4 |  | OK
170 | Irrigation Room | Steel wire mesh 2 1 | Pcs | 54 | 54 | 50 |  |  |  | 50 |  |  |  | 50 | 4 | MISSING 4
171 | Irrigation Room | Presser φ3 | Pcs | 800 | 800 | [8 empty] | 0 | 800 | NO DATA in team file — physically recount
172 | Irrigation Room | Arch connector 51 | Pcs | 80 | 80 | [8 empty] | 0 | 80 | NO DATA in team file — physically recount
173 | Irrigation Room | T-clamp 32*32 | Pcs | 170 | 170 | [8 empty] | 0 | 170 | NO DATA in team file — physically recount
174 | Irrigation Room | T-clamp 20*25 | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
175 | Irrigation Room | Small L-bar L30*30 | Pcs | 336 | 336 | 776 |  |  |  | 773 |  |  |  | 776 | -440 | EXCESS 440
176 | Irrigation Room | End clamp 48 | Pcs | 150 | 150 | 150 |  |  |  | 67 |  |  |  | 150 |  | OK
177 | Boom System | Main frame | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
178 | Boom System | Transfer cart main frame | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
179 | Boom System | Rail fixing support frame | Pcs | 3 | 3 | 3 | [7 empty] | 3 |  | OK
180 | Boom System | Transfer rail fixing support frame | Pcs | 6 | 6 | [8 empty] | 0 | 6 | NO DATA in team file — physically recount
181 | Boom System | Main support hanging bracket 1 | Pcs | 36 | 36 | [8 empty] | 0 | 36 | NO DATA in team file — physically recount
182 | Boom System | Main support hanging bracket 2 | Pcs | 7 | 7 | [8 empty] | 0 | 7 | NO DATA in team file — physically recount
183 | Boom System | Auxiliary support hanging bracket 1 | Pcs | 36 | 36 | [8 empty] | 0 | 36 | NO DATA in team file — physically recount
184 | Boom System | Auxiliary support hanging bracket 2 | Pcs | 7 | 7 | [8 empty] | 0 | 7 | NO DATA in team file — physically recount
185 | Boom System | Main rail hanging rod 20*1.5 | Pcs | 72 | 72 | [8 empty] | 0 | 72 | NO DATA in team file — physically recount
186 | Boom System | Transfer rail hanging rod 20*1.5 | Pcs | 14 | 14 | [8 empty] | 0 | 14 | NO DATA in team file — physically recount
187 | Boom System | Rail fixing frame hanging rod 20*1.5 | Pcs | 12 | 12 | [8 empty] | 0 | 12 | NO DATA in team file — physically recount
188 | Boom System | Rail fixing support hanging rod 20*1.5 | Pcs | 6 | 6 | [8 empty] | 0 | 6 | NO DATA in team file — physically recount
189 | Boom System | Main rail pipe 1 70*40*1.5 | Pcs | 66 | 66 | [8 empty] | 0 | 66 | NO DATA in team file — physically recount
190 | Boom System | Main rail pipe 2 70*40*1.5 | Pcs | 6 | 6 | [8 empty] | 0 | 6 | NO DATA in team file — physically recount
191 | Boom System | Transfer rail pipe 70*40*1.5 | Pcs | 14 | 14 | [8 empty] | 0 | 14 | NO DATA in team file — physically recount
192 | Boom System | Transfer rail pipe 70*40*1.5 | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
193 | Boom System | Transfer rail longitudinal beam 80*40*1.5 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
194 | Boom System | Transfer rail longitudinal beam 80*40*2 | Pcs | 8 | 8 | [8 empty] | 0 | 8 | NO DATA in team file — physically recount
195 | Boom System | End beam 80*40*2 | Pcs | 3 | 3 | [8 empty] | 0 | 3 | NO DATA in team file — physically recount
196 | Boom System | Adjusting rod | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
197 | Boom System | U-bolt φ32 | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
198 | Boom System | Turnbuckle M8 | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
199 | Boom System | Stainless steel wire φ3 | Pcs | 10 | 10 | [8 empty] | 0 | 10 | NO DATA in team file — physically recount
200 | Boom System | Rope clamp φ3 | Pcs | 12 | 12 | [8 empty] | 0 | 12 | NO DATA in team file — physically recount
201 | Boom System | Cross rod φ33.2 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
202 | Boom System | Balance rod | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
203 | Boom System | Adjusting rod screw lock block 32 | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
204 | Boom System | Corrugated pipe | Pcs | 8 | 8 | [8 empty] | 0 | 8 | NO DATA in team file — physically recount
205 | Boom System | Electric wire 1 2*1.5 | Pcs | 30 | 30 | [8 empty] | 0 | 30 | NO DATA in team file — physically recount
206 | Boom System | Electric wire 2 2*1.5+2*0.3 | Pcs | 90 | 90 | [8 empty] | 0 | 90 | NO DATA in team file — physically recount
207 | Boom System | Electric wire 3 3*0.5 | Pcs | 70 | 70 | [8 empty] | 0 | 70 | NO DATA in team file — physically recount
208 | Boom System | Nylon cable tie Black-250 | Pcs | 2 | 2 | 2 | [7 empty] | 2 |  | OK
209 | Boom System | Pulley | Pcs | 38 | 38 | [8 empty] | 0 | 38 | NO DATA in team file — physically recount
210 | Boom System | Double corner connector | Pcs | 14 | 14 | [8 empty] | 0 | 14 | NO DATA in team file — physically recount
211 | Boom System | Fixing clamp 80*40 | Pcs | 14 | 14 | [8 empty] | 0 | 14 | NO DATA in team file — physically recount
212 | Boom System | Fixing clamp 40*80 | Pcs | 12 | 12 | [8 empty] | 0 | 12 | NO DATA in team file — physically recount
213 | Boom System | Fixing clamp T40*70 | Pcs | 14 | 14 | [8 empty] | 0 | 14 | NO DATA in team file — physically recount
214 | Boom System | End clamp 30*50 | Pcs | 82 | 82 | 119 |  |  |  | 119 |  |  |  | 119 | -37 | EXCESS 37
215 | Boom System | End clamp 40*80 | Pcs | 30 | 30 | 30 |  |  |  | 30 |  |  |  | 30 |  | OK
216 | Boom System | End clamp 32 | Pcs | 6 | 6 | [8 empty] | 0 | 6 | NO DATA in team file — physically recount
217 | Boom System | Power conversion box 1 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
218 | Boom System | Sprinkler control box 1 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
219 | Boom System | Sprinkler control box 2 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
220 | Boom System | Light sensor | Pcs | 3 | 3 | [8 empty] | 0 | 3 | NO DATA in team file — physically recount
221 | Boom System | Infrared sensor | Pcs | 6 | 6 | [8 empty] | 0 | 6 | NO DATA in team file — physically recount
222 | Boom System | Light sensor fixing connector | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
223 | Boom System | Automatic track-changing light sensor fixing connector | Pcs | 4 | 4 |  |  |  |  | 176 |  |  |  | 0 | -172 | EXCESS 172 · RECEIVED not recorded
224 | Boom System | Automatic track-changing light sensor | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
225 | Boom System | Proximity open pipe | Pcs | 5 | 5 | [8 empty] | 0 | 5 | NO DATA in team file — physically recount
226 | Boom System | Self-tapping screw M5*25 | Pcs | 100 | 100 | [8 empty] | 0 | 100 | NO DATA in team file — physically recount
227 | Boom System | High-pressure host 10L/min | Pcs | 1 | 1 | 1 | [7 empty] | 1 |  | OK
228 | Boom System | End single-hole spray seat φ9.52 | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
229 | Boom System | Bidirectional single-hole spray seat φ9.52 | Pcs | 24 | 24 | [8 empty] | 0 | 24 | NO DATA in team file — physically recount
230 | Boom System | Top-pressure three-way connector φ9.52 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
231 | Boom System | High-pressure stainless steel pipe φ9.52 | Pcs | 24 | 24 | [8 empty] | 0 | 24 | NO DATA in team file — physically recount
232 | Boom System | High-pressure stainless steel pipe φ9.52 | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
233 | Boom System | Atomizing nozzle | Pcs | 90 | 90 | [8 empty] | 0 | 90 | NO DATA in team file — physically recount
234 | Boom System | Filter | Pcs | 1 | 1 | 1 | [7 empty] | 1 |  | OK
235 | Boom System | High-pressure valve seat | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
236 | Boom System | High-pressure pipe 2m | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
237 | Boom System | PA pressure regulating valve VB130 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
238 | Boom System | High-pressure pe pipe | Pcs | 100 | 100 | [8 empty] | 0 | 100 | NO DATA in team file — physically recount
239 | Boom System | Compression male straight connector | Pcs | 3 | 3 | [8 empty] | 0 | 3 | NO DATA in team file — physically recount
240 | Boom System | Quick-connect male straight connector | Pcs | 3 | 3 | [8 empty] | 0 | 3 | NO DATA in team file — physically recount
241 | Boom System | Double female straight connector | Pcs | 3 | 3 | [8 empty] | 0 | 3 | NO DATA in team file — physically recount
242 | Boom System | Compression elbow | Pcs | 4 | 4 | [8 empty] | 0 | 4 | NO DATA in team file — physically recount
243 | Boom System | Three-way spray base | Pcs | 26 | 26 | [8 empty] | 0 | 26 | NO DATA in team file — physically recount
244 | Boom System | Water supply PVC female straight connector φ25 | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
245 | Boom System | Water supply PVC male straight connector φ25 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
246 | Boom System | PTFE tape | Pcs | 1 | 1 | 1 | [7 empty] | 1 |  | OK
247 | Boom System | Shock-absorbing rubber pad | Pcs | 10 | 10 | [8 empty] | 0 | 10 | NO DATA in team file — physically recount
|  | TOTALS — Container 1 |  | 43601 |  | 25166 | 2177 | 313 | 0 | 20964 | 0 | 0 | 13 |  | 10490

## Container 2
No | Section | Item (container list) | Unit | Container Qty | Team Listed | Received | → Project 15 | → Project 12 | Warehouse C | Warehouse E | Doc's WH | Warehouse | Return | Ending Bal | MISSING / UNACCOUNTED | Status / Audit note
1 | Greenhouse Main Structure Pipe | Reinforcement bar φ12 | M | 1100 | 1100 | 1100 | [7 empty] | 1100 |  | OK
2 | Greenhouse Main Structure Pipe | Ring beam stirrup φ6 | Pcs | 1150 | 1150 | 1100 | [7 empty] | 1100 | 50 | MISSING 50
3 | Greenhouse Main Structure Pipe | Reinforcement bar φ8 | M | 3200 | 3200 | 3348 | [7 empty] | 3348 | -148 | EXCESS 148
4 | Greenhouse Main Structure Pipe | Gutter stirrup φ6 | Pcs | 1200 | 1200 | 1200 | [7 empty] | 1200 |  | OK
5 | Greenhouse Main Structure Pipe | Steel pin 25 | Pcs | 4 | 4 | 4 |  |  |  | 4 |  |  |  | 4 |  | OK
6 | Greenhouse Main Structure Pipe | Flat iron S4*40 | M | 180 | 180 | 180 |  |  |  | 180 |  |  |  | 180 |  | OK
7 | Greenhouse Main Structure Pipe | Point foundation reinforcement bar φ16 1 | Pcs | 376 | 376 | 275 | [7 empty] | 275 | 101 | MISSING 101
8 | Greenhouse Main Structure Pipe | Point foundation stirrup | Pcs | 440 | 440 | [9 empty] | 440 | NO DATA in team file — physically recount
9 | Greenhouse Main Structure Pipe | Main column 120*120*3 4 | Pcs | 30 | 4 |  | 4 | [7 empty] | 26 | MISSING 26 · matched to team row "Corner Column 4" — verify; RECEIVED not recorded; team qty 4 vs list 30
10 | Greenhouse Main Structure Pipe | End column 120*60*3 6 | Pcs | 12 | [10 empty] | 12 | NOT IN TEAM FILE — whole line unaccounted
11 | Greenhouse Main Structure Pipe | End column 120*60*3 5.38 | Pcs | 12 | 30 | 30 | 119 | [6 empty] | 0 | -107 | EXCESS 107 · matched to team row "Main Column 1 120x120x3" — verify; team qty 30 vs list 12; book gap: received 30 vs accounted 119
12 | Greenhouse Main Structure Pipe | Door beam 120*60*3 1.94 | Pcs | 2 | 2 | 2 | 2 | [6 empty] | 0 |  | OK
13 | Greenhouse Main Structure Pipe | Door column 120*60*3 2 | Pcs | 4 | 4 | 4 | 4 | [6 empty] | 0 |  | OK
14 | Greenhouse Main Structure Pipe | Gutter k500-2 4 | Pcs | 24 | 24 | 24 | 24 | [6 empty] | 0 |  | OK
15 | Greenhouse Main Structure Pipe | Gutter k500-2 2 | Pcs | 4 | 4 | 4 | 80 | [6 empty] | 0 | -76 | EXCESS 76 · book gap: received 4 vs accounted 80
16 | Greenhouse Main Structure Pipe | End beam/inner beam 50*30*2 9.88 | Pcs | 45 | 45 | 46 | [7 empty] | 46 | -1 | EXCESS 1
17 | Greenhouse Main Structure Pipe | End girt beam K50*30*1.5 8 | Pcs | 24 | 24 | 24 |  | 24 | [5 empty] | 24 | -24 | EXCESS 24 · book gap: received 24 vs accounted 48
18 | Greenhouse Main Structure Pipe | End girt beam K50*30*1.5 2 | Pcs | 24 | 24 | 24 | [7 empty] | 24 |  | OK
19 | Greenhouse Main Structure Pipe | End girt beam K50*30*1.5 6 | Pcs | 6 | 6 | [8 empty] | 0 | 6 | NO DATA in team file — physically recount
20 | Greenhouse Main Structure Pipe | Fan column K50*30*1.5 1.45 | Pcs | 30 | 30 | 30 | [7 empty] | 30 |  | OK
21 | Greenhouse Main Structure Pipe | Middle arch 1 51*1.5 5.5 | Pcs | 45 | 45 | 45 | 1 | 45 | [5 empty] | 44 | -45 | EXCESS 45 · matched to team row "Middle Arc 1 51x1.5" — verify; book gap: received 45 vs accounted 90
22 | Greenhouse Main Structure Pipe | Middle arch 2 51*1.5 5.5 | Pcs | 45 | 45 | 45 |  | 45 | [5 empty] | 45 | -45 | EXCESS 45 · matched to team row "Middle Arc 2 51x1.5" — verify; book gap: received 45 vs accounted 90
23 | Greenhouse Main Structure Pipe | Middle arch 3 48*2 5.54 | Pcs | 78 | 78 | 78 | 1 | 78 | [5 empty] | 77 | -78 | EXCESS 78 · matched to team row "Middle Arc 3 48x2" — verify; book gap: received 78 vs accounted 156
24 | Greenhouse Main Structure Pipe | Middle arch 4 48*2 5.54 | Pcs | 78 | 78 | 78 |  | 78 | [5 empty] | 78 | -78 | EXCESS 78 · matched to team row "Middle Arc 4 48x2" — verify; book gap: received 78 vs accounted 156
25 | Greenhouse Main Structure Pipe | Side arch 1 51*1.5 4.9 | Pcs | 30 | 30 | 30 |  | 30 | [5 empty] | 30 | -30 | EXCESS 30 · matched to team row "Side Arc 1 51x1.5" — verify; book gap: received 30 vs accounted 60
26 | Greenhouse Main Structure Pipe | Side arch 2 48*2 5 | Pcs | 52 | 52 | 52 | 1 | 52 | [5 empty] | 51 | -52 | EXCESS 52 · matched to team row "Side Arc 2 48x2" — verify; book gap: received 52 vs accounted 104
27 | Greenhouse Main Structure Pipe | Wind brace 40*2 5.5 | Pcs | 12 | 12 | 12 |  | 12 | [5 empty] | 12 | -12 | EXCESS 12 · book gap: received 12 vs accounted 24
28 | Greenhouse Main Structure Pipe | Roof beam 1 40*2 5.5 | Pcs | 81 | 81 | [8 empty] | 0 | 81 | NO DATA in team file — physically recount
29 | Greenhouse Main Structure Pipe | Roof beam 2 40*2 3.3 | Pcs | 9 | 9 |  |  | 9 | [5 empty] | 0 |  | OK · RECEIVED not recorded
30 | Greenhouse Main Structure Pipe | Inner support beam 1 32*2 2.31 | Pcs | 39 | 39 | 39 |  | 39 | [5 empty] | 39 | -39 | EXCESS 39 · book gap: received 39 vs accounted 78
31 | Greenhouse Main Structure Pipe | Inner support beam 2 32*2 3.09 | Pcs | 78 | 78 | 99 |  | 99 | [5 empty] | 99 | -120 | EXCESS 120 · book gap: received 99 vs accounted 198
32 | Greenhouse Main Structure Pipe | Column brace 32*2 5 | Pcs | 16 | 16 | 16 |  | 16 | [5 empty] | 16 | -16 | EXCESS 16 · book gap: received 16 vs accounted 32
33 | Greenhouse Main Structure Pipe | Side arch diagonal brace 32*2 1.05 | Pcs | 82 | 82 | 82 | [7 empty] | 82 |  | OK
34 | Greenhouse Main Structure Pipe | Anti-wind support beam 32*32 4 | Pcs | 82 | 82 | [8 empty] | 0 | 82 | NO DATA in team file — physically recount
35 | Greenhouse Accessories | Anchor bolt M16*320 | Pcs | 632 | 632 | 632 |  |  |  | 633 |  |  |  | 632 | -1 | EXCESS 1 · book gap: received 632 vs accounted 633
36 | Greenhouse Accessories | Foundation plate 150*150 | Pcs | 158 | 158 | 158 |  |  |  | 100 |  |  |  | 158 |  | OK
37 | Ventilation System | Climbing pole 25*2 4.5 | Pcs | 2 | 2 | 2 |  | 2 | [5 empty] | 2 | -2 | EXCESS 2 · book gap: received 2 vs accounted 4
38 | Ventilation System | Insert pipe 25*2 4.5 | Pcs | 2 | 2 | 2 |  | 2 | [5 empty] | 2 | -2 | EXCESS 2 · book gap: received 2 vs accounted 4
39 | Ventilation System | Rolling pipe P36-1 6 | Pcs | 35 | 35 | 35 |  | 35 | [5 empty] | 35 | -35 | EXCESS 35 · book gap: received 35 vs accounted 70
40 | Ventilation System | Double lock channel S1.2 with coating | M | 420 | 420 | 420 |  | 420 | [5 empty] | 420 | -420 | EXCESS 420 · book gap: received 420 vs accounted 840
41 | Ventilation System | Wiggle wire | M | 3720 | 3720 | 3720 |  |  | 360 |  |  |  |  | 3720 |  | OK
42 | Ventilation System | Window frame 1 5.6 | m | 2 | 2 | 2 | [7 empty] | 2 |  | OK
43 | Ventilation System | Window frame 2 6.3 | Pcs | 2 | 2 | 2 | [7 empty] | 2 |  | OK
44 | Ventilation System | Square pipe K50*30*1.5 1.7 | Pcs | 4 | 4 | 4 | [7 empty] | 4 |  | OK
45 | Drainage System | Downspout φ110 4 | Pcs | 4 | 4 | 4 | [7 empty] | 4 |  | OK · matched to team row "Dowspout 110" — verify
46 | Cooling System | Cooling pad sealing edge C1*60*120*60 1.91 | Pcs | 12 | 12 | 12 | [7 empty] | 12 |  | OK
47 | Cooling System | Cooling pad sealing edge C1*60*120*60 1.94 | Pcs | 18 | 18 | 18 | [7 empty] | 18 |  | OK
48 | Cooling System | Cooling pad sealing edge C1*60*120*60 1.75 | Pcs | 2 | 2 | 2 | [7 empty] | 2 |  | OK
49 | Shading System | Inner longitudinal beam 40*1.5 5 | Pcs | 6 | 6 | 6 |  | 6 | [5 empty] | 6 | -6 | EXCESS 6 · book gap: received 6 vs accounted 12
50 | Shading System | Inner longitudinal beam 40*1.5 3.7 | Pcs | 12 | 12 | 12 |  | 12 | [5 empty] | 12 | -12 | EXCESS 12 · book gap: received 12 vs accounted 24
51 | Shading System | Rack 2.75 3.95 | Pcs | 9 | 9 | 9 | [7 empty] | 9 |  | OK
52 | Shading System | Push-pull pipe 32*1.5 4.07 | Pcs | 90 | 90 | 90 |  | 90 | [5 empty] | 90 | -90 | EXCESS 90 · book gap: received 90 vs accounted 180
53 | Shading System | Push net rod ZM33-D 6 | Pcs | 60 | 60 | 60 | [7 empty] | 60 |  | OK
54 | Buffer Room | Main column 1 120*60*3 2.2 | Pcs | 4 | 4 | 4 |  | 4 | [5 empty] | 4 | -4 | EXCESS 4 · book gap: received 4 vs accounted 8
55 | Buffer Room | Main column 2 120*60*3 2.4 | Pcs | 2 | 2 | 2 |  | 2 | [5 empty] | 2 | -2 | EXCESS 2 · book gap: received 2 vs accounted 4
56 | Buffer Room | Roof truss 120*60*3 2.94 | Pcs | 4 | 4 | 4 |  | 4 | [5 empty] | 4 | -4 | EXCESS 4 · book gap: received 4 vs accounted 8
57 | Buffer Room | Roof beam 50*30*2 1.94 | Pcs | 33 | 33 | [8 empty] | 0 | 33 | NO DATA in team file — physically recount
58 | Buffer Room | PC sheet 10mm 3 1.99 | Pcs | 3 | 3 | 3 |  | 4 | [5 empty] | 3 | -4 | EXCESS 4 · book gap: received 3 vs accounted 7
59 | Buffer Room | Bottom part JP-J06 6 | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
60 | Buffer Room | Roof truss edge sealing sheet L1*50*50 4 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
61 | Buffer Room | Roof truss edge sealing sheet L1*50*50 2 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
62 | Buffer Room | Roof truss edge sealing sheet L1*50*50 3.05 | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
63 | Buffer Room | Roof truss edge sealing sheet L1*75*50 4 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
64 | Buffer Room | Roof truss edge sealing sheet L1*75*50 2 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
65 | NFT Table | Table leg | Pcs | 102 | 102 | 305 |  |  |  | 305 |  |  |  | 305 | -203 | EXCESS 203
66 | NFT Table | Table bracket | Pcs | 66 | 66 | 66 | [7 empty] | 66 |  | OK
67 | NFT Table | Leg brace 25*2 3 | Pcs | 24 | 24 | 24 |  | 24 | [5 empty] | 24 | -24 | EXCESS 24 · book gap: received 24 vs accounted 48
68 | NFT Table | Longitudinal tube 1 42*2 5.5 | Pcs | 240 | 240 | 240 |  | 282 | [5 empty] | 240 | -282 | EXCESS 282 · book gap: received 240 vs accounted 522
69 | NFT Table | Longitudinal tube 2 42*2 4.72 | Pcs | 30 | 30 | 30 |  | 30 | [5 empty] | 30 | -30 | EXCESS 30 · book gap: received 30 vs accounted 60
70 | NFT Table | Longitudinal tube 3 25*2 6 | Pcs | 126 | 126 | 126 |  | 126 | [5 empty] | 126 | -126 | EXCESS 126 · matched to team row "Longhitudinal Tube 3 25x2" — verify; book gap: received 126 vs accounted 252
71 | NFT Table | Longitudinal tube 4 25*2 6.63 | Pcs | 18 | 18 | 18 |  | 18 | [5 empty] | 18 | -18 | EXCESS 18 · matched to team row "Longhitudinal Tube 4 25x2" — verify; book gap: received 18 vs accounted 36
72 | NFT Table | Steel pipe 32*2 0.2 | Pcs | 170 | 170 | 143 | [7 empty] | 143 | 27 | MISSING 27
73 | Boom System | Main frame | Pcs | 1 | 1 | 1 | [7 empty] | 1 |  | OK
74 | Boom System | Transfer cart main frame | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
75 | Boom System | Rail fixing support frame | Pcs | 3 | 3 | 3 | [7 empty] | 3 |  | OK
76 | Boom System | Transfer rail fixing support frame | Pcs | 6 | 6 | 6 | [7 empty] | 6 |  | OK
77 | Boom System | Main support hanging bracket 1 | Pcs | 36 | 36 | 33 | [7 empty] | 33 | 3 | MISSING 3
78 | Boom System | Main support hanging bracket 2 | Pcs | 7 | 7 | [8 empty] | 0 | 7 | NO DATA in team file — physically recount
79 | Boom System | Auxiliary support hanging bracket 1 | Pcs | 36 | 36 | [8 empty] | 0 | 36 | NO DATA in team file — physically recount
80 | Boom System | Auxiliary support hanging bracket 2 | Pcs | 7 | 7 | [8 empty] | 0 | 7 | NO DATA in team file — physically recount
81 | Boom System | Main rail hanging rod 20*1.5 | Pcs | 72 | 72 | 74 |  | 74 | [5 empty] | 74 | -76 | EXCESS 76 · book gap: received 74 vs accounted 148
82 | Boom System | Transfer rail hanging rod 20*1.5 | Pcs | 14 | 14 | 14 |  | 14 | [5 empty] | 14 | -14 | EXCESS 14 · book gap: received 14 vs accounted 28
83 | Boom System | Rail fixing frame hanging rod 20*1.5 | Pcs | 12 | 12 | 12 |  | 12 | [5 empty] | 12 | -12 | EXCESS 12 · book gap: received 12 vs accounted 24
84 | Boom System | Rail fixing support hanging rod 20*1.5 | Pcs | 6 | 6 | 6 | [7 empty] | 6 |  | OK
85 | Boom System | Main rail pipe 1 70*40*1.5 | Pcs | 66 | 66 | 66 |  | 66 | [5 empty] | 66 | -66 | EXCESS 66 · book gap: received 66 vs accounted 132
86 | Boom System | Main rail pipe 2 70*40*1.5 | Pcs | 6 | 6 | 6 |  | 6 | [5 empty] | 6 | -6 | EXCESS 6 · book gap: received 6 vs accounted 12
87 | Boom System | Transfer rail pipe 70*40*1.5 | Pcs | 14 | 14 | 14 |  | 14 | [5 empty] | 14 | -14 | EXCESS 14 · book gap: received 14 vs accounted 28
88 | Boom System | Transfer rail pipe 70*40*1.5 | Pcs | 2 | 2 | 2 |  | 2 | [5 empty] | 2 | -2 | EXCESS 2 · book gap: received 2 vs accounted 4
89 | Boom System | Transfer rail longitudinal beam 80*40*1.5 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
90 | Boom System | Transfer rail longitudinal beam 80*40*2 | Pcs | 8 | 8 | 8 | [7 empty] | 8 |  | OK
91 | Boom System | End beam 80*40*2 | Pcs | 3 | 3 | 3 | [7 empty] | 3 |  | OK
92 | Boom System | Adjusting rod | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
93 | Boom System | Cross rod 2 | Pcs | 1 | 1 | [8 empty] | 0 | 1 | NO DATA in team file — physically recount
94 | Boom System | Balance rod φ33.2 4.5 | Pcs | 2 | 2 | [8 empty] | 0 | 2 | NO DATA in team file — physically recount
95 | Other | Greenhouse film tape 10cm *50m | Pcs | 81 | 81 | 81 |  |  |  |  | 81 |  |  | 81 |  | OK
96 | Other | Greenhouse film tape 30cm *50m | Pcs | 27 | 27 | 27 |  |  |  |  | 27 |  |  | 27 |  | OK
97 | Other | Forklift | Pcs | 1 | 1 | 1 | [5 empty] | 1 |  | 1 |  | OK
98 | Other | Entrance door | Pcs | 4 | 4 | 4 | [7 empty] | 4 |  | OK
99 | Other | Excavator door | Pcs | 1 | 1 | 1 |  |  |  | 5 |  | 1 |  | 3 | -5 | EXCESS 5 · book gap: received 1 vs accounted 6
|  | TOTALS — Container 2 |  | 15034 |  | 14488 | 236 | 1776 | 360 | 1227 | 108 | 2 | 0 |  | 926

## MISSING ITEMS
Container | No | Section | Item | Unit | Container Qty | Accounted | MISSING | Why
Container 1 | 80 | Ventilation System | Fixing film rope White | M | 2400 | 0 | 2400 | NO DATA in team file — physically recount
Container 1 | 165 | Irrigation Room | Self-drilling screw Square head M5.5*25 | Pcs | 1000 | 0 | 1000 | NO DATA in team file — physically recount
Container 1 | 171 | Irrigation Room | Presser φ3 | Pcs | 800 | 0 | 800 | NO DATA in team file — physically recount
Container 1 | 114 | Shading System | Self-tapping screw stainless steel M5.5*19 | Pcs | 570 | 0 | 570 | NO DATA in team file — physically recount
Container 1 | 7 | Greenhouse Main Structure Pipe | Point foundation | Pcs | 440 | 0 | 440 | NO DATA in team file — physically recount
Container 1 | 76 | Ventilation System | Double lock channel S1.2 with coating | M | 420 | 0 | 420 | NO DATA in team file — physically recount
Container 1 | 148 | NFT Table | Horizontal and vertical rod connector | Pcs | 408 | 0 | 408 | NO DATA in team file — physically recount
Container 1 | 81 | Ventilation System | Film hook | Pcs | 300 | 0 | 300 | NO DATA in team file — physically recount
Container 1 | 136 | Buffer Room | Self-drilling screw Square head M5.5*38 | Pcs | 300 | 0 | 300 | NO DATA in team file — physically recount
Container 1 | 96 | Cooling System | Corner connector | Pcs | 290 | 0 | 290 | NO DATA in team file — physically recount
Container 1 | 151 | NFT Table | Longitudinal tube 1 42*2 5.5 | Pcs | 240 | 0 | 240 | NO DATA in team file — physically recount
Container 1 | 37 | Greenhouse Accessories | Anchor bolt M16*320 | Pcs | 792 | 597 | 195 | MISSING 195 · book gap: received 582 vs accounted 597
Container 1 | 173 | Irrigation Room | T-clamp 32*32 | Pcs | 170 | 0 | 170 | NO DATA in team file — physically recount
Container 1 | 55 | Greenhouse Accessories | End clamp 30*50 | Pcs | 121 | 0 | 121 | NO DATA in team file — physically recount
Container 1 | 47 | Greenhouse Accessories | Girt beam clamp 60*120 double head | Pcs | 112 | 0 | 112 | NO DATA in team file — physically recount
Container 1 | 118 | Shading System | Push net rod clamp 32 | Pcs | 108 | 0 | 108 | NO DATA in team file — physically recount
Container 1 | 65 | Greenhouse Accessories | Corner connector 70*80*95 | Pcs | 104 | 0 | 104 | NO DATA in team file — physically recount
Container 1 | 226 | Boom System | Self-tapping screw M5*25 | Pcs | 100 | 0 | 100 | NO DATA in team file — physically recount
Container 1 | 238 | Boom System | High-pressure pe pipe | Pcs | 100 | 0 | 100 | NO DATA in team file — physically recount
Container 1 | 163 | Irrigation Room | Double corner connector | Pcs | 96 | 0 | 96 | NO DATA in team file — physically recount
Container 1 | 206 | Boom System | Electric wire 2 2*1.5+2*0.3 | Pcs | 90 | 0 | 90 | NO DATA in team file — physically recount
Container 1 | 233 | Boom System | Atomizing nozzle | Pcs | 90 | 0 | 90 | NO DATA in team file — physically recount
Container 1 | 36 | Greenhouse Main Structure Pipe | Anti-wind support beam 32*32 4 | Pcs | 82 | 0 | 82 | NO DATA in team file — physically recount
Container 1 | 30 | Greenhouse Main Structure Pipe | Roof beam 1 40*2 5.5 | Pcs | 81 | 0 | 81 | NO DATA in team file — physically recount
Container 1 | 172 | Irrigation Room | Arch connector 51 | Pcs | 80 | 0 | 80 | NO DATA in team file — physically recount
Container 1 | 25 | Greenhouse Main Structure Pipe | Middle arch 3 48*2 5.54 | Pcs | 78 | 0 | 78 | NO DATA in team file — physically recount
Container 1 | 185 | Boom System | Main rail hanging rod 20*1.5 | Pcs | 72 | 0 | 72 | NO DATA in team file — physically recount
Container 1 | 207 | Boom System | Electric wire 3 3*0.5 | Pcs | 70 | 0 | 70 | NO DATA in team file — physically recount
Container 1 | 189 | Boom System | Main rail pipe 1 70*40*1.5 | Pcs | 66 | 0 | 66 | NO DATA in team file — physically recount
Container 1 | 115 | Shading System | Push net rod ZM33-D 5.8 | Pcs | 60 | 0 | 60 | NO DATA in team file — physically recount
Container 1 | 147 | NFT Table | Adjusting bolt 40*20 | Pcs | 306 | 248 | 58 | MISSING 58 · RECEIVED not recorded
Container 1 | 13 | Greenhouse Main Structure Pipe | Side secondary column 120*60*3 4 | Pcs | 52 | 0 | 52 | NO DATA in team file — physically recount
Container 1 | 28 | Greenhouse Main Structure Pipe | Side arch 2 48*2 5 | Pcs | 52 | 0 | 52 | NO DATA in team file — physically recount
Container 1 | 38 | Greenhouse Accessories | Foundation plate 150*150 | Pcs | 207 | 159 | 48 | MISSING 48 · book gap: received 153 vs accounted 159
Container 1 | 61 | Greenhouse Accessories | Double head clamp 120*120 | Pcs | 48 | 0 | 48 | NO DATA in team file — physically recount
Container 1 | 23 | Greenhouse Main Structure Pipe | Middle arch 1 51*1.5 5.5 | Pcs | 45 | 0 | 45 | NO DATA in team file — physically recount
Container 1 | 32 | Greenhouse Main Structure Pipe | Inner support beam 1 32*2 2.31 | Pcs | 39 | 0 | 39 | NO DATA in team file — physically recount
Container 1 | 209 | Boom System | Pulley | Pcs | 38 | 0 | 38 | NO DATA in team file — physically recount
Container 1 | 101 | Shading System | Double head clamp 32 | Pcs | 36 | 0 | 36 | NO DATA in team file — physically recount
Container 1 | 181 | Boom System | Main support hanging bracket 1 | Pcs | 36 | 0 | 36 | NO DATA in team file — physically recount
Container 1 | 183 | Boom System | Auxiliary support hanging bracket 1 | Pcs | 36 | 0 | 36 | NO DATA in team file — physically recount
Container 1 | 74 | Ventilation System | Rolling pipe P36-1 6 | Pcs | 35 | 0 | 35 | NO DATA in team file — physically recount
Container 1 | 113 | Shading System | Push-pull pipe | Pcs | 90 | 58 | 32 | MISSING 32 · RECEIVED not recorded
Container 1 | 9 | Greenhouse Main Structure Pipe | Main column 120*120*3 4 | Pcs | 30 | 0 | 30 | NO DATA in team file — physically recount
Container 1 | 27 | Greenhouse Main Structure Pipe | Side arch 1 51*1.5 4.9 | Pcs | 30 | 0 | 30 | NO DATA in team file — physically recount
Container 1 | 44 | Greenhouse Accessories | Girt beam connector K50*30 | Pcs | 30 | 0 | 30 | NO DATA in team file — physically recount
Container 1 | 152 | NFT Table | Longitudinal tube 2 42*2 4.72 | Pcs | 30 | 0 | 30 | NO DATA in team file — physically recount
Container 1 | 205 | Boom System | Electric wire 1 2*1.5 | Pcs | 30 | 0 | 30 | NO DATA in team file — physically recount
Container 1 | 56 | Greenhouse Accessories | Side column - inner beam connector | Pcs | 28 | 0 | 28 | NO DATA in team file — physically recount
Container 1 | 57 | Greenhouse Accessories | Middle column- inner beam connector | Pcs | 28 | 0 | 28 | NO DATA in team file — physically recount
Container 1 | 12 | Greenhouse Main Structure Pipe | Side column 120*60*3 4 | Pcs | 26 | 0 | 26 | NO DATA in team file — physically recount
Container 1 | 43 | Greenhouse Accessories | Fixing clamp 50*30 | Pcs | 26 | 0 | 26 | NO DATA in team file — physically recount
Container 1 | 243 | Boom System | Three-way spray base | Pcs | 26 | 0 | 26 | NO DATA in team file — physically recount
Container 1 | 19 | Greenhouse Main Structure Pipe | End girt beam K50*30*1.5 8 | Pcs | 24 | 0 | 24 | NO DATA in team file — physically recount
Container 1 | 20 | Greenhouse Main Structure Pipe | End girt beam K50*30*1.5 2 | Pcs | 24 | 0 | 24 | NO DATA in team file — physically recount
Container 1 | 229 | Boom System | Bidirectional single-hole spray seat φ9.52 | Pcs | 24 | 0 | 24 | NO DATA in team file — physically recount
Container 1 | 231 | Boom System | High-pressure stainless steel pipe φ9.52 | Pcs | 24 | 0 | 24 | NO DATA in team file — physically recount
Container 1 | 33 | Greenhouse Main Structure Pipe | Inner support beam 2 32*2 3.09 | Pcs | 78 | 56 | 22 | MISSING 22 · RECEIVED not recorded
Container 1 | 106 | Shading System | Gear seat bolt U30*50 | Pcs | 18 | 0 | 18 | NO DATA in team file — physically recount
Container 1 | 111 | Shading System | Rack connector 32 | Pcs | 18 | 0 | 18 | NO DATA in team file — physically recount
Container 1 | 150 | NFT Table | Double head clamp 20*40 | Pcs | 48 | 30 | 18 | MISSING 18 · RECEIVED not recorded
Container 1 | 60 | Greenhouse Accessories | Double head clamp 60*120 | Pcs | 16 | 0 | 16 | NO DATA in team file — physically recount
Container 1 | 133 | Buffer Room | PC sheet sealing strip JP-J02 | M | 15 | 0 | 15 | NO DATA in team file — physically recount
Container 1 | 48 | Greenhouse Accessories | Girt beam clamp 60*120 double head | Pcs | 14 | 0 | 14 | NO DATA in team file — physically recount
Container 1 | 186 | Boom System | Transfer rail hanging rod 20*1.5 | Pcs | 14 | 0 | 14 | NO DATA in team file — physically recount
Container 1 | 191 | Boom System | Transfer rail pipe 70*40*1.5 | Pcs | 14 | 0 | 14 | NO DATA in team file — physically recount
Container 1 | 210 | Boom System | Double corner connector | Pcs | 14 | 0 | 14 | NO DATA in team file — physically recount
Container 1 | 211 | Boom System | Fixing clamp 80*40 | Pcs | 14 | 0 | 14 | NO DATA in team file — physically recount
Container 1 | 213 | Boom System | Fixing clamp T40*70 | Pcs | 14 | 0 | 14 | NO DATA in team file — physically recount
Container 1 | 11 | Greenhouse Main Structure Pipe | End column 120*60*3 5.38 | Pcs | 12 | 0 | 12 | NO DATA in team file — physically recount
Container 1 | 116 | Shading System | Push net rod ZM33-D 1 | Pcs | 12 | 0 | 12 | NO DATA in team file — physically recount
Container 1 | 137 | Buffer Room | Aluminum foil tape | M | 12 | 0 | 12 | NO DATA in team file — physically recount
Container 1 | 187 | Boom System | Rail fixing frame hanging rod 20*1.5 | Pcs | 12 | 0 | 12 | NO DATA in team file — physically recount
Container 1 | 200 | Boom System | Rope clamp φ3 | Pcs | 12 | 0 | 12 | NO DATA in team file — physically recount
Container 1 | 212 | Boom System | Fixing clamp 40*80 | Pcs | 12 | 0 | 12 | NO DATA in team file — physically recount
Container 1 | 199 | Boom System | Stainless steel wire φ3 | Pcs | 10 | 0 | 10 | NO DATA in team file — physically recount
Container 1 | 247 | Boom System | Shock-absorbing rubber pad | Pcs | 10 | 0 | 10 | NO DATA in team file — physically recount
Container 1 | 105 | Shading System | Gear seat | Pcs | 9 | 0 | 9 | NO DATA in team file — physically recount
Container 1 | 126 | Buffer Room | Roof beam 50*30*2 1.94 | Pcs | 9 | 0 | 9 | NO DATA in team file — physically recount · team qty differs
Container 1 | 194 | Boom System | Transfer rail longitudinal beam 80*40*2 | Pcs | 8 | 0 | 8 | NO DATA in team file — physically recount
Container 1 | 204 | Boom System | Corrugated pipe | Pcs | 8 | 0 | 8 | NO DATA in team file — physically recount
Container 1 | 107 | Shading System | Shaft pipe 33.4*2.75 3.57 | Pcs | 7 | 0 | 7 | NO DATA in team file — physically recount
Container 1 | 182 | Boom System | Main support hanging bracket 2 | Pcs | 7 | 0 | 7 | NO DATA in team file — physically recount
Container 1 | 184 | Boom System | Auxiliary support hanging bracket 2 | Pcs | 7 | 0 | 7 | NO DATA in team file — physically recount
Container 1 | 21 | Greenhouse Main Structure Pipe | End girt beam K50*30*1.5 6 | Pcs | 6 | 0 | 6 | NO DATA in team file — physically recount
Container 1 | 99 | Shading System | Inner longitudinal beam 40*1.5 5 | Pcs | 6 | 0 | 6 | NO DATA in team file — physically recount
Container 1 | 180 | Boom System | Transfer rail fixing support frame | Pcs | 6 | 0 | 6 | NO DATA in team file — physically recount
Container 1 | 188 | Boom System | Rail fixing support hanging rod 20*1.5 | Pcs | 6 | 0 | 6 | NO DATA in team file — physically recount
Container 1 | 190 | Boom System | Main rail pipe 2 70*40*1.5 | Pcs | 6 | 0 | 6 | NO DATA in team file — physically recount
Container 1 | 216 | Boom System | End clamp 32 | Pcs | 6 | 0 | 6 | NO DATA in team file — physically recount
Container 1 | 221 | Boom System | Infrared sensor | Pcs | 6 | 0 | 6 | NO DATA in team file — physically recount
Container 1 | 225 | Boom System | Proximity open pipe | Pcs | 5 | 0 | 5 | NO DATA in team file — physically recount
Container 1 | 8 | Greenhouse Main Structure Pipe | Corner column 120*120*3 4 | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 69 | Ventilation System | Roll-up device 230V 60HZ 100W | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 70 | Ventilation System | Roll-up device connector 36 | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 71 | Ventilation System | Climber | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 104 | Shading System | Motor seat bolt M10*140 | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 125 | Buffer Room | Roof truss 120*60*3 2.94 | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 127 | Buffer Room | Buffer connection plate 1 | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 130 | Buffer Room | Upper panel connector YG-JP-A08 3 | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 131 | Buffer Room | Lower panel connector YG-JP-A09 3 | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 170 | Irrigation Room | Steel wire mesh 2 1 | Pcs | 54 | 50 | 4 | MISSING 4
Container 1 | 174 | Irrigation Room | T-clamp 20*25 | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 197 | Boom System | U-bolt φ32 | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 198 | Boom System | Turnbuckle M8 | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 203 | Boom System | Adjusting rod screw lock block 32 | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 224 | Boom System | Automatic track-changing light sensor | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 228 | Boom System | End single-hole spray seat φ9.52 | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 242 | Boom System | Compression elbow | Pcs | 4 | 0 | 4 | NO DATA in team file — physically recount
Container 1 | 195 | Boom System | End beam 80*40*2 | Pcs | 3 | 0 | 3 | NO DATA in team file — physically recount
Container 1 | 220 | Boom System | Light sensor | Pcs | 3 | 0 | 3 | NO DATA in team file — physically recount
Container 1 | 239 | Boom System | Compression male straight connector | Pcs | 3 | 0 | 3 | NO DATA in team file — physically recount
Container 1 | 240 | Boom System | Quick-connect male straight connector | Pcs | 3 | 0 | 3 | NO DATA in team file — physically recount
Container 1 | 241 | Boom System | Double female straight connector | Pcs | 3 | 0 | 3 | NO DATA in team file — physically recount
Container 1 | 72 | Ventilation System | Climbing pole 25*2 4.5 | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 1 | 73 | Ventilation System | Insert pipe 25*2 4.5 | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 1 | 95 | Cooling System | Cooling pad sealing edge C1*60*120*60 1.75 | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 1 | 128 | Buffer Room | Buffer connection plate 2 | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 1 | 132 | Buffer Room | Bottom part JP-J06 6 | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 1 | 138 | Buffer Room | Black structural adhesive | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 1 | 141 | Buffer Room | Roof truss edge sealing sheet L1*50*50 3.05 | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 1 | 192 | Boom System | Transfer rail pipe 70*40*1.5 | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 1 | 196 | Boom System | Adjusting rod | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 1 | 202 | Boom System | Balance rod | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 1 | 232 | Boom System | High-pressure stainless steel pipe φ9.52 | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 1 | 244 | Boom System | Water supply PVC female straight connector φ25 | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 1 | 108 | Shading System | Shaft pipe 33.4*2.75 0.97 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 109 | Shading System | Shaft pipe 33.4*2.75 2.34 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 139 | Buffer Room | Roof truss edge sealing sheet L1*50*50 4 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 140 | Buffer Room | Roof truss edge sealing sheet L1*50*50 2 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 142 | Buffer Room | Roof truss edge sealing sheet L1*75*50 4 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 143 | Buffer Room | Roof truss edge sealing sheet L1*75*50 2 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 166 | Irrigation Room | Fertilizer tank platform 50*30*2 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 177 | Boom System | Main frame | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 178 | Boom System | Transfer cart main frame | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 193 | Boom System | Transfer rail longitudinal beam 80*40*1.5 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 201 | Boom System | Cross rod φ33.2 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 217 | Boom System | Power conversion box 1 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 218 | Boom System | Sprinkler control box 1 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 219 | Boom System | Sprinkler control box 2 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 222 | Boom System | Light sensor fixing connector | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 230 | Boom System | Top-pressure three-way connector φ9.52 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 235 | Boom System | High-pressure valve seat | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 236 | Boom System | High-pressure pipe 2m | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 237 | Boom System | PA pressure regulating valve VB130 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 1 | 245 | Boom System | Water supply PVC male straight connector φ25 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 2 | 8 | Greenhouse Main Structure Pipe | Point foundation stirrup | Pcs | 440 | 0 | 440 | NO DATA in team file — physically recount
Container 2 | 7 | Greenhouse Main Structure Pipe | Point foundation reinforcement bar φ16 1 | Pcs | 376 | 275 | 101 | MISSING 101
Container 2 | 34 | Greenhouse Main Structure Pipe | Anti-wind support beam 32*32 4 | Pcs | 82 | 0 | 82 | NO DATA in team file — physically recount
Container 2 | 28 | Greenhouse Main Structure Pipe | Roof beam 1 40*2 5.5 | Pcs | 81 | 0 | 81 | NO DATA in team file — physically recount
Container 2 | 2 | Greenhouse Main Structure Pipe | Ring beam stirrup φ6 | Pcs | 1150 | 1100 | 50 | MISSING 50
Container 2 | 79 | Boom System | Auxiliary support hanging bracket 1 | Pcs | 36 | 0 | 36 | NO DATA in team file — physically recount
Container 2 | 57 | Buffer Room | Roof beam 50*30*2 1.94 | Pcs | 33 | 0 | 33 | NO DATA in team file — physically recount
Container 2 | 72 | NFT Table | Steel pipe 32*2 0.2 | Pcs | 170 | 143 | 27 | MISSING 27
Container 2 | 9 | Greenhouse Main Structure Pipe | Main column 120*120*3 4 | Pcs | 30 | 4 | 26 | MISSING 26 · matched to team row "Corner Column 4" — verify; RECEIVED not recorded; team qty 4 vs list 30
Container 2 | 10 | Greenhouse Main Structure Pipe | End column 120*60*3 6 | Pcs | 12 | 0 | 12 | NOT IN TEAM FILE — whole line unaccounted
Container 2 | 78 | Boom System | Main support hanging bracket 2 | Pcs | 7 | 0 | 7 | NO DATA in team file — physically recount
Container 2 | 80 | Boom System | Auxiliary support hanging bracket 2 | Pcs | 7 | 0 | 7 | NO DATA in team file — physically recount
Container 2 | 19 | Greenhouse Main Structure Pipe | End girt beam K50*30*1.5 6 | Pcs | 6 | 0 | 6 | NO DATA in team file — physically recount
Container 2 | 77 | Boom System | Main support hanging bracket 1 | Pcs | 36 | 33 | 3 | MISSING 3
Container 2 | 59 | Buffer Room | Bottom part JP-J06 6 | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 2 | 62 | Buffer Room | Roof truss edge sealing sheet L1*50*50 3.05 | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 2 | 92 | Boom System | Adjusting rod | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 2 | 94 | Boom System | Balance rod φ33.2 4.5 | Pcs | 2 | 0 | 2 | NO DATA in team file — physically recount
Container 2 | 60 | Buffer Room | Roof truss edge sealing sheet L1*50*50 4 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 2 | 61 | Buffer Room | Roof truss edge sealing sheet L1*50*50 2 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 2 | 63 | Buffer Room | Roof truss edge sealing sheet L1*75*50 4 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 2 | 64 | Buffer Room | Roof truss edge sealing sheet L1*75*50 2 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 2 | 74 | Boom System | Transfer cart main frame | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 2 | 89 | Boom System | Transfer rail longitudinal beam 80*40*1.5 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount
Container 2 | 93 | Boom System | Cross rod 2 | Pcs | 1 | 0 | 1 | NO DATA in team file — physically recount